## 24-01-2023
S# | Name of Canal | Name of Division | Estimated Cost(RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Progress Till date in % | Remarks
1 | Silt Clearance of Disty No.6 from RD: 55+000 to 60+000 in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.1829 | 0.1546 | 22.25 | 0.61 |  |  | Not yet started
2 | Silt Clearance of Disty No.6 from RD: 60+000 to 65+000 in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.1568 | 0.1325 | 22.25 | 0.45 |  |  | Not yet started
3 | Silt Clearance of Disty No.6 from RD: 65+000 to 73+000 in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.1999 | 0.169 | 22.25 | 0.61 | 0.5 | 82% | Work is in progress
4 | Silt Clearance of Nisatta Branch from RD: 0+000 to Tail in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.335 | 0.283 | 11.88 | 1 |  |  | Not yet started
5 | Silt Clearance of Nisatta Minor from RD: 0+000 to Tail in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.217 | 0.184 | 3.35 | 2 |  |  | Not yet started
6 | Silt Clearance of Palosa Minor from RD: 0+000 to Tail in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.252 | 0.213 | 5.05 | 1.35 |  |  | Not yet started
7 | Silt Clearance of Zardad and Kheshki Branch in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.347 | 0.294 | 14.49 | 7 | 1 | 20% | Work is in progress
8 | Shamizai Irrigation Canal | Swat Irrigation Division-II Matta | 1 | 0.779 | 20.73 | 19.5 | 4.57 | 23% | Work is in progress
9 | Barwai Irrigation Canal | Swat Irrigation Division-II Matta | 0.3 | 0.2805 | 11.216 | 6.096 | 1.524 | 25% | Work is in progress
11 | Removal of Heaps / Clearance of Bari Band Disty RD: 39+500-88+600 in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.33775 | 14.96 | 8.21 |  |  | Not yet started
12 | Removal of Heaps / Clearance of Hero Shah Minor RD: 0 -38+000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 11.58 | 11.58 | 0.25 | 2.16 | Work is in progress
13 | Removal of Heaps / Clearance of Kalu Shah Disty and Dundian Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.1 | 0.098 | 7.69 | 5 | 1 | 20% | Work is in progress
14 | Removal of Heaps / Clearance of Sarwala Disty and Lund Khwar Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 18.29 | 10.06 |  |  | Not yet started
15 | Removal of Heaps / Clearance of Said Abad Disty and Pir Abad Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 20.42 | 7.31 |  |  | Not yet started
16 | Removal of Heaps / Clearance of Katlang Disty from RD: 0-40+000 in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 12.19 | 7.61 |  |  | Not yet started
17 | Removal of Heaps / Clearance of Shamozai Disty/ Syphon and Likpani Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.392 | 17.67 | 13.01 | 0.5 | 3.84% | Work is in progress
18 | Removal of Heaps / Clearance of Dheri Minor and Tail Minor Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.15 | 0.147 | 7.01 | 6 | 0.75 | 12.5% | Work is in progress
19 | Bazai Main Canal Head Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 10.5 | 7 | 33% | Work is in progress
20 | Wartair Disty | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 6 | 6 | 5 | 83% | Work is in progress
21 | Kharki Disty No. 02 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 3.3 | 3.3 | 3.3 | 100% | Desiltation Completed
22 | Additional Minor No. 03, 06 and Bazai Disty No. 01. | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | 16.8 | 3 | 1 | 33% | Work is in progress
23 | Bazai Main Canal, Syphon No. 4431, 5851, 12530, 13590, 14842, 18400, 47527 & 58853 | Malakand Irrigation Division Malakand | 0.1 | 0.0975 |  |  |  | 50% | Work is in progress
24 | Bazai Disty No. 04, Bazai Minor No. 09, 11 and 12. | Malakand Irrigation Division Malakand | 0.27 | 0.26625 | 15.2 | 9 | 2 | 22% | Work is in progress
25 | Clearance of Syphon 79205, 93480 and 97962. | Malakand Irrigation Division Malakand | 0.1 | 0.975 |  |  |  |  | Not yet started
26 | Bazai Disty No. 03 and Bazai Minor No. 05. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | 20.5 | 7 |  |  | Not yet started
27 | Bazai Main Canal Tail Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 10.5 |  |  | Not yet started
28 | Silt & Shingle Clearance of P.C Minor from RD 0+000 To Tail in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.3395 |  |  |  |  | Not yet started
29 | Clearance of Shingri Minor from RD 0-17250 in reaches. | Malakand Irrigation Division Malakand | 0.2 | 0.194 |  |  |  |  | Not yet started
30 | Clearance of Meherdi Minor from RD 0-31000 in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2425 |  |  |  |  | Not yet started
31 | Clearance of Kalu Branch from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.33 | 0.3218 |  |  |  |  | Not yet started
32 | Clearance of Hathian Minor from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.05 | 0.04875 |  |  |  |  | Not yet started
33 | Clearance of Jalala Disty from RD: 29000 to Tail in reaches | Malakand Irrigation Division Malakand | 0.37 | 0.3607 |  |  |  |  | Not yet started
34 | Clearance of Pirsaddo Disty, Ghano Minor and Qutab Gharh Minor from : H-Tail to Tail in reaches. | Malakand Irrigation Division Malakand | 0.35 | 0.412 |  |  |  |  | Not yet started
35 | Clearance of Shergarh Minor from Head to Rd:12+000 in reaches. | Malakand Irrigation Division Malakand | 0.15 | 0.146 |  |  |  |  | Not yet started
36 | Clearance of Shergarh Minor from Rd:12+000 tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 |  |  |  |  | Not yet started
37 | Clearance of Spokanda Disty from RD: 18000 to Tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 |  |  |  |  | Not yet started
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086
24-01-2023

## 25-01-2023
S# | Name of Canal | Name of Division | Estimated Cost(RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Total Quantity of Silt to be removed (m3) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Total Quantity of Silt removed till date (m3) | Progress Till date in % | Remarks
1 | Nipki Khel Irrigation Scheme | Swat Irrigation Division -I | 2.2 | 1.76 | 38.87 |  | 38.87 | 4.6 |  | 11.83% | No activity due to rainfall in the area.
2 | Silt clearance from RD:0+00 to RD:8+000 in reaches of Ghazai Khani Flow Irrigation Scheme | Swat Irrigation Division -I | 0.12 | 0.119 | 2.44 |  | 2.44 | 0.3 |  | 12% | In progress
3 | "Silt clearance from RD:0+00 to RD:12+000 in reaches of Karshalizara Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.08 | 0.072 | 3.66 |  | 3.66 | 1.06 |  | 29% | In progress
4 | "Silt clearance from RD:0+00 to RD:20+000 in reaches of Charorai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 6.1 |  | 6.1 | 0.77 |  | 13% | In progress
5 | "Silt clearance from RD:0+00 to RD:12+000 in reaches of Kuriya Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 3.66 |  | 3.66 | 0.91 |  | 25% | In progress
6 | "Silt clearance from RD:0+00 to RD:9+000 in reaches of Elai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 2.74 |  | 2.74 | 0.15244 |  | 6% | In progress
7 | "Silt clearance from RD:0+00 to RD:60+000 in reaches of Budal Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.25 | 0.225 | 18.29 |  | 18.29 | 0 |  | 0% | No activity start at site and will be started soon
8 | "Silt clearance from RD:0+00 to RD:16+000 in reaches of Singarai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.15 | 0.135 | 4.88 |  | 4.88 | 0.91463 |  | 19% | In progress
9 | "Silt clearance from RD:0+00 to RD:26+000 in reaches of Bajkata Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.24 | 0.213 | 7.93 |  | 7.93 | 0.60976 |  | 8% | In progress
10 | Silt clearance of Doaba Canal RD. 0+000-4+500 in Reaches. | Charsadda Irrigation Division Charsadda | 0.226 | 0.144 | 14.7828 |  | 0.48 | 0 |  | 0% | Not yet started
11 | Silt clearance of Doaba Canal RD. 4+600-9+100 in Reaches. | Charsadda Irrigation Division Charsadda | 0.242 | 0.1548 | 14.7828 |  | 0.58 | 0 |  | 0% | Not yet started
12 | Silt clearance of Doaba Canal RD. 9+200-13+000 in Reaches. | Charsadda Irrigation Division Charsadda | 0.343 | 0.22 | 14.7828 |  | 0.548 | 0 |  | 0% | Not yet started
13 | Silt clearance of Doaba Canal RD. 13+200-17+000 in Reaches. | Charsadda Irrigation Division Charsadda | 0.341 | 0.218 | 14.7828 |  | 0.6 | 0 |  | 0% | Not yet started
14 | Silt Clearance of Doaba Canal RD.17+300-21+200 in reaches. | Charsadda Irrigation Division Charsadda | 0.338 | 0.22 | 14.7828 |  | 0.672 | 0 |  | 0% | Not yet started
15 | Silt Clearance of Doaba Canal RD.21+250-24+475 in reaches. | Charsadda Irrigation Division Charsadda | 0.312 | 0.2 | 14.7828 |  | 0.74 | 0 |  | 0% | Not yet started
16 | Silt clearance of New Michni Branch RD. 0+000-4+100 in reaches. | Charsadda Irrigation Division Charsadda | 0.3439 | 0.22 | 11.027 |  | 0.685 | 0.176 |  | 23% | In progress
17 | Silt clearance of New Michni Branch RD. 4+200-8+300 in reaches. | Charsadda Irrigation Division Charsadda | 0.332 | 0.212 | 11.027 |  | 0.731 | 0.243 |  | 25% | In progress
18 | Silt clearance of New Michni Branch RD 8+500-12+000 in reaches. | Charsadda Irrigation Division Charsadda | 0.32 | 0.2 | 11.027 |  | 0.609 |  |  | 0% | Not yet started
19 | Silt Clearance of Dalazak Minor RD. 0+000-4+000 in reaches. | Charsadda Irrigation Division Charsadda | 0.1244 | 0.796 | 3.96 |  | 0.67 |  |  | 0% | Not yet started
20 | Silt Clearance of Subhan Khwar Disty RD.0+000-4+500 in reaches. | Charsadda Irrigation Division Charsadda | 0.315 | 0.201 | 4.81 |  | 0.84 |  |  | 0% | Not yet started
21 | Silt clearance of Ichri Branch RD. 0-4366 in reaches. | Charsadda Irrigation Division Charsadda | 0.15 | 0.096 | 1.33 |  | 0.67 | 0.304 |  | 38% | In progress
22 | Silt Clearance of Shabqadar Branch RD.0+000-15+000 in reaches. | Charsadda Irrigation Division Charsadda | 0.38 | 0.24 | 4.5 |  | 1.645 | 0.457 |  | 26% | In progress
23 | Silt Clearance of Iceland Canal RD..0+00-Tail in reaches. | Charsadda Irrigation Division Charsadda | 0.35 | 0.224 | 8.83 |  | 2.103 |  |  | 0% | Not yet started
24 | Silt Clearance of Samkana Branch RD.0+000-30+000 in reaches. | Charsadda Irrigation Division Charsadda | 0.3 | 0.192 | 9.14 |  | 2.103 |  |  | 0% | Not yet Strated
25 | Silt & Shingle Clearance of P.C Minor from RD 0+000 To Tail in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.3395 | 12.881 |  |  | 0 |  | 0% | Not yet started
26 | Clearance of Shingri Minor from RD 0-17250 in reaches. | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.309 |  |  | 0 |  | 0% | Not yet started
27 | Clearance of Meherdi Minor from RD 0-31000 in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2425 | 9.451 |  |  | 0 |  | 0% | Not yet started
28 | Clearance of Kalu Branch from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.33 | 0.3218 | 11.563 |  |  | 0 |  | 0% | Not yet started
29 | Clearance of Hathian Minor from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.05 | 0.04875 | 2.35 |  |  | 0 |  | 0% | Not yet started
30 | Clearance of Jalala Disty from RD: 29000 to Tail in reaches | Malakand Irrigation Division Malakand | 0.37 | 0.3607 | 14.024 |  |  | 0 |  | 0% | Not yet started
31 | Clearance of Pirsaddo Disty, Ghano Minor and Qutab Gharh Minor from : H-Tail to Tail in reaches. | Malakand Irrigation Division Malakand | 0.35 | 0.412 | 1.88 |  |  | 0 |  | 0% | Not yet started
32 | Clearance of Shergarh Minor from Head to Rd:12+000 in reaches. | Malakand Irrigation Division Malakand | 0.15 | 0.146 | 7.752 |  |  | 0 |  | 0% | Not yet started
33 | Clearance of Shergarh Minor from Rd:12+000 tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 7.7752 |  |  | 0 |  | 0% | Not yet started
34 | Clearance of Spokanda Disty from RD: 18000 to Tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 5.659 |  |  | 0 |  | 0% | Not yet started
35 | Silt clearance/removal of heaps of Disty No. 9 RD; 41000 to 85500 | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 13.41 |  | 1 | 0.2 |  | 20% | Work in progress
36 | Silt clearance of power House Minor RD 0 to tail | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 1.28 |  | 1.28 | 0.3 |  | 23% | Work in progress
37 | Silt clearance of conduit covering portion of 2/9 Hoti Minor RD 4200 to 5000, 5800 to 7000 & 7200 to 7500 | Mardan Irrigation Division Mardan | 0.7 | 0.4546 | 0.7 |  | 0.7 | 0.2 |  | 29% | Work in progress
38 | Silt clearance of 2/9 Hoti Minor RD 0 to 4200, 5000 to 5800 & 7500 to 19000 | Mardan Irrigation Division Mardan | 0.8 | 0.5195 | 5.94 |  | 2.43 | 0.5 |  | 21% | Work in progress
39 | Silt clearance /removal of heaps of kalpani disty RD 0-51000 in reaches and clearance of syphones RD 10500 and 15000 | Mardan Irrigation Division Mardan | 0.7 | 0.4544 | 15.6 |  | 5.07 | 1 |  | 20% | Work in progress
40 | Silt clearance /removal of heaps of 1/kalpani Kodinaka Minor RD 0-27000 in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 8.22 |  | 1.82 | 0.5 |  | 27% | Work in progress
41 | Silt clearance /removal of heaps of 2/kalpani Taus Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 6.4 |  | 5.5 | 0.5 |  | 9% | Work in progress
42 | Silt clearance of 3/9 Toru Minor RD 0 to 15800 | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 4.81 |  | 4.81 | 1 |  | 21% | Work in progress
43 | Silt clearance of branch 2/kalpani Muhib Banda Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.175 | 0.1308 | 2.89 |  | 2 | 0.5 |  | 25% | Work in progress
44 | Silt Clearance of Maho Dheri Minor RD: 4000 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.1493 | 4.57 |  | 3.35 | 2.13 |  | 64% | Work in progress
45 | Silt Clearance of Rashakai Minor from RD: 7000 to 31000 in reaches | Mardan Irrigation Division Mardan | 0.6 | 0.3894 | 9.45 |  | 7.31 | 3.35 |  | 46% | Work in progress
46 | Silt Clearance of Nowshera Minor RD:0 - tail in reachers | Mardan Irrigation Division Mardan | 0.35 | 0.2613 | 5.18 |  | 3.2 | 1.52 |  | 48% | Work in progress
47 | Silt Clearance of Turlandi Minor Head to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 5.27 |  | 4.71 | 4.71 |  | 100% | Completed
48 | Silt Clearance of Khan Mahi Branch from RD: 0 to 3000 and RD: 8000 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 13.41 |  | 5.48 | 1.21 |  | 22% | Work in progress
49 | Silt Clearance of Bara Banda Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 3.04 |  | 3.04 | 0.3 |  | 10% | Work in progress
50 | Periodical silt clearance of Bara Banda Minor RD: 0 to 5000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.1493 | 3.04 |  | 3.04 | 0 |  | 0% | Not yet started
51 | Removal of heaps of Disty No. 8 RD: 52000 to 68000 in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 9.45 |  | 1.43 | 1.43 |  | 100% | Completed
52 | Silt Clearance/removal of heaps of Disty No. 7 at RD: 4000 to 14000 in reaches | Mardan Irrigation Division Mardan | 0.15 | 0.1133 | 4.26 |  | 3.04 | 2.43 |  | 80% | Work in progress
53 | Silt Clearance/removal of heaps of Sheikh yousaf Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 5.48 |  | 2.13 | 0.6 |  | 28% | Work in progress
54 | Silt Clearance/removal of heaps of 1/9 Guide Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 7 |  | 2.74 | 0 |  | 0% | Not yet started
55 | Silt Clearance/removal of heaps of Koragh Branch RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 14.93 |  | 2.23 | 2.23 |  | 100% | Completed
56 | Removal of heaps of Disty No.8 RD: 0 to 38000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 11.58 |  | 1 | 1 |  | 100% | Completed
57 | Removal of heaps of Disty No.9 RD: 0 to 41000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 12.5 |  | 1 | 1 |  | 100% | Completed
58 | Silt Clearance of Disty No.6 from RD: 55+000 to 60+000 in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.183 | 0.155 | 22.25 |  | 0.61 |  |  |  | Not yet started
59 | Silt Clearance of Disty No.6 from RD: 60+000 to 65+000 in reaches. | do | 0.157 | 0.133 | 22.25 |  | 0.45 | 60% |  |  | Work in progress
60 | Silt Clearance of Disty No.6 from RD: 65+000 to 73+000 in reaches. | do | 0.2 | 0.169 | 22.25 |  | 0.61 | 0.5 |  | 100% | Completed
61 | Silt Clearance of Nisatta Branch from RD: 0+000 to Tail in reaches. | do | 0.336 | 0.284 | 11.88 |  | 1 |  |  |  | Not yet started
62 | Silt Clearance of Nisatta Minor from RD: 0+000 to Tail in reaches. | do | 0.218 | 0.184 | 3.35 |  | 2 |  |  | 40% | Work in progress
63 | Silt Clearance of Palosa Minor from RD: 0+000 to Tail in reaches. | do | 0.253 | 0.214 | 5.03 |  | 1.35 |  |  |  | Not yet started
64 | Silt Clearance of Zardad and Kheshki Branch in reaches. | do | 0.348 | 0.294 | 14.49 |  | 7 | 2.5 |  | 30% | Work is in progress
65 | Removal of Heaps / Clearance of Bari Band Disty RD: 39+500-88+600 in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.33775 | 14.96 |  | 8.21 | 0 |  | 0% | Not yet started
66 | Removal of Heaps / Clearance of Hero Shah Minor RD: 0 -38+000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 11.58 |  | 11.58 | 0.25 |  | 2.16 | Work is in progress
67 | Removal of Heaps / Clearance of Kalu Shah Disty and Dundian Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.1 | 0.098 | 7.69 |  | 5 | 1 |  | 20% | Work is in progress
68 | Removal of Heaps / Clearance of Sarwala Disty and Lund Khwar Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 18.29 |  | 10.06 | 0 |  | 0% | Not yet started
69 | Removal of Heaps / Clearance of Said Abad Disty and Pir Abad Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 20.42 |  | 7.31 | 0 |  | 0% | Not yet started
70 | Removal of Heaps / Clearance of Katlang Disty from RD: 0-40+000 in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 12.19 |  | 7.61 | 0 |  | 0% | Not yet started
71 | Removal of Heaps / Clearance of Shamozai Disty/ Syphon and Likpani Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.392 | 17.67 |  | 13.01 | 0.5 |  | 3.84% | Work is in progress
72 | Removal of Heaps / Clearance of Dheri Minor and Tail Minor Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.15 | 0.147 | 7.01 |  | 6 | 0.75 |  | 12.5% | Work is in progress
73 | Bazai Main Canal Head Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 |  | 10.5 | 8 |  | 40% | Work is in progress
74 | Wartair Disty | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 6 |  | 6 | 5.5 |  | 90% | Work is in progress
75 | Kharki Disty No. 02 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 3.3 |  | 3.3 | 3.3 |  | 100% | Desiltation Completed
76 | Additional Minor No. 03, 06 and Bazai Disty No. 01. | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | 16.8 |  | 3 | 2 |  | 66% | Work is in progress
77 | Bazai Main Canal, Syphon No. 4431, 5851, 12530, 13590, 14842, 18400, 47527 & 58853 | Malakand Irrigation Division Malakand | 0.1 | 0.0975 |  |  |  | 0 |  | 60% | Work is in progress
78 | Bazai Disty No. 04, Bazai Minor No. 09, 11 and 12. | Malakand Irrigation Division Malakand | 0.27 | 0.26625 | 15.2 |  | 9 | 2 |  | 22% | Work is in progress
79 | Clearance of Syphon 79205, 93480 and 97962. | Malakand Irrigation Division Malakand | 0.1 | 0.975 |  |  |  | 0 |  | 10% | Work is in progress
80 | Bazai Disty No. 03 and Bazai Minor No. 05. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | 20.5 |  | 7 | 1 |  | 10% | Work is in progress
81 | Bazai Main Canal Tail Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 |  | 10.5 | 0 |  | 0% | Not yet started
82 | Shamizai Irrigation Canal | Swat Irrigation Division-II Matta | 1 | 0.779 | 20.73 | 5150 | 19.5 | 7.01 | 1852 | 36% | Work is in progress
83 | Barwai Irrigation Canal | Swat Irrigation Division-II Matta | 0.3 | 0.2805 | 11.22 | 1300 | 6.1 | 1.52 | 325 | 25% | Work is in progress
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086

## 26-01-2023
S# | Name of Canal | Name of Division | Estimated Cost(RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Total Quantity of Silt to be removed (m3) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Total Quantity of Silt removed till date (m3) | Progress Till date in % | Remarks
1 | Shamizai Irrigation Canal | Swat Irrigation Division-II Matta | 1 | 0.779 | 20.73 | 5150 | 19.5 | 9.75 | 2576 | 50% | Work is in progress
2 | Barwai Irrigation Canal | Swat Irrigation Division-II Matta | 0.3 | 0.2805 | 11.22 | 1300 | 6.1 | 2.01 | 429 | 33% | Work is in progress
3 | Silt clearance/removal of heaps of Disty No. 9 RD; 41000 to 85500 | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 13.41 | 599.93 | 1 | 0.2 | 119.99 | 20% | In progress
4 | Silt clearance of Power House Minor RD 0 to tail | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 1.28 | 599.9 | 1.28 | 0.35 | 164.04 | 27% | In progress
5 | Silt clearance of conduit covering portion of 2/9 Hoti Minor RD 4200 to 5000, 5800 to 7000 & 7200 to 7500 | Mardan Irrigation Division Mardan | 0.7 | 0.4546 | 0.7 | 745.53 | 0.7 | 0.24 | 255.61 | 34% | In progress
6 | Silt clearance of 2/9 Hoti Minor RD 0 to 4200, 5000 to 5800 & 7500 to 19000 | Mardan Irrigation Division Mardan | 0.8 | 0.5195 | 5.94 | 921.08 | 2.43 | 0.5 | 189.52 | 21% | In progress
7 | Silt clearance /removal of heaps of kalpani disty RD 0-51000 in reaches and clearance of syphones RD 10500 and 15000 | Mardan Irrigation Division Mardan | 0.7 | 0.4544 | 15.6 | 4463.54 | 5.07 | 1.2 | 1056.46 | 24% | In progress
8 | Silt clearance /removal of heaps of 1/kalpani Kodinaka Minor RD 0-27000 in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 8.22 | 599.94 | 1.82 | 0.5 | 164.82 | 27% | In progress
9 | Silt clearance /removal of heaps of 2/kalpani Taus Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 6.4 | 2801.12 | 5.5 | 0.5 | 254.65 | 9% | In progress
10 | Silt clearance of 3/9 Toru Minor RD 0 to 15800 | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 4.81 | 2801.12 | 4.81 | 1.5 | 873.53 | 31% | In progress
11 | Silt clearance of branch 2/kalpani Muhib Banda Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.175 | 0.1308 | 2.89 | 1633.98 | 2 | 0.5 | 408.5 | 25% | In progress
12 | Silt Clearance of Maho Dheri Minor RD: 4000 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.1493 | 4.57 | 1138.2 | 3.35 | 2.43 | 825.62 | 73% | In progress
13 | Silt Clearance of Rashakai Minor from RD: 7000 to 31000 in reaches | Mardan Irrigation Division Mardan | 0.6 | 0.3894 | 9.45 | 2972.29 | 7.31 | 4.77 | 1939.51 | 65% | In progress
14 | Silt Clearance of Nowshera Minor RD:0 - tail in reachers | Mardan Irrigation Division Mardan | 0.35 | 0.2613 | 5.18 | 2059.85 | 3.2 | 1.92 | 1235.91 | 60% | In progress
15 | Silt Clearance of Turlandi Minor Head to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 5.27 | 2134.4 | 4.71 | 4.71 | 2134.4 | 100% | Completed
16 | Silt Clearance of Khan Mahi Branch from RD: 0 to 3000 and RD: 8000 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 13.41 | 2344.08 | 5.48 | 2.11 | 902.56 | 39% | In progress
17 | Silt Clearance of Bara Banda Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 3.04 | 1703.02 | 3.04 | 1.65 | 924.34 | 54% | In progress
18 | Removal of heaps of Disty No. 8 RD: 52000 to 68000 in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 9.45 | 1860.72 | 1.43 | 1.43 | 1860.72 | 100% | Completed
19 | Silt Clearance/removal of heaps of Disty No. 7 at RD: 4000 to 14000 in reaches | Mardan Irrigation Division Mardan | 0.15 | 0.1133 | 4.26 | 1400.56 | 3.04 | 3.04 | 1400.56 | 100% | Completed
20 | Silt Clearance/removal of heaps of Sheikh yousaf Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 5.48 | 239.97 | 2.13 | 1.06 | 119.42 | 50% | In progress
21 | Silt Clearance/removal of heaps of 1/9 Guide Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 7 | 479.94 | 2.74 | 0.55 | 96.34 | 20% | In progress
22 | Silt Clearance/removal of heaps of Koragh Branch RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 14.93 | 479.94 | 2.23 | 2.23 | 479.94 | 100% | Completed
23 | Removal of heaps of Disty No.8 RD: 0 to 38000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 11.58 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
24 | Removal of heaps of Disty No.9 RD: 0 to 41000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 12.5 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
25 | Silt & Shingle Clearance of P.C Minor from RD 0+000 To Tail in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.3395 | 12.881 |  |  | 0 |  | 0% | Not yet started
26 | Clearance of Shingri Minor from RD 0-17250 in reaches. | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.309 |  |  | 0 |  | 0% | Not yet started
27 | Clearance of Meherdi Minor from RD 0-31000 in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2425 | 9.451 |  |  | 0 |  | 0% | Not yet started
28 | Clearance of Kalu Branch from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.33 | 0.3218 | 11.563 |  |  | 0 |  | 0% | Not yet started
29 | Clearance of Hathian Minor from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.05 | 0.04875 | 2.35 |  |  | 0 |  | 0% | Not yet started
30 | Clearance of Jalala Disty from RD: 29000 to Tail in reaches | Malakand Irrigation Division Malakand | 0.37 | 0.3607 | 14.024 |  |  | 0 |  | 0% | Not yet started
31 | Clearance of Pirsaddo Disty, Ghano Minor and Qutab Gharh Minor from : H-Tail to Tail in reaches. | Malakand Irrigation Division Malakand | 0.35 | 0.412 | 1.88 |  |  | 0 |  | 0% | Not yet started
32 | Clearance of Shergarh Minor from Head to Rd:12+000 in reaches. | Malakand Irrigation Division Malakand | 0.15 | 0.146 | 7.752 |  |  | 0 |  | 0% | Not yet started
33 | Clearance of Shergarh Minor from Rd:12+000 tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 7.7752 |  |  | 0 |  | 0% | Not yet started
34 | Clearance of Spokanda Disty from RD: 18000 to Tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 5.659 |  |  | 0 |  | 0% | Not yet started
35 | Removal of Heaps / Clearance of Bari Band Disty RD: 39+500-88+600 in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.33775 | 14.96 |  | 8.21 | 0.5 |  | 6.09% | Work is in progress
36 | Removal of Heaps / Clearance of Hero Shah Minor RD: 0 -38+000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 11.58 |  | 11.58 | 2 |  | 17.27% | Work is in progress
37 | Removal of Heaps / Clearance of Kalu Shah Disty and Dundian Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.1 | 0.098 | 7.69 |  | 5 | 3 |  | 60% | Work is in progress
38 | Removal of Heaps / Clearance of Sarwala Disty and Lund Khwar Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 18.29 |  | 10.06 | 1.5 |  | 14.91% | Work is in progress
39 | Removal of Heaps / Clearance of Said Abad Disty and Pir Abad Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 20.42 |  | 7.31 | 1 |  | 13.61% | Work is in progress
40 | Removal of Heaps / Clearance of Katlang Disty from RD: 0-40+000 in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 12.19 |  | 7.61 | 0 |  | 0% | Not yet started
41 | Removal of Heaps / Clearance of Shamozai Disty/ Syphon and Likpani Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.392 | 17.67 |  | 13.01 | 1.5 |  | 11.53% | Work is in progress
42 | Removal of Heaps / Clearance of Dheri Minor and Tail Minor Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.15 | 0.147 | 7.01 |  | 6 | 1.5 |  | 25% | Work is in progress
43 | Bazai Main Canal Head Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 |  | 10.5 | 9 |  | 44% | Work is in progress
44 | Wartair Disty | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 6 |  | 6 | 6 |  | 100% | Completed
45 | Kharki Disty No. 02 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 3.3 |  | 3.3 | 3.3 |  | 100% | Completed
46 | Additional Minor No. 03, 06 and Bazai Disty No. 01. | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | 16.8 |  | 3 | 2.5 |  | 85% | Work is in progress
47 | Bazai Main Canal, Syphon No. 4431, 5851, 12530, 13590, 14842, 18400, 47527 & 58853 | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | [5 empty] | 70% | Work is in progress
48 | Bazai Disty No. 04, Bazai Minor No. 09, 11 and 12. | Malakand Irrigation Division Malakand | 0.27 | 0.26625 | 15.2 |  | 9 | 2.5 |  | 30% | Work is in progress
49 | Clearance of Syphon 79205, 93480 and 97962. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | [5 empty] | 20% | Work is in progress
50 | Bazai Disty No. 03 and Bazai Minor No. 05. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | 20.5 |  | 7 | 3 |  | 45% | Work is in progress
51 | Bazai Main Canal Tail Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 |  | 10.5 | 0 |  | 0% | Not yet started
52 | Silt Clearance of Disty No.6 from RD: 55+000 to 60+000 in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.183 | 0.155 | 22.25 | 0.61 |  | 10% | Not yet started
53 | Silt Clearance of Disty No.6 from RD: 60+000 to 65+000 in reaches. | do | 0.157 | 0.133 | 22.25 | 0.45 | 60% | 100% | Completed
54 | Silt Clearance of Disty No.6 from RD: 65+000 to 73+000 in reaches. | do | 0.2 | 0.169 | 22.25 | 0.61 | 0.5 | 100% | Completed
55 | Silt Clearance of Nisatta Branch from RD: 0+000 to Tail in reaches. | do | 0.336 | 0.284 | 11.88 | 1 |  |  | Not yet started
56 | Silt Clearance of Nisatta Minor from RD: 0+000 to Tail in reaches. | do | 0.218 | 0.184 | 3.35 | 2 |  | 50% | Work in progress
57 | Silt Clearance of Palosa Minor from RD: 0+000 to Tail in reaches. | do | 0.253 | 0.214 | 5.03 | 1.35 |  |  | Not yet started
58 | Silt Clearance of Zardad and Kheshki Branch in reaches. | do | 0.348 | 0.294 | 14.49 | 7 | 3 | 40% | Work is in progress
59 | Nipki Khel Irrigation Scheme | Swat Irrigation Division -I | 2.2 | 1.76 | 38.87 | 10172.62 | 38.87 | 6.0976 | 1118.92 | 15.69% | Work is in progress
60 | Silt clearance from RD:0+00 to RD:8+000 in reaches of Ghazai Khani Flow Irrigation Scheme | Swat Irrigation Division -I | 0.12 | 0.119 | 2.44 | 613 | 2.44 | 0.3 | 73.56 | 12% | Work is in progress
61 | "Silt clearance from RD:0+00 to RD:12+000 in reaches of Karshalizara Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.08 | 0.072 | 3.66 | 408.66 | 3.66 | 1.06 | 118.56 | 29% | Work is in progress
62 | "Silt clearance from RD:0+00 to RD:20+000 in reaches of Charorai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 6.1 | 613 | 6.1 | 0.77 | 79.69 | 13% | Work is in progress
63 | "Silt clearance from RD:0+00 to RD:12+000 in reaches of Kuriya Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 3.66 | 613 | 3.66 | 0.91 | 153.25 | 25% | Work is in progress
64 | "Silt clearance from RD:0+00 to RD:9+000 in reaches of Elai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 2.74 | 613 | 2.74 | 0.152 | 36.78 | 6% | Work is in progress
65 | "Silt clearance from RD:0+00 to RD:60+000 in reaches of Budal Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.25 | 0.225 | 18.29 | 1277.1 | 18.29 | 0 | 0 | 0% | Not yet Started
66 | "Silt clearance from RD:0+00 to RD:16+000 in reaches of Singarai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.15 | 0.135 | 4.88 | 766.25 | 4.88 | 0.91 | 145.59 | 19% | Work is in progress
67 | "Silt clearance from RD:0+00 to RD:26+000 in reaches of Bajkata Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.24 | 0.213 | 18.29 | 1226 | 28 | 0.61 | 98.08 | 8% | Work is in progress
68 | Silt clearance of Doaba Canal RD. 0+000-4+500 in Reaches. | Charsadda Irrigation Division Charsadda | 0.226 | 0.144 | 14.7828 |  | 0.48 | 0.12 |  | 41% | In progress
69 | Silt clearance of Doaba Canal RD. 4+600-9+100 in Reaches. | Charsadda Irrigation Division Charsadda | 0.242 | 0.1548 | 14.7828 |  | 0.58 | 0.13 |  | 45% | In progress
70 | Silt clearance of Doaba Canal RD. 9+200-13+000 in Reaches. | Charsadda Irrigation Division Charsadda | 0.343 | 0.22 | 14.7828 |  | 0.548 | 0 |  | 0% | Not yet started
71 | Silt clearance of Doaba Canal RD. 13+200-17+000 in Reaches. | Charsadda Irrigation Division Charsadda | 0.341 | 0.218 | 14.7828 |  | 0.6 | 0 |  | 0% | Not yet started
72 | Silt Clearance of Doaba Canal RD.17+300-21+200 in reaches. | Charsadda Irrigation Division Charsadda | 0.338 | 0.22 | 14.7828 |  | 0.672 | 0 |  | 0% | Not yet started
73 | Silt Clearance of Doaba Canal RD.21+250-24+475 in reaches. | Charsadda Irrigation Division Charsadda | 0.312 | 0.2 | 14.7828 |  | 0.74 | 0 |  | 0% | Not yet started
74 | Silt clearance of New Michni Branch RD. 0+000-4+100 in reaches. | Charsadda Irrigation Division Charsadda | 0.3439 | 0.22 | 11.027 |  | 0.685 | 0.36 |  | 50% | In progress
75 | Silt clearance of New Michni Branch RD. 4+200-8+300 in reaches. | Charsadda Irrigation Division Charsadda | 0.332 | 0.212 | 11.027 |  | 0.731 | 0.54 |  | 55% | In progress
76 | Silt clearance of New Michni Branch RD 8+500-12+000 in reaches. | Charsadda Irrigation Division Charsadda | 0.32 | 0.2 | 11.027 |  | 0.609 | 0 |  | 0% | Not yet started
77 | Silt Clearance of Dalazak Minor RD. 0+000-4+000 in reaches. | Charsadda Irrigation Division Charsadda | 0.1244 | 0.796 | 3.96 |  | 0.67 | 0.22 |  | 30% | In progress
78 | Silt Clearance of Subhan Khwar Disty RD.0+000-4+500 in reaches. | Charsadda Irrigation Division Charsadda | 0.315 | 0.201 | 4.81 |  | 0.84 |  |  | 0% | Not yet started
79 | Silt clearance of Ichri Branch RD. 0-4366 in reaches. | Charsadda Irrigation Division Charsadda | 0.15 | 0.096 | 1.33 |  | 0.67 | 0.45 |  | 45% | In progress
80 | Silt Clearance of Shabqadar Branch RD.0+000-15+000 in reaches. | Charsadda Irrigation Division Charsadda | 0.38 | 0.24 | 4.5 |  | 1.645 | 0.85 |  | 50% | In progress
81 | Silt Clearance of Iceland Canal RD..0+00-Tail in reaches. | Charsadda Irrigation Division Charsadda | 0.35 | 0.224 | 8.83 |  | 2.103 | 0 |  | 0% | Not yet started
82 | Silt Clearance of Samkana Branch RD.0+000-30+000 in reaches. | Charsadda Irrigation Division Charsadda | 0.3 | 0.192 | 9.14 |  | 2.103 | 0 |  | 0% | Not yet Strated
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086

## 27-01-2023
| Name of Canal | Name of Division | Estimated Cost(RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Total Quantity of Silt to be removed (m3) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Total Quantity of Silt removed till date (m3) | Progress Till date in % | Remarks
1 | Silt Clearance of Disty No.6 from RD: 55+000 to 60+000 in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.183 | 0.155 | 22.25 |  | 0.61 | 0.1 |  |  | Not yet started
2 | Silt Clearance of Disty No.6 from RD: 60+000 to 65+000 in reaches. | do | 0.157 | 0.133 | 22.25 |  | 0.45 | 0.45 |  |  | Completed
3 | Silt Clearance of Disty No.6 from RD: 65+000 to 73+000 in reaches. | do | 0.2 | 0.169 | 22.25 |  | 0.61 | 0.61 |  |  | Completed
4 | Silt Clearance of Nisatta Branch from RD: 0+000 to Tail in reaches. | do | 0.336 | 0.284 | 11.88 |  | 1 | 0 |  |  | Not yet started
5 | Silt Clearance of Nisatta Minor from RD: 0+000 to Tail in reaches. | do | 0.218 | 0.184 | 3.35 |  | 2 | 1.2 |  |  | Work in progress
6 | Silt Clearance of Palosa Minor from RD: 0+000 to Tail in reaches. | do | 0.253 | 0.214 | 5.03 |  | 1.35 | 0 |  |  | Not yet started
7 | Silt Clearance of Zardad and Kheshki Branch in reaches. | do | 0.348 | 0.294 | 14.49 |  | 7 | 3.3 |  |  | Work is in progress
8 | Silt clearance of Doaba Canal RD. 0+000-4+500 in Reaches. | Charsadda Irrigation Division Charsadda | 0.226 | 0.144 | 14.7828 |  | 0.48 | 0.18 |  | 53% | In progress
9 | Silt clearance of Doaba Canal RD. 4+600-9+100 in Reaches. | Charsadda Irrigation Division Charsadda | 0.242 | 0.1548 | 14.7828 |  | 0.58 | 0.34 |  | 45% | In progress
10 | Silt clearance of Doaba Canal RD. 9+200-13+000 in Reaches. | Charsadda Irrigation Division Charsadda | 0.343 | 0.22 | 14.7828 |  | 0.548 | 0.12 |  | 35% | In progress
11 | Silt clearance of Doaba Canal RD. 13+200-17+000 in Reaches. | Charsadda Irrigation Division Charsadda | 0.341 | 0.218 | 14.7828 |  | 0.6 | 0 |  | 0% | Not yet started
12 | Silt Clearance of Doaba Canal RD.17+300-21+200 in reaches. | Charsadda Irrigation Division Charsadda | 0.338 | 0.22 | 14.7828 |  | 0.672 | 0 |  | 0% | Not yet started
13 | Silt Clearance of Doaba Canal RD.21+250-24+475 in reaches. | Charsadda Irrigation Division Charsadda | 0.312 | 0.2 | 14.7828 |  | 0.74 | 0 |  | 0% | Not yet started
14 | Silt clearance of New Michni Branch RD. 0+000-4+100 in reaches. | Charsadda Irrigation Division Charsadda | 0.3439 | 0.22 | 11.027 |  | 0.685 | 0.36 |  | 50% | In progress
15 | Silt clearance of New Michni Branch RD. 4+200-8+300 in reaches. | Charsadda Irrigation Division Charsadda | 0.332 | 0.212 | 11.027 |  | 0.731 | 0.54 |  | 55% | In progress
16 | Silt clearance of New Michni Branch RD 8+500-12+000 in reaches. | Charsadda Irrigation Division Charsadda | 0.32 | 0.2 | 11.027 |  | 0.609 | 0 |  | 0% | Not yet started
17 | Silt Clearance of Dalazak Minor RD. 0+000-4+000 in reaches. | Charsadda Irrigation Division Charsadda | 0.1244 | 0.796 | 3.96 |  | 0.67 | 0.22 |  | 30% | In progress
18 | Silt Clearance of Subhan Khwar Disty RD.0+000-4+500 in reaches. | Charsadda Irrigation Division Charsadda | 0.315 | 0.201 | 4.81 |  | 0.84 | 0.12 |  | 25% | In progress
19 | Silt clearance of Ichri Branch RD. 0-4366 in reaches. | Charsadda Irrigation Division Charsadda | 0.15 | 0.096 | 1.33 |  | 0.67 | 0.45 |  | 45% | In progress
20 | Silt Clearance of Shabqadar Branch RD.0+000-15+000 in reaches. | Charsadda Irrigation Division Charsadda | 0.38 | 0.24 | 4.5 |  | 1.645 | 0.85 |  | 50% | In progress
21 | Silt Clearance of Iceland Canal RD..0+00-Tail in reaches. | Charsadda Irrigation Division Charsadda | 0.35 | 0.224 | 8.83 |  | 2.103 | 0 |  | 0% | Not yet started
22 | Silt Clearance of Samkana Branch RD.0+000-30+000 in reaches. | Charsadda Irrigation Division Charsadda | 0.3 | 0.192 | 9.14 |  | 2.103 | 0 |  | 0% | Not yet Strated
23 | Silt Clearance of Sherpao Minor from RD 0+00 to Tail in reaches | Tangi Irrigation Sub Division Tangi | 0.38 | 0.24 | 3.89 |  | 1.48 | 1 |  | 68% | In progress
24 | Silt Clearance of Disty No. 2 RD 0+00 toTail in reaches | Tangi Irrigation Sub Division Tangi | 0.4 | 0.256 | 4.84 |  | 2.65 | 1 |  | 38% | In progress
25 | Silt Clearance of Behram Dheri Disty from RD: 0+000 to RD: 24+000 in reaches. | Tangi Irrigation Sub Division Tangi | 0.4 | 0.32 | 13.967 |  | 2.804 | 0.701 |  | 25% | In progress
26 | Silt Clearance of Behram Dheri Disty from RD:24+000 to Tail in reaches. | Tangi Irrigation Sub Division Tangi | 0.395 | 0.2528 | 13.967 |  | 3.505 | 0.87 |  | 25% | In progress
27 | Silt Clearance of Amir Abad Disty RD: 15+000 to Tail in reaches. | Tangi Irrigation Sub Division Tangi | 0.4 | 0.32 | 12.298 |  | 2.438 | 0.61 |  | 25% | In progress
28 | Silt Clearance of Barazai Minor head-Tail . | Tangi Irrigation Sub Division Tangi | 0.134 | 0.107 | 3.962 |  | 0.761 | 0.19 |  | 25% | In progress
29 | Silt Clearance of Harichand Disty from RD:0+000 to Tail in reaches | Tangi Irrigation Sub Division Tangi | 0.4 | 0.32 | 8.27 |  | 2.743 | 0.69 |  | 25% | In progress
30 | Silt Clearance of Nastrat zai Minor from head-Tail in reaches. | Tangi Irrigation Sub Division Tangi | 0.2 | 0.16 | 6.79 |  | 0.457 | 0.12 |  | 25% | In progress
31 | Silt Clearance of Disty No. 3 head to tail in reaches | Tangi Irrigation Sub Division Tangi | 0.35 | 0.224 | 4.57 |  | 1.066 | 0.5 |  | 47% | In progress
32 | Nipki Khel Irrigation Scheme | Swat Irrigation Division -I | 2.2 | 1.76 | 38.87 | 10172.62 | 38.87 | 6.0976 | 1118.92 | 15.69% | Progress of work is stopped due to Friday
33 | Silt clearance from RD:0+00 to RD:8+000 in reaches of Ghazai Khani Flow Irrigation Scheme | Swat Irrigation Division -I | 0.12 | 0.119 | 2.44 | 613 | 2.44
34 | "Silt clearance from RD:0+00 to RD:12+000 in reaches of Karshalizara Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.08 | 0.072 | 3.66 | 408.66 | 3.66
35 | "Silt clearance from RD:0+00 to RD:20+000 in reaches of Charorai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 6.1 | 613 | 6.1
36 | "Silt clearance from RD:0+00 to RD:12+000 in reaches of Kuriya Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 3.66 | 613 | 3.66
37 | "Silt clearance from RD:0+00 to RD:9+000 in reaches of Elai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 2.74 | 613 | 2.74
38 | "Silt clearance from RD:0+00 to RD:60+000 in reaches of Budal Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.25 | 0.225 | 18.29 | 1277.1 | 18.29
39 | "Silt clearance from RD:0+00 to RD:16+000 in reaches of Singarai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.15 | 0.135 | 4.88 | 766.25 | 4.88
40 | "Silt clearance from RD:0+00 to RD:26+000 in reaches of Bajkata Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.24 | 0.213 | 7.93 | 1226 | 7.93
41 | Silt clearance/removal of heaps of Disty No. 9 RD; 41000 to 85500 | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 13.41 | 599.93 | 1 | 0.25 | 149.98 | 25% | In progress
42 | Silt clearance of Power House Minor RD 0 to tail | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 1.28 | 599.9 | 1.28 | 0.4 | 187.47 | 31% | In progress
43 | Silt clearance of conduit covering portion of 2/9 Hoti Minor RD 4200 to 5000, 5800 to 7000 & 7200 to 7500 | Mardan Irrigation Division Mardan | 0.7 | 0.4546 | 0.7 | 745.53 | 0.7 | 0.24 | 255.61 | 34% | In progress
44 | Silt clearance of 2/9 Hoti Minor RD 0 to 4200, 5000 to 5800 & 7500 to 19000 | Mardan Irrigation Division Mardan | 0.8 | 0.5195 | 5.94 | 921.08 | 2.43 | 0.5 | 189.52 | 21% | In progress
45 | Silt clearance /removal of heaps of kalpani disty RD 0-51000 in reaches and clearance of syphones RD 10500 and 15000 | Mardan Irrigation Division Mardan | 0.7 | 0.4544 | 15.6 | 4463.54 | 5.07 | 1.5 | 1320.57 | 30% | In progress
46 | Silt clearance /removal of heaps of 1/kalpani Kodinaka Minor RD 0-27000 in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 8.22 | 599.94 | 1.82 | 0.7 | 230.75 | 38% | In progress
47 | Silt clearance /removal of heaps of 2/kalpani Taus Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 6.4 | 2801.12 | 5.5 | 0.5 | 254.65 | 9% | In progress
48 | Silt clearance of 3/9 Toru Minor RD 0 to 15800 | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 4.81 | 2801.12 | 4.81 | 1.5 | 873.53 | 31% | In progress
49 | Silt clearance of branch 2/kalpani Muhib Banda Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.175 | 0.1308 | 2.89 | 1633.98 | 2 | 0.5 | 408.5 | 25% | In progress
50 | Silt Clearance of Maho Dheri Minor RD: 4000 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.1493 | 4.57 | 1138.2 | 3.35 | 2.83 | 961.52 | 84% | In progress
51 | Silt Clearance of Rashakai Minor from RD: 7000 to 31000 in reaches | Mardan Irrigation Division Mardan | 0.6 | 0.3894 | 9.45 | 2972.29 | 7.31 | 5.57 | 2264.8 | 76% | In progress
52 | Silt Clearance of Nowshera Minor RD:0 - tail in reachers | Mardan Irrigation Division Mardan | 0.35 | 0.2613 | 5.18 | 2059.85 | 3.2 | 2.62 | 1686.5 | 82% | In progress
53 | Silt Clearance of Turlandi Minor Head to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 5.27 | 2134.4 | 4.71 | 4.71 | 2134.4 | 100% | Completed
54 | Silt Clearance of Khan Mahi Branch from RD: 0 to 3000 and RD: 8000 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 13.41 | 2344.08 | 5.48 | 2.61 | 1116.43 | 48% | In progress
55 | Silt Clearance of Bara Banda Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 3.04 | 1703.02 | 3.04 | 2.45 | 1372.5 | 81% | In progress
56 | Removal of heaps of Disty No. 8 RD: 52000 to 68000 in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 9.45 | 1860.72 | 1.43 | 1.43 | 1860.72 | 100% | Completed
57 | Silt Clearance/removal of heaps of Disty No. 7 at RD: 4000 to 14000 in reaches | Mardan Irrigation Division Mardan | 0.15 | 0.1133 | 4.26 | 1400.56 | 3.04 | 3.04 | 1400.56 | 100% | Completed
58 | Silt Clearance/removal of heaps of Sheikh yousaf Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 5.48 | 239.97 | 2.13 | 1.4 | 157.73 | 66% | In progress
59 | Silt Clearance/removal of heaps of 1/9 Guide Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 7 | 479.94 | 2.74 | 1 | 175.16 | 36% | In progress
60 | Silt Clearance/removal of heaps of Koragh Branch RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 14.93 | 479.94 | 2.23 | 2.23 | 479.94 | 100% | Completed
61 | Removal of heaps of Disty No.8 RD: 0 to 38000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 11.58 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
62 | Removal of heaps of Disty No.9 RD: 0 to 41000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 12.5 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
63 | Removal of Heaps / Clearance of Bari Band Disty RD: 39+500-88+600 in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.33775 | 14.96 | 1435.76 | 8.21 | 1 | 200 | 12.18% | In progress
64 | Removal of Heaps / Clearance of Hero Shah Minor RD: 0 -38+000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 11.58 | 2446.93 | 11.58 | 2.5 | 500 | 21.62% | In progress
65 | Removal of Heaps / Clearance of Kalu Shah Disty and Dundian Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.1 | 0.098 | 7.69 | 785.8 | 5 | 3.5 | 485 | 70% | In progress
66 | Removal of Heaps / Clearance of Sarwala Disty and Lund Khwar Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 18.29 | 3172.99 | 10.06 | 2 | 600 | 19.88% | In progress
67 | Removal of Heaps / Clearance of Said Abad Disty and Pir Abad Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 20.42 | 3113.1 | 7.31 | 1.5 | 150 | 20.51% | In progress
68 | Removal of Heaps / Clearance of Katlang Disty from RD: 0-40+000 in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 12.19 | 1910.43 | 7.61 | 0.5 | 200 | 6.57% | In progress
69 | Removal of Heaps / Clearance of Shamozai Disty/ Syphon and Likpani Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.392 | 17.67 | 2730.62 | 13.01 | 2 | 400 | 15.37% | In progress
70 | Removal of Heaps / Clearance of Dheri Minor and Tail Minor Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.15 | 0.147 | 7.01 | 1211.68 | 6 | 2 | 250 | 33.33% | In progress
71 | Shamizai Irrigation Canal | Swat Irrigation Division-II Matta | 1 | 0.779 | 20.73 | 5150 | 19.5 | 10.67 | 2817 | 55% | Work is in progress
72 | Barwai Irrigation Canal | Swat Irrigation Division-II Matta | 0.3 | 0.2805 | 11.22 | 1300 | 6.1 | 2.42 | 517 | 40% | Work is in progress
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086

## 28-01-2023
S# | Name of Canal | Name of Division | Estimated Cost(RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Total Quantity of Silt to be removed (m3) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Total Quantity of Silt removed till date (m3) | Progress Till date in % | Remarks
1 | Shamizai Irrigation Canal | Swat Irrigation Division-II Matta | 1 | 0.779 | 20.73 | 5150 | 19.5 | 11.89 | 3139 | 61% | Work is in progress
2 | Barwai Irrigation Canal | Swat Irrigation Division-II Matta | 0.3 | 0.2805 | 11.22 | 1300 | 6.1 | 2.8 | 598 | 46% | Work is in progress
3 | Silt clearance/removal of heaps of Disty No. 9 RD; 41000 to 85500 | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 13.41 | 599.93 | 1 | 0.35 | 209.98 | 35% | In progress
4 | Silt clearance of Power House Minor RD 0 to tail | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 1.28 | 599.9 | 1.28 | 0.5 | 234.34 | 39% | In progress
5 | Silt clearance of conduit covering portion of 2/9 Hoti Minor RD 4200 to 5000, 5800 to 7000 & 7200 to 7500 | Mardan Irrigation Division Mardan | 0.7 | 0.4546 | 0.7 | 745.53 | 0.7 | 0.31 | 330.16 | 44% | In progress
6 | Silt clearance of 2/9 Hoti Minor RD 0 to 4200, 5000 to 5800 & 7500 to 19000 | Mardan Irrigation Division Mardan | 0.8 | 0.5195 | 5.94 | 921.08 | 2.43 | 0.85 | 322.19 | 35% | In progress
7 | Silt clearance /removal of heaps of kalpani disty RD 0-51000 in reaches and clearance of syphones RD 10500 and 15000 | Mardan Irrigation Division Mardan | 0.7 | 0.4544 | 15.6 | 4463.54 | 5.07 | 2.1 | 1848.8 | 41% | In progress
8 | Silt clearance /removal of heaps of 1/kalpani Kodinaka Minor RD 0-27000 in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 8.22 | 599.94 | 1.82 | 0.9 | 296.67 | 49% | In progress
9 | Silt clearance /removal of heaps of 2/kalpani Taus Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 6.4 | 2801.12 | 5.5 | 1.35 | 687.55 | 25% | In progress
10 | Silt clearance of 3/9 Toru Minor RD 0 to 15800 | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 4.81 | 2801.12 | 4.81 | 1.9 | 1106.47 | 40% | In progress
11 | Silt clearance of branch 2/kalpani Muhib Banda Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.175 | 0.1308 | 2.89 | 1633.98 | 2 | 0.7 | 571.89 | 35% | In progress
12 | Silt Clearance of Maho Dheri Minor RD: 4000 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.1493 | 4.57 | 1138.2 | 3.35 | 3 | 1019.28 | 90% | In progress
13 | Silt Clearance of Rashakai Minor from RD: 7000 to 31000 in reaches | Mardan Irrigation Division Mardan | 0.6 | 0.3894 | 9.45 | 2972.29 | 7.31 | 6.3 | 2561.62 | 86% | In progress
14 | Silt Clearance of Nowshera Minor RD:0 - tail in reachers | Mardan Irrigation Division Mardan | 0.35 | 0.2613 | 5.18 | 2059.85 | 3.2 | 2.9 | 1866.74 | 91% | In progress
15 | Silt Clearance of Turlandi Minor Head to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 5.27 | 2134.4 | 4.71 | 4.71 | 2134.4 | 100% | Completed
16 | Silt Clearance of Khan Mahi Branch from RD: 0 to 3000 and RD: 8000 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 13.41 | 2344.08 | 5.48 | 3.25 | 1390.19 | 59% | In progress
17 | Silt Clearance of Bara Banda Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 3.04 | 1703.02 | 3.04 | 2.75 | 1540.56 | 90% | In progress
18 | Removal of heaps of Disty No. 8 RD: 52000 to 68000 in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 9.45 | 1860.72 | 1.43 | 1.43 | 1860.72 | 100% | Completed
19 | Silt Clearance/removal of heaps of Disty No. 7 at RD: 4000 to 14000 in reaches | Mardan Irrigation Division Mardan | 0.15 | 0.1133 | 4.26 | 1400.56 | 3.04 | 3.04 | 1400.56 | 100% | Completed
20 | Silt Clearance/removal of heaps of Sheikh yousaf Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 5.48 | 239.97 | 2.13 | 1.65 | 185.89 | 77% | In progress
21 | Silt Clearance/removal of heaps of 1/9 Guide Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 7 | 479.94 | 2.74 | 1.25 | 218.95 | 46% | In progress
22 | Silt Clearance/removal of heaps of Koragh Branch RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 14.93 | 479.94 | 2.23 | 2.23 | 479.94 | 100% | Completed
23 | Removal of heaps of Disty No.8 RD: 0 to 38000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 11.58 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
24 | Removal of heaps of Disty No.9 RD: 0 to 41000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 12.5 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
25 | Nipki Khel Irrigation Scheme | Swat Irrigation Division -I | 2.2 | 1.76 | 38.87 | 10172.62 | 38.87 | 7.7744 | 1118.92 | 20% | In progress
26 | Silt clearance from RD:0+00 to RD:8+000 in reaches of Ghazai Khani Flow Irrigation Scheme | Swat Irrigation Division -I | 0.12 | 0.119 | 2.44 | 613 | 2.44 | 0.85 | 146 | 34.84% | In progress
27 | "Silt clearance from RD:0+00 to RD:12+000 in reaches of Karshalizara Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.08 | 0.072 | 3.66 | 408.66 | 3.66 | 1.66 | 210 | 45.36% | In progress
28 | "Silt clearance from RD:0+00 to RD:20+000 in reaches of Charorai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 6.1 | 613 | 6.1 | 1.5 |  | 24.59% | In progress
29 | "Silt clearance from RD:0+00 to RD:12+000 in reaches of Kuriya Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 3.66 | 613 | 3.66 |  |  | 0% | In progress
30 | "Silt clearance from RD:0+00 to RD:9+000 in reaches of Elai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 2.74 | 613 | 2.74 |  |  | 0% | In progress
31 | "Silt clearance from RD:0+00 to RD:60+000 in reaches of Budal Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.25 | 0.225 | 18.29 | 1277.1 | 18.29 |  |  | 0% | In progress
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086

## 29-01-2023
S# | Name of Canal | Name of Division | Estimated Cost(RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Total Quantity of Silt to be removed (m3) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Total Quantity of Silt removed till date (m3) | Progress Till date in % | Remarks
1 | Silt clearance/removal of heaps of Disty No. 9 RD; 41000 to 85500 | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 13.41 | 599.93 | 1 | 0.45 | 269.97 | 45% | In progress
2 | Silt clearance of Power House Minor RD 0 to tail | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 1.28 | 599.9 | 1.28 | 0.7 | 328.07 | 55% | In progress
3 | Silt clearance of conduit covering portion of 2/9 Hoti Minor RD 4200 to 5000, 5800 to 7000 & 7200 to 7500 | Mardan Irrigation Division Mardan | 0.7 | 0.4546 | 0.7 | 745.53 | 0.7 | 0.38 | 404.72 | 54% | In progress
4 | Silt clearance of 2/9 Hoti Minor RD 0 to 4200, 5000 to 5800 & 7500 to 19000 | Mardan Irrigation Division Mardan | 0.8 | 0.5195 | 5.94 | 921.08 | 2.43 | 1.22 | 462.44 | 50% | In progress
5 | Silt clearance /removal of heaps of kalpani disty RD 0-51000 in reaches and clearance of syphones RD 10500 and 15000 | Mardan Irrigation Division Mardan | 0.7 | 0.4544 | 15.6 | 4463.54 | 5.07 | 2.75 | 2421.05 | 54% | In progress
6 | Silt clearance /removal of heaps of 1/kalpani Kodinaka Minor RD 0-27000 in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 8.22 | 599.94 | 1.82 | 1.08 | 356.01 | 59% | In progress
7 | Silt clearance /removal of heaps of 2/kalpani Taus Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 6.4 | 2801.12 | 5.5 | 2.25 | 1145.91 | 41% | In progress
8 | Silt clearance of 3/9 Toru Minor RD 0 to 15800 | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 4.81 | 2801.12 | 4.81 | 2.35 | 1368.53 | 49% | In progress
9 | Silt clearance of branch 2/kalpani Muhib Banda Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.175 | 0.1308 | 2.89 | 1633.98 | 2 | 0.9 | 735.29 | 45% | In progress
10 | Silt Clearance of Maho Dheri Minor RD: 4000 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.1493 | 4.57 | 1138.2 | 3.35 | 3 | 1019.28 | 90% | In progress
11 | Silt Clearance of Rashakai Minor from RD: 7000 to 31000 in reaches | Mardan Irrigation Division Mardan | 0.6 | 0.3894 | 9.45 | 2972.29 | 7.31 | 7 | 2846.24 | 96% | In progress
12 | Silt Clearance of Nowshera Minor RD:0 - tail in reachers | Mardan Irrigation Division Mardan | 0.35 | 0.2613 | 5.18 | 2059.85 | 3.2 | 2.9 | 1866.74 | 91% | In progress
13 | Silt Clearance of Turlandi Minor Head to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 5.27 | 2134.4 | 4.71 | 4.71 | 2134.4 | 100% | Completed
14 | Silt Clearance of Khan Mahi Branch from RD: 0 to 3000 and RD: 8000 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 13.41 | 2344.08 | 5.48 | 3.7 | 1582.68 | 68% | In progress
15 | Silt Clearance of Bara Banda Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 3.04 | 1703.02 | 3.04 | 2.75 | 1540.56 | 90% | In progress
16 | Removal of heaps of Disty No. 8 RD: 52000 to 68000 in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 9.45 | 1860.72 | 1.43 | 1.43 | 1860.72 | 100% | Completed
17 | Silt Clearance/removal of heaps of Disty No. 7 at RD: 4000 to 14000 in reaches | Mardan Irrigation Division Mardan | 0.15 | 0.1133 | 4.26 | 1400.56 | 3.04 | 3.04 | 1400.56 | 100% | Completed
18 | Silt Clearance/removal of heaps of Sheikh yousaf Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 5.48 | 239.97 | 2.13 | 1.83 | 206.17 | 86% | In progress
19 | Silt Clearance/removal of heaps of 1/9 Guide Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 7 | 479.94 | 2.74 | 1.68 | 294.27 | 61% | In progress
20 | Silt Clearance/removal of heaps of Koragh Branch RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 14.93 | 479.94 | 2.23 | 2.23 | 479.94 | 100% | Completed
21 | Removal of heaps of Disty No.8 RD: 0 to 38000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 11.58 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
22 | Removal of heaps of Disty No.9 RD: 0 to 41000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 12.5 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
23 | Shamizai Irrigation Canal | Swat Irrigation Division-II Matta | 1 | 0.779 | 20.73 | 5150 | 19.5 | 13.2 | 3485 | 68% | Work is in progress
24 | Barwai Irrigation Canal | Swat Irrigation Division-II Matta | 0.3 | 0.2805 | 11.22 | 1300 | 6.1 | 2.99 | 637 | 49% | Work is in progress
25 | Nipki Khel Irrigation Scheme | Swat Irrigation Division -I | 2.2 | 1.76 | 38.87 | 10172.62 | 38.87 | 9.2988 | 2440 | 23.92% | In progress
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086

## 30-01-2023
S# | Name of Canal | Name of Division | Estimated Cost(RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Total Quantity of Silt to be removed (m3) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Total Quantity of Silt removed till date (m3) | Progress Till date in % | Remarks
1 | Silt Clearance of Sherpao Minor from RD 0+00 to Tail in reaches | Tangi Irrigation Sub Division Tangi | 0.38 | 0.24 | 3.89 | 1885.63 | 1.48 | 1.11 | 1414.22 | 75% | In progress
2 | Silt Clearance of Disty No. 2 RD 0+00 toTail in reaches | Tangi Irrigation Sub Division Tangi | 0.4 | 0.256 | 4.84 | 1592.05 | 2.65 | 1.59 | 955.23 | 60% | In progress
3 | Silt Clearance of Behram Dheri Disty from RD: 0+000 to RD: 24+000 in reaches. | Tangi Irrigation Sub Division Tangi | 0.4 | 0.32 | 13.967 | 2075.64 | 2.804 | 1.065 | 788.74 | 38% | In progress
4 | Silt Clearance of Behram Dheri Disty from RD:24+000 to Tail in reaches. | Tangi Irrigation Sub Division Tangi | 0.395 | 0.2528 | 13.967 | 1466.82 | 3.505 | 1.33 | 557.39 | 38% | In progress
5 | Silt Clearance of Amir Abad Disty RD: 15+000 to Tail in reaches. | Tangi Irrigation Sub Division Tangi | 0.4 | 0.32 | 12.298 | 1713.18 | 2.438 | 0.99 | 702.4 | 41% | In progress
6 | Silt Clearance of Barazai Minor head-Tail . | Tangi Irrigation Sub Division Tangi | 0.134 | 0.107 | 3.962 | 389.36 | 0.761 | 0.32 | 97.34 | 25% | In progress
7 | Silt Clearance of Harichand Disty from RD:0+000 to Tail in reaches | Tangi Irrigation Sub Division Tangi | 0.4 | 0.32 | 8.27 | 1316.74 | 2.743 | 1.39 | 671.53 | 51% | In progress
8 | Silt Clearance of Nastrat zai Minor from head-Tail in reaches. | Tangi Irrigation Sub Division Tangi | 0.2 | 0.16 | 6.79 | 368.12 | 0.457 | 0.15 | 121.48 | 33% | In progress
9 | Silt Clearance of Disty No. 3 head to tail in reaches | Tangi Irrigation Sub Division Tangi | 0.35 | 0.224 | 4.57 | 750.4 | 1.066 | 0.64 | 450.24 | 60% | In progress
10 | Jue Shiekh Canal | Peshawar Canals Division Peshawar. | 16.29 | 13.03 | 53.35 | 132353 | 53.35 | 29.5 | 67500 | 55% | Work is in progress
11 | Jue Zardad Canal | Peshawar Canals Division Peshawar. | 3.6 | 2.88 | 13.1 | 18500 | 13.1 | 4.4 | 6214 | 34% | Work is in progress
12 | Kabul River Canal | Peshawar Canals Division Peshawar. | 27.855 | 22.284 | 60.35 | 1062085 | 60.35 | 13.41 | 236011 | 22% | Work is in progress
13 | Hazar Khwani Branch | Peshawar Canals Division Peshawar. | 23.2 | 18.56 | 28.04 | 1016303 | 28.04 | 11.4 | 413190 | 41% | Work is in progress
14 | Warsak Gravity Canal | Warsak Canals Division Peshawar | 18.8 | 16.2 | 68.88 | 23089.8 | 61.26 | 16.76 | 6318.1 | 27% | Work is in progress
15 | Warsak Minor | Warsak Canals Division Peshawar | 0.8 | 0.736 | 5.85 | 873 | 5.85 | 1.37 | 204.61 | 23% | Work is in progress
16 | Kafoor Dheri Minor | Warsak Canals Division Peshawar | 0.4 | 0.368 | 0.94 | 900 | 0.94 | 0 | 0 | 0% | Work is in progress
17 | Shahi Bala Minor | Warsak Canals Division Peshawar | 0.4 | 0.368 | 1.07 | 995 | 1.07 | 0 | 0 | 0% | Work is in progress
18 | Mullazai Minor | Warsak Canals Division Peshawar | 0.3 | 0.552 | 3.35 | 1670 | 3.35 | 0.98 | 485.82 | 29% | Work is in progress
19 | Tehkal Minor | Warsak Canals Division Peshawar | 0.6 | 0.552 | 0.99 | 360 | 0.99 | 0 | 0 | 0% | Work is in progress
20 | Palosai Minor | Warsak Canals Division Peshawar | 0.5 | 0.46 | 0.66 | 455 | 0.66 | 0 | 0 | 0% | Work is in progress
21 | Surizai Minor | Warsak Canals Division Peshawar | 0.4 | 0.368 | 3.02 | 1039 | 3.02 | 0.7 | 241.38 | 23% | Work is in progress
22 | Urmar Minor | Warsak Canals Division Peshawar | 0.8 | 0.736 | 6.71 | 1490 | 6.71 | 1.66 | 369.11 | 25% | Work is in progress
23 | Pabbi Minor | Warsak Canals Division Peshawar | 0.4 | 0.368 | 2.44 | 694 | 2.44 | 1.84 | 524.84 | 76% | Work is in progress
24 | Warsak Lift Canal | Warsak Canals Division Peshawar | 8.39 | 6.5 | 46.63 | 7487.19 | 29.56 | 7.31 | 1852.5 | 25% | Work is in progress
25 | Regi Minor | Warsak Canals Division Peshawar | 0.13 | 0.15 | 0.91 | 270 | 0.91 | 0 | 0 | 0% | Work is in progress
26 | Badabher Minor | Warsak Canals Division Peshawar | 0.26 | 0.29 | 5.49 | 530 | 5.49 | 0 | 0 | 0% | Work is in progress
27 | Warsak Left Bank Canal | Warsak Canals Division Peshawar | 1.69 | 1.554 | 19.29 | 6837.96 | 13.2 | 1.65 | 852.77 | 12% | Work is in progress
28 | Periodical silt clearance of Fore Bay and Feeder Channel Of WPH, Sump Well, Sedimenattion Tank & Raising Main | Warsak Canals Division Peshawar | 2.2 | 1.9 | 3.22 | 4500 | 3.22 | 0 | 0 | 0% | Work is in progress
29 | Silt clearance/removal of heaps of Disty No. 9 RD; 41000 to 85500 | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 13.41 | 599.93 | 1 | 0.6 | 359.96 | 60% | In progress
30 | Silt clearance of Power House Minor RD 0 to tail | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 1.28 | 599.9 | 1.28 | 0.83 | 389 | 65% | In progress
31 | Silt clearance of conduit covering portion of 2/9 Hoti Minor RD 4200 to 5000, 5800 to 7000 & 7200 to 7500 | Mardan Irrigation Division Mardan | 0.7 | 0.4546 | 0.7 | 745.53 | 0.7 | 0.48 | 511.22 | 69% | In progress
32 | Silt clearance of 2/9 Hoti Minor RD 0 to 4200, 5000 to 5800 & 7500 to 19000 | Mardan Irrigation Division Mardan | 0.8 | 0.5195 | 5.94 | 921.08 | 2.43 | 1.47 | 557.2 | 60% | In progress
33 | Silt clearance /removal of heaps of kalpani disty RD 0-51000 in reaches and clearance of syphones RD 10500 and 15000 | Mardan Irrigation Division Mardan | 0.7 | 0.4544 | 15.6 | 4463.54 | 5.07 | 3.53 | 3107.75 | 70% | In progress
34 | Silt clearance /removal of heaps of 1/kalpani Kodinaka Minor RD 0-27000 in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 8.22 | 599.94 | 1.82 | 1.26 | 415.34 | 69% | In progress
35 | Silt clearance /removal of heaps of 2/kalpani Taus Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 6.4 | 2801.12 | 5.5 | 3 | 1527.88 | 55% | In progress
36 | Silt clearance of 3/9 Toru Minor RD 0 to 15800 | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 4.81 | 2801.12 | 4.81 | 3.15 | 1834.41 | 65% | In progress
37 | Silt clearance of branch 2/kalpani Muhib Banda Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.175 | 0.1308 | 2.89 | 1633.98 | 2 | 1.2 | 980.39 | 60% | In progress
38 | Silt Clearance of Maho Dheri Minor RD: 4000 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.1493 | 4.57 | 1138.2 | 3.35 | 3 | 1019.28 | 90% | In progress
39 | Silt Clearance of Rashakai Minor from RD: 7000 to 31000 in reaches | Mardan Irrigation Division Mardan | 0.6 | 0.3894 | 9.45 | 2972.29 | 7.31 | 7 | 2846.24 | 96% | In progress
40 | Silt Clearance of Nowshera Minor RD:0 - tail in reachers | Mardan Irrigation Division Mardan | 0.35 | 0.2613 | 5.18 | 2059.85 | 3.2 | 2.9 | 1866.74 | 91% | In progress
41 | Silt Clearance of Turlandi Minor Head to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 5.27 | 2134.4 | 4.71 | 4.71 | 2134.4 | 100% | Completed
42 | Silt Clearance of Khan Mahi Branch from RD: 0 to 3000 and RD: 8000 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 13.41 | 2344.08 | 5.48 | 4.25 | 1817.95 | 78% | In progress
43 | Silt Clearance of Bara Banda Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 3.04 | 1703.02 | 3.04 | 2.75 | 1540.56 | 90% | In progress
44 | Removal of heaps of Disty No. 8 RD: 52000 to 68000 in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 9.45 | 1860.72 | 1.43 | 1.43 | 1860.72 | 100% | Completed
45 | Silt Clearance/removal of heaps of Disty No. 7 at RD: 4000 to 14000 in reaches | Mardan Irrigation Division Mardan | 0.15 | 0.1133 | 4.26 | 1400.56 | 3.04 | 3.04 | 1400.56 | 100% | Completed
46 | Silt Clearance/removal of heaps of Sheikh yousaf Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 5.48 | 239.97 | 2.13 | 2.05 | 230.96 | 96% | In progress
47 | Silt Clearance/removal of heaps of 1/9 Guide Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 7 | 479.94 | 2.74 | 1.95 | 341.56 | 71% | In progress
48 | Silt Clearance/removal of heaps of Koragh Branch RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 14.93 | 479.94 | 2.23 | 2.23 | 479.94 | 100% | Completed
49 | Removal of heaps of Disty No.8 RD: 0 to 38000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 11.58 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
50 | Removal of heaps of Disty No.9 RD: 0 to 41000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 12.5 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
51 | Silt Clearance of Disty No.6 from RD: 55+000 to 60+000 in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.183 | 0.155 | 22.25 | 0.61 |  | 0.1 |  | 10% | Work in progress
52 | Silt Clearance of Disty No.6 from RD: 60+000 to 65+000 in reaches. | do | 0.157 | 0.133 | 22.25 | 0.45 |  | 0.45 |  | 100% | Completed
53 | Silt Clearance of Disty No.6 from RD: 65+000 to 73+000 in reaches. | do | 0.2 | 0.169 | 22.25 | 0.61 |  | 0.61 |  | 100% | Completed
54 | Silt Clearance of Nisatta Branch from RD: 0+000 to Tail in reaches. | do | 0.336 | 0.284 | 11.88 | 1 |  | 0.4 |  | 15% | Work in progress
55 | Silt Clearance of Nisatta Minor from RD: 0+000 to Tail in reaches. | do | 0.218 | 0.184 | 3.35 | 2 |  | 1.2 |  | 60% | Work in progress
56 | Silt Clearance of Palosa Minor from RD: 0+000 to Tail in reaches. | do | 0.253 | 0.214 | 5.03 | 1.35 |  | 0.41 |  | 30% | Work in progress
57 | Silt Clearance of Zardad and Kheshki Branch in reaches. | do | 0.348 | 0.294 | 14.49 | 7 |  | 5 |  | 75% | Work in progress
58 | Desiltation / berm cutting/Jungle clearance of Disty No.04, RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 10.11 |  | 2.13 | 0 |  | 0% | yet to be started
59 | Desiltation / berm cutting/Jungle clearance of Disty No.5 & its Minor and sub Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 26.31 |  | 4.75 | 0 |  | 0% | yet to be started
60 | Desiltation / berm cutting/Jungle clearance of Dera Disty RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 16.7 |  | 2.74 | 0.75 |  | 27% | work in progress
61 | Silt clearance/ jungle clearance of Muryali Minor RD. 00-15000 in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.64 |  | 3.04 | 0 |  | 0% | yet to be started
62 | Silt clearance/ jungle clearance including removal of debris of Lachra Minor/Makali Minor in reaches. | CRBC Irrigation Division DIKhan | 0.25 | 0.23 | 3.92 |  | 3 | 0 |  | 0% | yet to be started
63 | Desiltation / berm cutting/Jungle clearance of Mehmood Disty. RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.05 |  | 4.42 | 0 |  | 0% | yet to be started
64 | Desiltation / berm cutting/Jungle clearance of Nawab Minor RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.3 | 0.27 | 7.62 |  | 2.43 | 0.73 |  | 30% | work in progress
65 | Desiltation / berm cutting/Jungle clearance of Disty No.7, i/c Minors of Disty No.7 RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 30.53 |  | 10.18 | 1 |  | 30% | work in progress
66 | Desiltation / berm cutting/Jungle clearance of Disty No. 8 & 8-A, RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.29 |  | 3.95 | 1 |  | 25% | work in progress
67 | Desiltation / berm cutting/Jungle clearance of Disty No.9 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.71 |  | 2.89 | 0 |  | 0% | yet to be started
68 | Desiltation / berm cutting/Jungle clearance of Disty No.10 & 10/A RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11 |  | 3.28 | 0 |  | 0% | yet to be started
69 | Desiltation / berm cutting/Jungle clearance of Disty No. 11 & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 9.1 |  | 5.78 | 0 |  | 0% | yet to be started
70 | Desiltation / berm cutting/Jungle clearance of Disty No. 11-A, & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 21.86 |  | 5.93 | 0 |  | 0% | yet to be started
71 | Desiltation / berm cutting/Jungle clearance of Disty No. 12 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.23 |  | 3.04 | 0.9 |  | 30% | work in progress
72 | Desiltation /Jungle Clearance of Disty # 13 & its System RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.675 | 0.6075 | 21.655 |  | 4.66 | 0.45 |  | 10% | Work is in progress.
73 | Shingling of CPR & Jungle Clearance of Disty # 14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.725 | 0.6525 | 21.616 |  | 4.58 | 0 |  | 0%
74 | Shingling of CPR & Jungle Clearance of MD-14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.433 |  | 1.82 | 0 |  | 0%
75 | Shingling of CPR & Jungle Clearance of Disty # 15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.7 | 0.63 | 21.494 |  | 4.5 | 0 |  | 0% | Work not yet started.
76 | Shingling of CPR & Jungle Clearance of MD-15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.325 | 0.2925 | 5.8384 |  | 2.28 | 0 |  | 0% | Work not yet started.
77 | Shingling of CPR & Jungle Clearance of Disty 16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 12.75 |  | 2.43 | 0 |  | 0% | Work not yet started.
78 | Shingling of CPR & Jungle Clearance of Minor of Disty-16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.8445 |  | 2.45 | 0 |  | 0% | Work not yet started.
79 | Desiltation / Jungle Clearance of Disty # 17 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 9.6951 |  | 2.13 | 0 |  | 0% | Work not yet started.
80 | Shingling of CPR & Jungle Clearance of Disty # 18 its Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 18.009 |  | 4.26 | 0 |  | 0% | Work not yet started.
81 | Shingling of CPR & Jungle Clearance of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.55 | 0.495 | 15.753 |  | 3.96 | 0 |  | 0% | Work not yet started.
82 | Desiltation / Jungle Clearance of M-1 & M-2 of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.829 |  | 5 | 0 |  | 0% | Work not yet started.
83 | Shamizai Irrigation Canal | Swat Irrigation Division-II Matta | 1 | 0.779 | 20.73 | 5150 | 19.5 | 14.26 | 3767 | 73% | Work is in progress
84 | Barwai Irrigation Canal | Swat Irrigation Division-II Matta | 0.3 | 0.2805 | 11.22 | 1300 | 6.1 | 4.05 | 863 | 66% | Work is in progress
85 | Nipki Khel Irrigation Scheme | Swat Irrigation Division -I | 2.2 | 1.76 | 38.87 | 10172.62 | 38.87 | 9.2988 | 2440 | 23.92% | In progress
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086

## 31-01-2023
S# | Name of Canal | Name of Division | Estimated Cost(RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Total Quantity of Silt to be removed (m3) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Total Quantity of Silt removed till date (m3) | Progress Till date in % | Remarks
1 | Jue Shiekh Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 16.29 | 13.03 | 53.35 | 132353 | 53.35 | 31.3 | 77650 | 59% | Work is in progress
2 | Jue Zardad Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 3.6 | 2.88 | 13.1 | 18500 | 13.1 | 5.9 | 8332 | 45% | Work is in progress
3 | Kabul River Canal | Peshawar Canal Division, Peshawar (Kabaul River Canal Sub Division) | 27.855 | 22.284 | 60.35 | 1062085 | 60.35 | 14.85 | 261355 | 25% | Work is in progress
4 | Hazar Khwani Branch | Peshawar Canal Division, Peshawar (Kabul River Canal Sub Division) | 23.2 | 18.56 | 28.04 | 1016303 | 28.04 | 12.8 | 463933 | 46% | Work is in progress
5 | Silt clearance/removal of heaps of Disty No. 9 RD; 41000 to 85500 | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 13.41 | 599.93 | 1 | 0.75 | 449.95 | 75% | In progress
6 | Silt clearance of Power House Minor RD 0 to tail | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 1.28 | 599.9 | 1.28 | 0.83 | 389 | 65% | In progress
7 | Silt clearance of conduit covering portion of 2/9 Hoti Minor RD 4200 to 5000, 5800 to 7000 & 7200 to 7500 | Mardan Irrigation Division Mardan | 0.7 | 0.4546 | 0.7 | 745.53 | 0.7 | 0.48 | 511.22 | 69% | In progress
8 | Silt clearance of 2/9 Hoti Minor RD 0 to 4200, 5000 to 5800 & 7500 to 19000 | Mardan Irrigation Division Mardan | 0.8 | 0.5195 | 5.94 | 921.08 | 2.43 | 1.47 | 557.2 | 60% | In progress
9 | Silt clearance /removal of heaps of kalpani disty RD 0-51000 in reaches and clearance of syphones RD 10500 and 15000 | Mardan Irrigation Division Mardan | 0.7 | 0.4544 | 15.6 | 4463.54 | 5.07 | 4.08 | 3591.96 | 80% | In progress
10 | Silt clearance /removal of heaps of 1/kalpani Kodinaka Minor RD 0-27000 in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 8.22 | 599.94 | 1.82 | 1.26 | 415.34 | 69% | In progress
11 | Silt clearance /removal of heaps of 2/kalpani Taus Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 6.4 | 2801.12 | 5.5 | 3.88 | 1976.06 | 71% | In progress
12 | Silt clearance of 3/9 Toru Minor RD 0 to 15800 | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 4.81 | 2801.12 | 4.81 | 3.6 | 2096.47 | 75% | In progress
13 | Silt clearance of branch 2/kalpani Muhib Banda Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.175 | 0.1308 | 2.89 | 1633.98 | 2 | 1.4 | 1143.79 | 70% | In progress
14 | Silt Clearance of Maho Dheri Minor RD: 4000 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.1493 | 4.57 | 1138.2 | 3.35 | 3.2 | 1087.24 | 96% | In progress
15 | Silt Clearance of Rashakai Minor from RD: 7000 to 31000 in reaches | Mardan Irrigation Division Mardan | 0.6 | 0.3894 | 9.45 | 2972.29 | 7.31 | 7 | 2846.24 | 96% | In progress
16 | Silt Clearance of Nowshera Minor RD:0 - tail in reachers | Mardan Irrigation Division Mardan | 0.35 | 0.2613 | 5.18 | 2059.85 | 3.2 | 3.06 | 1969.73 | 96% | In progress
17 | Silt Clearance of Turlandi Minor Head to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 5.27 | 2134.4 | 4.71 | 4.71 | 2134.4 | 100% | Completed
18 | Silt Clearance of Khan Mahi Branch from RD: 0 to 3000 and RD: 8000 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 13.41 | 2344.08 | 5.48 | 4.8 | 2053.21 | 88% | In progress
19 | Silt Clearance of Bara Banda Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 3.04 | 1703.02 | 3.04 | 2.88 | 1613.39 | 95% | In progress
20 | Removal of heaps of Disty No. 8 RD: 52000 to 68000 in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 9.45 | 1860.72 | 1.43 | 1.43 | 1860.72 | 100% | Completed
21 | Silt Clearance/removal of heaps of Disty No. 7 at RD: 4000 to 14000 in reaches | Mardan Irrigation Division Mardan | 0.15 | 0.1133 | 4.26 | 1400.56 | 3.04 | 3.04 | 1400.56 | 100% | Completed
22 | Silt Clearance/removal of heaps of Sheikh yousaf Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 5.48 | 239.97 | 2.13 | 2.05 | 230.96 | 96% | In progress
23 | Silt Clearance/removal of heaps of 1/9 Guide Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 7 | 479.94 | 2.74 | 2.35 | 411.63 | 86% | In progress
24 | Silt Clearance/removal of heaps of Koragh Branch RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 14.93 | 479.94 | 2.23 | 2.23 | 479.94 | 100% | Completed
25 | Removal of heaps of Disty No.8 RD: 0 to 38000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 11.58 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
26 | Removal of heaps of Disty No.9 RD: 0 to 41000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 12.5 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
27 | Silt Clearance of Disty No.6 from RD: 55+000 to 60+000 in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.183 | 0.155 | 22.25 |  | 0.61 | 0.24 |  | 40% | Work in progress
28 | Silt Clearance of Disty No.6 from RD: 60+000 to 65+000 in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.157 | 0.133 | 22.25 |  | 0.45 | 0.45 |  | 100% | Completed
29 | Silt Clearance of Disty No.6 from RD: 65+000 to 73+000 in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.2 | 0.169 | 22.25 |  | 0.61 | 0.61 |  | 100% | Completed
30 | Silt Clearance of Nisatta Branch from RD: 0+000 to Tail in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.336 | 0.284 | 11.88 |  | 1 | 0.4 |  | 35% | Work in progress
31 | Silt Clearance of Nisatta Minor from RD: 0+000 to Tail in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.218 | 0.184 | 3.35 |  | 2 | 1.3 |  | 65% | Work in progress
32 | Silt Clearance of Palosa Minor from RD: 0+000 to Tail in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.253 | 0.214 | 5.03 |  | 1.35 | 0.67 |  | 50% | Work in progress
33 | Silt Clearance of Zardad and Kheshki Branch in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.348 | 0.294 | 14.49 |  | 7 | 6 |  | 85% | Work in progress
34 | Desiltation / berm cutting/Jungle clearance of Disty No.04, RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 10.11 |  | 2.13 | 0 |  | 0% | yet to be started
35 | Desiltation / berm cutting/Jungle clearance of Disty No.5 & its Minor and sub Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 26.31 |  | 4.75 | 0 |  | 0% | yet to be started
36 | Desiltation / berm cutting/Jungle clearance of Dera Disty RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 16.7 |  | 2.74 | 0.75 |  | 27% | work in progress
37 | Silt clearance/ jungle clearance of Muryali Minor RD. 00-15000 in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.64 |  | 3.04 | 0 |  | 0% | yet to be started
38 | Silt clearance/ jungle clearance including removal of debris of Lachra Minor/Makali Minor in reaches. | CRBC Irrigation Division DIKhan | 0.25 | 0.23 | 3.92 |  | 3 | 0 |  | 0% | yet to be started
39 | Desiltation / berm cutting/Jungle clearance of Mehmood Disty. RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.05 |  | 4.42 | 0 |  | 0% | yet to be started
40 | Desiltation / berm cutting/Jungle clearance of Nawab Minor RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.3 | 0.27 | 7.62 |  | 2.43 | 0.73 |  | 30% | work in progress
41 | Desiltation / berm cutting/Jungle clearance of Disty No.7, i/c Minors of Disty No.7 RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 30.53 |  | 10.18 | 1 |  | 30% | work in progress
42 | Desiltation / berm cutting/Jungle clearance of Disty No. 8 & 8-A, RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.29 |  | 3.95 | 1 |  | 25% | work in progress
43 | Desiltation / berm cutting/Jungle clearance of Disty No.9 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.71 |  | 2.89 | 0 |  | 0% | yet to be started
44 | Desiltation / berm cutting/Jungle clearance of Disty No.10 & 10/A RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11 |  | 3.28 | 0 |  | 0% | yet to be started
45 | Desiltation / berm cutting/Jungle clearance of Disty No. 11 & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 9.1 |  | 5.78 | 0 |  | 0% | yet to be started
46 | Desiltation / berm cutting/Jungle clearance of Disty No. 11-A, & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 21.86 |  | 5.93 | 0 |  | 0% | yet to be started
47 | Desiltation / berm cutting/Jungle clearance of Disty No. 12 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.23 |  | 3.04 | 0.9 |  | 30% | work in progress
48 | Desiltation /Jungle Clearance of Disty # 13 & its System RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.675 | 0.6075 | 21.655 | 3242 | 4.66 | 1.4 | 973 | 30% | Work is in progress.
49 | Shingling of CPR & Jungle Clearance of Disty # 14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.725 | 0.6525 | 21.616 | 3491 | 4.58 | 1.21 | 908 | 26% | Work is in progress.
50 | Shingling of CPR & Jungle Clearance of MD-14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.433 | 2700 | 2.43 | 0.42 | 405 | 15% | Work is in progress.
51 | Shingling of CPR & Jungle Clearance of Disty # 15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.7 | 0.63 | 21.494 |  | 4.5 | 0 |  | 0% | Work not yet started.
52 | Shingling of CPR & Jungle Clearance of MD-15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.325 | 0.2925 | 5.8384 |  | 2.28 | 0 |  | 0% | Work not yet started.
53 | Shingling of CPR & Jungle Clearance of Disty 16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 12.75 |  | 2.43 | 0 |  | 0% | Work not yet started.
54 | Shingling of CPR & Jungle Clearance of Minor of Disty-16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.8445 |  | 2.45 | 0 |  | 0% | Work not yet started.
55 | Desiltation / Jungle Clearance of Disty # 17 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 9.6951 |  | 2.13 | 0 |  | 0% | Work not yet started.
56 | Shingling of CPR & Jungle Clearance of Disty # 18 its Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 18.009 |  | 4.26 | 0 |  | 0% | Work not yet started.
57 | Shingling of CPR & Jungle Clearance of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.55 | 0.495 | 15.753 |  | 3.96 | 0 |  | 0% | Work not yet started.
58 | Desiltation / Jungle Clearance of M-1 & M-2 of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.829 |  | 4 | 0 |  | 0% | Work not yet started.
59 | Shamizai Irrigation Canal | Swat Irrigation Division-II Matta | 1 | 0.779 | 20.73 | 5150 | 19.5 | 15.7 | 4145 | 80% | Work is in progress
60 | Barwai Irrigation Canal | Swat Irrigation Division-II Matta | 0.3 | 0.2805 | 11.22 | 1300 | 6.1 | 4.61 | 983 | 76% | Work is in progress
61 | Nipki Khel Irrigation Scheme | Swat Irrigation Division -I | 2.2 | 1.76 | 38.87 | 10172.62 | 38.87 | 11.7378 | 4072 | 30.2% | In progress
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086

## 01-02-2023
S# | Name of Canal | Name of Division | Estimated Cost(RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Total Quantity of Silt to be removed (m3) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Total Quantity of Silt removed till date (m3) | Progress Till date in % | Remarks
1 | Silt clearance/removal of heaps of Disty No. 9 RD; 41000 to 85500 | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 13.41 | 599.93 | 1 | 0.85 | 509.94 | 85% | In progress
2 | Silt clearance of Power House Minor RD 0 to tail | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 1.28 | 599.9 | 1.28 | 0.83 | 389 | 65% | The canal passing through thickly populated area of Mardan City and the adjacenet locals are throwing garbages into the canal, therefore, it is expedient to clear the remaining portion exact at the end of closure period.
3 | Silt clearance of conduit covering portion of 2/9 Hoti Minor RD 4200 to 5000, 5800 to 7000 & 7200 to 7500 | Mardan Irrigation Division Mardan | 0.7 | 0.4546 | 0.7 | 745.53 | 0.7 | 0.48 | 511.22 | 69% | ..do…
4 | Silt clearance of 2/9 Hoti Minor RD 0 to 4200, 5000 to 5800 & 7500 to 19000 | Mardan Irrigation Division Mardan | 0.8 | 0.5195 | 5.94 | 921.08 | 2.43 | 1.47 | 557.2 | 60% | ..do…
5 | Silt clearance /removal of heaps of kalpani disty RD 0-51000 in reaches and clearance of syphones RD 10500 and 15000 | Mardan Irrigation Division Mardan | 0.7 | 0.4544 | 15.6 | 4463.54 | 5.07 | 4.55 | 4005.74 | 90% | In progress
6 | Silt clearance /removal of heaps of 1/kalpani Kodinaka Minor RD 0-27000 in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 8.22 | 599.94 | 1.82 | 1.26 | 415.34 | 69% | The canal passing through thickly populated area of Mardan City and the adjacenet locals are throwing garbages into the canal, therefore, it is expedient to clear the remaining portion exact at the end of closure period.
7 | Silt clearance /removal of heaps of 2/kalpani Taus Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 6.4 | 2801.12 | 5.5 | 4.48 | 2281.64 | 81% | In progress
8 | Silt clearance of 3/9 Toru Minor RD 0 to 15800 | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 4.81 | 2801.12 | 4.81 | 4.07 | 2370.18 | 85% | In progress
9 | Silt clearance of branch 2/kalpani Muhib Banda Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.175 | 0.1308 | 2.89 | 1633.98 | 2 | 1.7 | 1388.88 | 85% | In progress
10 | Silt Clearance of Maho Dheri Minor RD: 4000 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.1493 | 4.57 | 1138.2 | 3.35 | 3.2 | 1087.24 | 96% | In progress
11 | Silt Clearance of Rashakai Minor from RD: 7000 to 31000 in reaches | Mardan Irrigation Division Mardan | 0.6 | 0.3894 | 9.45 | 2972.29 | 7.31 | 7 | 2846.24 | 96% | In progress
12 | Silt Clearance of Nowshera Minor RD:0 - tail in reachers | Mardan Irrigation Division Mardan | 0.35 | 0.2613 | 5.18 | 2059.85 | 3.2 | 3.06 | 1969.73 | 96% | In progress
13 | Silt Clearance of Turlandi Minor Head to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 5.27 | 2134.4 | 4.71 | 4.71 | 2134.4 | 100% | Completed
14 | Silt Clearance of Khan Mahi Branch from RD: 0 to 3000 and RD: 8000 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 13.41 | 2344.08 | 5.48 | 5.2 | 2224.31 | 95% | In progress
15 | Silt Clearance of Bara Banda Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 3.04 | 1703.02 | 3.04 | 2.88 | 1613.39 | 95% | In progress
16 | Removal of heaps of Disty No. 8 RD: 52000 to 68000 in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 9.45 | 1860.72 | 1.43 | 1.43 | 1860.72 | 100% | Completed
17 | Silt Clearance/removal of heaps of Disty No. 7 at RD: 4000 to 14000 in reaches | Mardan Irrigation Division Mardan | 0.15 | 0.1133 | 4.26 | 1400.56 | 3.04 | 3.04 | 1400.56 | 100% | Completed
18 | Silt Clearance/removal of heaps of Sheikh yousaf Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 5.48 | 239.97 | 2.13 | 2.05 | 230.96 | 96% | In progress
19 | Silt Clearance/removal of heaps of 1/9 Guide Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 7 | 479.94 | 2.74 | 2.62 | 458.92 | 96% | In progress
20 | Silt Clearance/removal of heaps of Koragh Branch RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 14.93 | 479.94 | 2.23 | 2.23 | 479.94 | 100% | Completed
21 | Removal of heaps of Disty No.8 RD: 0 to 38000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 11.58 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
22 | Removal of heaps of Disty No.9 RD: 0 to 41000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 12.5 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
23 | Silt Clearance of Disty No.6 from RD: 55+000 to 60+000 in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.183 | 0.155 | 22.25 |  | 0.61 | 0.49 |  | 80% | Work in progress
24 | Silt Clearance of Disty No.6 from RD: 60+000 to 65+000 in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.157 | 0.133 | 22.25 |  | 0.45 | 0.45 |  | 100% | Completed
25 | Silt Clearance of Disty No.6 from RD: 65+000 to 73+000 in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.2 | 0.169 | 22.25 |  | 0.61 | 0.61 |  | 100% | Completed
26 | Silt Clearance of Nisatta Branch from RD: 0+000 to Tail in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.336 | 0.284 | 11.88 |  | 1 | 0.45 |  | 45% | Work in progress
27 | Silt Clearance of Nisatta Minor from RD: 0+000 to Tail in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.218 | 0.184 | 3.35 |  | 2 | 1.5 |  | 75% | Work in progress
28 | Silt Clearance of Palosa Minor from RD: 0+000 to Tail in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.253 | 0.214 | 5.03 |  | 1.35 | 95 |  | 70% | Work in progress
29 | Silt Clearance of Zardad and Kheshki Branch in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.348 | 0.294 | 14.49 |  | 7 | 6.3 |  | 90% | Work in progress
30 | Jue Shiekh Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 16.29 | 13.03 | 53.35 | 132353 | 53.35 | 34 | 84349 | 64% | Work is in progress
31 | Jue Zardad Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 3.6 | 2.88 | 13.1 | 18500 | 13.1 | 7.2 | 10168 | 55% | Work is in progress
32 | Kabul River Canal | Peshawar Canal Division, Peshawar (Kabaul River Canal Sub Division) | 27.855 | 22.284 | 60.35 | 1062085 | 60.35 | 17.2 | 302714 | 29% | Work is in progress
33 | Hazar Khwani Branch | Peshawar Canal Division, Peshawar (Kabul River Canal Sub Division) | 23.2 | 18.56 | 28.04 | 1016303 | 28.04 | 14.1 | 511051 | 50% | Work is in progress
34 | Warsak Gravity Canal | Warsak Canals Division Peshawar | 18.8 | 16.2 | 68.88 | 23089.8 | 61.26 | 16.88 | 6318.1 | 28% | Work is in progress
35 | Warsak Minor | Warsak Canals Division Peshawar | 0.8 | 0.736 | 5.85 | 873 | 5.85 | 1.37 | 204.61 | 24% | Work is in progress
36 | Kafoor Dheri Minor | Warsak Canals Division Peshawar | 0.4 | 0.368 | 0.94 | 900 | 0.94 | 0 | 0 | 0% | Work is in progress
37 | Shahi Bala Minor | Warsak Canals Division Peshawar | 0.4 | 0.368 | 1.07 | 995 | 1.07 | 0 | 0 | 0% | Work is in progress
38 | Mullazai Minor | Warsak Canals Division Peshawar | 0.3 | 0.552 | 3.35 | 1670 | 3.35 | 0.98 | 485.82 | 31% | Work is in progress
39 | Tehkal Minor | Warsak Canals Division Peshawar | 0.6 | 0.552 | 0.99 | 360 | 0.99 | 0 | 0 | 0% | Work is in progress
40 | Palosai Minor | Warsak Canals Division Peshawar | 0.5 | 0.46 | 0.66 | 455 | 0.66 | 0 | 0 | 0% | Work is in progress
41 | Surizai Minor | Warsak Canals Division Peshawar | 0.4 | 0.368 | 3.02 | 1039 | 3.02 | 0.7 | 241.38 | 24% | Work is in progress
42 | Urmar Minor | Warsak Canals Division Peshawar | 0.8 | 0.736 | 6.71 | 1490 | 6.71 | 1.66 | 369.11 | 25% | Work is in progress
43 | Pabbi Minor | Warsak Canals Division Peshawar | 0.4 | 0.368 | 2.44 | 694 | 2.44 | 1.84 | 524.84 | 76% | Work is in progress
44 | Warsak Lift Canal | Warsak Canals Division Peshawar | 8.39 | 6.5 | 46.63 | 7487.19 | 29.56 | 7.31 | 1852.5 | 25% | Work is in progress
45 | Regi Minor | Warsak Canals Division Peshawar | 0.13 | 0.15 | 0.91 | 270 | 0.91 | 0 | 0 | 0% | Work is in progress
46 | Badabher Minor | Warsak Canals Division Peshawar | 0.26 | 0.29 | 5.49 | 530 | 5.49 | 0 | 0 | 0% | Work is in progress
47 | Warsak Left Bank Canal | Warsak Canals Division Peshawar | 1.69 | 1.554 | 19.29 | 6837.96 | 13.2 | 1.65 | 852.77 | 12% | Work is in progress
48 | Periodical silt clearance of Fore Bay and Feeder Channel Of WPH, Sump Well, Sedimenattion Tank & Raising Main | Warsak Canals Division Peshawar | 2.2 | 1.9 | 3.22 | 4500 | 3.22 | 0 | 0 | 0% | Work is in progress
49 | Silt Clearance of Sherpao Minor from RD 0+00 to Tail in reaches | Tangi Irrigation Sub Division ,Charsadda Division | 0.38 | 0.24 | 3.89 | 1885.63 | 1.48 | 1.184 | 1508.5 | 80% | Work In progress
50 | Silt Clearance of Disty No. 2 RD 0+00 toTail in reaches | Tangi Irrigation Sub Division ,Charsadda Division | 0.4 | 0.256 | 4.84 | 1592.05 | 2.65 | 1.855 | 1114.53 | 70% | Work In progress
51 | Silt Clearance of Behram Dheri Disty from RD: 0+000 to RD: 24+000 in reaches. | Tangi Irrigation Sub Division ,Charsadda Division | 0.4 | 0.32 | 13.967 | 2075.64 | 2.804 | 1.345 | 996.3 | 48% | Work In progress
52 | Silt Clearance of Behram Dheri Disty from RD:24+000 to Tail in reaches. | Tangi Irrigation Sub Division ,Charsadda Division | 0.395 | 0.2528 | 13.967 | 1466.82 | 3.505 | 1.72 | 718.74 | 49% | Work In progress
53 | Silt Clearance of Amir Abad Disty RD: 15+000 to Tail in reaches. | Tangi Irrigation Sub Division ,Charsadda Division | 0.4 | 0.32 | 12.298 | 1713.18 | 2.438 | 1.27 | 890.35 | 52% | Work In progress
54 | Silt Clearance of Barazai Minor head-Tail . | Tangi Irrigation Sub Division ,Charsadda Division | 0.134 | 0.107 | 3.962 | 389.36 | 0.761 | 0.27 | 136.27 | 35% | Work In progress
55 | Silt Clearance of Harichand Disty from RD:0+000 to Tail in reaches | Tangi Irrigation Sub Division ,Charsadda Division | 0.4 | 0.32 | 8.27 | 1316.74 | 2.743 | 1.65 | 790 | 60% | Work In progress
56 | Silt Clearance of Nastrat zai Minor from head-Tail in reaches. | Tangi Irrigation Sub Division ,Charsadda Division | 0.2 | 0.16 | 6.79 | 368.12 | 0.457 | 0.18 | 147.24 | 40% | Work In progress
57 | Silt Clearance of Disty No. 3 head to tail in reaches | Tangi Irrigation Sub Division ,Charsadda Division | 0.35 | 0.224 | 4.57 | 750.4 | 1.066 | 0.69 | 487.74 | 65% | Work In progress
58
59 | Desiltation / berm cutting/Jungle clearance of Disty No.04, RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 10.11 | 5964.26 | 5.64 | 1.41 | 1500 | 25% | yet to be started
60 | Desiltation / berm cutting/Jungle clearance of Disty No.5 & its Minor and sub Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 26.31 | 7688.07 | 8.2 | 0.8 | 800 | 10% | yet to be started
61 | Desiltation / berm cutting/Jungle clearance of Dera Disty RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 16.7 | 5812.06 | 6.55 | 2.7 | 2400 | 41% | work in progress
62 | Silt clearance/ jungle clearance of Muryali Minor RD. 00-15000 in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.64 | 4021.01 | 5.33 | 0 |  | 0% | yet to be started
63 | Silt clearance/ jungle clearance including removal of debris of Lachra Minor/Makali Minor in reaches. | CRBC Irrigation Division DIKhan | 0.25 | 0.23 | 3.92 | 2402.7 | 3.13 | 0 |  | 0% | yet to be started
64 | Desiltation / berm cutting/Jungle clearance of Mehmood Disty. RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.05 | 5737.19 | 4.42 | 1.15 | 1500 | 26% | yet to be started
65 | Desiltation / berm cutting/Jungle clearance of Nawab Minor RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.3 | 0.27 | 7.62 | 2952 | 2.43 | 0.73 |  | 30% | work in progress
66 | Desiltation / berm cutting/Jungle clearance of Disty No.7, i/c Minors of Disty No.7 RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 30.53 | 7801.33 | 10.18 | 1 |  | 30% | work in progress
67 | Desiltation / berm cutting/Jungle clearance of Disty No. 8 & 8-A, RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.29 | 3999 | 3.95 | 1.8 | 1799 | 45% | work in progress
68 | Desiltation / berm cutting/Jungle clearance of Disty No.9 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.71 |  | 2.89 | 0 |  | 0% | yet to be started
69 | Desiltation / berm cutting/Jungle clearance of Disty No.10 & 10/A RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11 | 3950.22 | 3.19 | 0 |  | 0% | yet to be started
70 | Desiltation / berm cutting/Jungle clearance of Disty No. 11 & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 9.1 | 5670.47 | 10.66 | 0 |  | 0% | yet to be started
71 | Desiltation / berm cutting/Jungle clearance of Disty No. 11-A, & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 21.86 | 7695.14 | 5.93 | 0 |  | 0% | yet to be started
72 | Desiltation / berm cutting/Jungle clearance of Disty No. 12 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.23 | 5762.51 | 4.11 | 0.9 |  | 30% | work in progress
73 | Desiltation /Jungle Clearance of Disty # 13 & its System RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.675 | 0.6075 | 21.655 | 4256.03 | 4.66 | 2.43 | 2043 | 52% | Work is in progress.
74 | Shingling of CPR & Jungle Clearance of Disty # 14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.725 | 0.6525 | 21.616 | 4176.75 | 4.58 | 2.7 | 2088 | 59% | Work is in progress.
75 | Shingling of CPR & Jungle Clearance of MD-14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.433 | 2145.01 | 2.43 | 0.95 | 915 | 39% | Work is in progress.
76 | Shingling of CPR & Jungle Clearance of Disty # 15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.7 | 0.63 | 21.494 |  | 4.5 | 0 |  | 0% | Work not yet started.
77 | Shingling of CPR & Jungle Clearance of MD-15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.325 | 0.2925 | 5.8384 |  | 2.28 | 0 |  | 0% | Work not yet started.
78 | Shingling of CPR & Jungle Clearance of Disty 16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 12.75 |  | 2.43 | 0 |  | 0% | Work not yet started.
79 | Shingling of CPR & Jungle Clearance of Minor of Disty-16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.8445 |  | 2.45 | 0 |  | 0% | Work not yet started.
80 | Desiltation / Jungle Clearance of Disty # 17 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 9.6951 |  | 2.13 | 0 |  | 0% | Work not yet started.
81 | Shingling of CPR & Jungle Clearance of Disty # 18 its Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 18.009 |  | 4.26 | 0 |  | 0% | Work not yet started.
82 | Shingling of CPR & Jungle Clearance of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.55 | 0.495 | 15.753 |  | 3.96 | 0 |  | 0% | Work not yet started.
83 | Desiltation / Jungle Clearance of M-1 & M-2 of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.829 |  | 4 | 0 |  | 0% | Work not yet started.
84 | Shamizai Irrigation Canal | Swat Irrigation Division-II Matta | 1 | 0.779 | 20.73 | 5150 | 19.5 | 17.3 | 4568 | 89% | Work is in progress
85 | Barwai Irrigation Canal | Swat Irrigation Division-II Matta | 0.3 | 0.2805 | 11.22 | 1300 | 6.1 | 5.46 | 1164 | 90% | Work is in progress
8 | Silt clearance of Doaba Canal RD. 0+000-4+500 in Reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.226 | 0.144 | 14.7828 | 1045.86 | 0.48 | 0.39 | 836.688 | 80% | In progress
9 | Silt clearance of Doaba Canal RD. 4+600-9+100 in Reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.242 | 0.1548 | 14.7828 | 1128.21 | 0.58 | 0.493 | 902.568 | 80% | In progress
10 | Silt clearance of Doaba Canal RD. 9+200-13+000 in Reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.343 | 0.22 | 14.7828 | 1595.38 | 0.548 | 0.438 | 1196.535 | 75% | In progress
11 | Silt clearance of Doaba Canal RD. 13+200-17+000 in Reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.341 | 0.218 | 14.7828 | 1586.32 | 0.6 | 0.5 | 1269.056 | 80% | In progress
12 | Silt Clearance of Doaba Canal RD.17+300-21+200 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.338 | 0.22 | 14.7828 | 1572.55 | 0.672 | 0.537 | 1289.491 | 82% | In progress
13 | Silt Clearance of Doaba Canal RD.21+250-24+475 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.312 | 0.2 | 14.7828 | 1454.79 | 0.74 | 0.555 | 1091.0925 | 75% | In progress
14 | Silt clearance of New Michni Branch RD. 0+000-4+100 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.3439 | 0.22 | 11.027 | 741.2 | 0.685 | 0.6 | 652.256 | 88% | In progress
15 | Silt clearance of New Michni Branch RD. 4+200-8+300 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.332 | 0.212 | 11.027 | 715.46 | 0.731 | 0.643 | 643.914 | 90% | In progress
16 | Silt clearance of New Michni Branch RD 8+500-12+000 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.32 | 0.2 | 11.027 | 689.67 | 0.609 | 0.4872 | 551.736 | 80% | In progress
17 | Silt Clearance of Dalazak Minor RD. 0+000-4+000 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.1244 | 0.796 | 3.96 | 451.34 | 0.67 | 0.502 | 333.99 | 74% | In progress
18 | Silt Clearance of Subhan Khwar Disty RD.0+000-4+500 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.315 | 0.201 | 4.81 | 680.17 | 0.84 | 0.54 | 442.11 | 65% | In progress
19 | Silt clearance of Ichri Branch RD. 0-4366 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.15 | 0.096 | 1.33 | 576.89 | 0.67 | 0.402 | 346.134 | 60% | In progress
20 | Silt Clearance of Shabqadar Branch RD.0+000-15+000 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.38 | 0.24 | 4.5 | 819.21 | 1.645 | 1.148 | 573.447 | 70% | In progress
21 | Silt Clearance of Iceland Canal RD..0+00-Tail in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.35 | 0.224 | 8.83 | 2045.2 | 2.103 | 0 |  | 0% | Not yet started
22 | Silt Clearance of Samkana Branch RD.0+000-30+000 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.3 | 0.192 | 9.14 | 2041.66 | 2.103 | 0 |  | 0% | Not yet Strated
101 | Silt clearance from RD:0+00 to RD:8+000 in reaches of Ghazai Khani Flow Irrigation Scheme | Swat Irrigation Division -I | 0.24 | 0.213 | 7.92 | 1339.39 | 7.92 | 1.52 | 605 | 45% | Work in Progress
102 | "Silt clearance from RD:0+00 to RD:12+000 in reaches of Karshalizara Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.1199 | 7.92 | 613 | 2.44 | 0.96 | 339.85 | 55% | Work in Progress
103 | "Silt clearance from RD:0+00 to RD:20+000 in reaches of Charorai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.15 | 0.135 | 7.92 | 766.25 | 4.88 | 1.46 | 665.53 | 87% | Work in Progress
104 | "Silt clearance from RD:0+00 to RD:12+000 in reaches of Kuriya Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.25 | 0.225 | 7.92 | 1397.44 | 9.14 | 3.05 | 500 | 36% | Work in Progress
105 | "Silt clearance from RD:0+00 to RD:9+000 in reaches of Elai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 7.92 | 613 | 2.74 | 0.88 | 229.4 | 37% | Work in Progress
106 | "Silt clearance from RD:0+00 to RD:60+000 in reaches of Budal Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 7.92 | 672.53 | 3.66 | 1.83 | 220.25 | 33% | Work in Progress
107 | "Silt clearance from RD:0+00 to RD:16+000 in reaches of Singarai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 7.92 | 669.7 | 6.1 | 1.68 | 240 | 36% | Work in Progress
108 | "Silt clearance from RD:0+00 to RD:26+000 in reaches of Bajkata Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.08 | 0.072 | 7.92 | 408.66 | 3.66 | 1.37 | 210 | 51% | Work in Progress
109 | Silt clearance from RD:0+00 to RD:34+000 in reaches of Gagra Flow Irrigation Scheme | Swat Irrigation Division -I | 0.5 | 0.4 | 7.92 | 2797 | 10.36 | 3.66 | 1200 | 43% | Work in Progress
110 | Removal of Heaps / Clearance of Bari Band Disty RD: 39+500-88+600 in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.33775 | 14.96 | 1435.76 | 8.21 | 3.5 | 900 | 42.63% | Work in Progress
111 | Removal of Heaps / Clearance of Hero Shah Minor RD: 0 -38+000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 11.58 | 2446.93 | 11.58 | 5 | 950 | 43.18% | Work in Progress
112 | Removal of Heaps / Clearance of Kalu Shah Disty and Dundian Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.1 | 0.098 | 7.69 | 785.8 | 5 | 5 | 785 | 100% | Completed
113 | Removal of Heaps / Clearance of Sarwala Disty and Lund Khwar Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 18.29 | 3172.99 | 10.06 | 5.5 | 1600 | 54.67% | Work in Progress
114 | Removal of Heaps / Clearance of Said Abad Disty and Pir Abad Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 20.42 | 3113.1 | 7.31 | 4 | 1550 | 54.72% | Work in Progress
115 | Removal of Heaps / Clearance of Katlang Disty from RD: 0-40+000 in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 12.19 | 1910.43 | 7.61 | 4 | 975 | 52.56% | Work in Progress
116 | Removal of Heaps / Clearance of Shamozai Disty/ Syphon and Likpani Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.392 | 17.67 | 2730.62 | 13.01 | 4.5 | 1000 | 34.59% | Work in Progress
117 | Removal of Heaps / Clearance of Dheri Minor and Tail Minor Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.15 | 0.147 | 7.01 | 1211.68 | 6 | 4.5 | 1000 | 75% | Work in Progress
118 | Silt & Shingle Clearance of P.C Minor from RD 0+000 To Tail in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.3395 | 12.881 | 1410.59 | 4.54 | 1.2 | 372.84 | 26.43% | Work in Progress
119 | Clearance of Shingri Minor from RD 0-17250 in reaches. | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.309 | 530.92 | 2.499 | 1.22 | 259.19 | 48.82% | Work in Progress
120 | Clearance of Meherdi Minor from RD 0-31000 in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2425 | 9.451 | 1809.24 | 6.858 | 3.05 | 804.63 | 44.47% | Work in Progress
121 | Clearance of Kalu Branch from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.33 | 0.3218 | 11.563 | [5 empty] | Not yet started
122 | Clearance of Hathian Minor from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.05 | 0.04875 | 2.35 | [5 empty] | Not yet started
123 | Clearance of Jalala Disty from RD: 29000 to Tail in reaches | Malakand Irrigation Division Malakand | 0.37 | 0.3607 | 14.024 | 1476.73 | 5900 | 5000 | 1033.71 | 84.74% | Work in Progress
124 | Clearance of Pirsaddo Disty, Ghano Minor and Qutab Gharh Minor from : H-Tail to Tail in reaches. | Malakand Irrigation Division Malakand | 0.35 | 0.412 | 1.88 | [5 empty] | Not yet started
125 | Clearance of Shergarh Minor from Head to Rd:12+000 in reaches. | Malakand Irrigation Division Malakand | 0.15 | 0.146 | 7.752 | [5 empty] | Not yet started
126 | Clearance of Shergarh Minor from Rd:12+000 tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 7.7752 | 1195.13 | 6000 | 5000 | 776.83 | 84.74% | Work in Progress
127 | Clearance of Spokanda Disty from RD: 18000 to Tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 5.659 | [5 empty] | Not yet started
128 | Nipki Khel Irrigation Scheme | Swat Irrigation Division -I | 2.2 | 1.76 | 38.87 | 10172.62 | 38.87 | 14.4817 | 4324 | 37.26% | Work in Progress
129 | Bazai Main Canal Head Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 |  | 21 | 21 |  | 100% | Completed
130 | Wartair Disty | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 6 |  | 6 | 6 |  | 100% | Completed
131 | Kharki Disty No. 02 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 3.3 |  | 3.3 | 3.3 |  | 100% | Completed
132 | Additional Minor No. 03, 06 and Bazai Disty No. 01. | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | 16.8 |  | 16.8 | 3 |  | 100% | Completed
133 | Bazai Main Canal, Syphon No. 4431, 5851, 12530, 13590, 14842, 18400, 47527 & 58853 | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | [5 empty] | 70% | Work in Progress
134 | Bazai Disty No. 04, Bazai Minor No. 09, 11 and 12. | Malakand Irrigation Division Malakand | 0.27 | 0.26625 | 15.2 |  | 9 | te |  | 100% | Completed
135 | Clearance of Syphon 79205, 93480 and 97962. | Malakand Irrigation Division Malakand | 0.1 | 0.975 |  |  |  | d |  | 20% | Work in Progress
136 | Bazai Disty No. 03 and Bazai Minor No. 05. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | 20.5 |  | 20.5 | 7 |  | 100% | Completed
137 | Bazai Main Canal Tail Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 |  | 0 | 0 |  | 0% | Not Yet start
138 | KM-1 RD: 0-2976 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  |  | 0.9 | 0.9 |  | 100% | Completed
139 | KM-1 RD: 0-1500, 22000-29000 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  |  | 2.6 | 2.6 |  | 100% | Completed
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086

## 02-02-2023
Name of Canal | Name of Division | Estimated Cost(RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Total Quantity of Silt to be removed (m3) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Total Quantity of Silt removed till date (m3) | Progress Till date in % | Remarks
Silt Clearance of Sherpao Minor from RD 0+00 to Tail in reaches | Tangi Irrigation Sub Division ,Charsadda Division | 0.38 | 0.24 | 3.89 | 1885.63 | 1.48 | 1.26 | 1602.78 | 85% | Work In progress
Silt Clearance of Disty No. 2 RD 0+00 toTail in reaches | Tangi Irrigation Sub Division ,Charsadda Division | 0.4 | 0.256 | 4.84 | 1592.05 | 2.65 | 1.99 | 1194.03 | 75% | Work In progress
Silt Clearance of Behram Dheri Disty from RD: 0+000 to RD: 24+000 in reaches. | Tangi Irrigation Sub Division ,Charsadda Division | 0.4 | 0.32 | 13.967 | 2075.64 | 2.804 | 1.51 | 1120.84 | 54% | Work In progress
Silt Clearance of Behram Dheri Disty from RD:24+000 to Tail in reaches. | Tangi Irrigation Sub Division ,Charsadda Division | 0.395 | 0.2528 | 13.967 | 1466.82 | 3.505 | 1.96 | 821.41 | 56% | Work In progress
Silt Clearance of Amir Abad Disty RD: 15+000 to Tail in reaches. | Tangi Irrigation Sub Division ,Charsadda Division | 0.4 | 0.32 | 12.298 | 1713.18 | 2.438 | 1.44 | 1010.77 | 59% | Work In progress
Silt Clearance of Barazai Minor head-Tail . | Tangi Irrigation Sub Division ,Charsadda Division | 0.134 | 0.107 | 3.962 | 389.36 | 0.761 | 0.32 | 163.53 | 42% | Work In progress
Silt Clearance of Harichand Disty from RD:0+000 to Tail in reaches | Tangi Irrigation Sub Division ,Charsadda Division | 0.4 | 0.32 | 8.27 | 1316.74 | 2.743 | 1.78 | 855.88 | 65% | Work In progress
Silt Clearance of Nastrat zai Minor from head-Tail in reaches. | Tangi Irrigation Sub Division ,Charsadda Division | 0.2 | 0.16 | 6.79 | 368.12 | 0.457 | 0.21 | 165.65 | 45% | Work In progress
Silt Clearance of Disty No. 3 head to tail in reaches | Tangi Irrigation Sub Division ,Charsadda Division | 0.35 | 0.224 | 4.57 | 750.4 | 1.066 | 0.76 | 532.78 | 71% | Work In progress
Silt Clearance of Badwan Kharif Irrigation Scheme at RD 0+00 To Tail. | Chakdara Irrigation Sub Division ,Dir Division | 0.9 | 0.8957 | 22.18 | 4635.35 | 22.18 | 3.65 | 1001.85 | 21.61% | Work In progress
Silt Clearance of Lower Siran Canal RD 0-14000 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3110.16 | 3.04 | 0.1524 | 115 | 4% | Work In progress
Silt clearance of Sarai Saleh NPC Rd 0-10000 in reaches | Haripur Irrigation Division Haripur | 0.35 | 0.283 | 15.85 | 1271 | 3.04 | 2.43 | 1016.8 | 80% | Work in porgress
Silt clearance of Sarai Saleh NPC Rd 10000-17000 i/c Minor No.1 in reaches | Haripur Irrigation Division Haripur | 0.3 | 0.24 | 15.85 | 1131.96 | 2.13 | 0.53 | 282.99 | 25% | Work in porgress
Silt clearance of Sarai Saleh NPC Rd 17000-30000 i/c Minor No.2 in reaches | Haripur Irrigation Division Haripur | 0.35 | 0.28 | 15.85 | 1347 | 3.96 | 1.31 | 404.1 | 30% | Work in porgress
Clearance of Daur Main Canal Rd 0-tail | Haripur Irrigation Division Haripur | 0.15 | 0.1216 | 0.838 | 555.2 | 0.838 | 0.838 | 555.2 | 100% | Wotrk completed
Silt Clearance of Disty No.02 RD 0-20000 in reaches. | Haripur Irrigation Division Haripur | 0.25 | 0.2 | 6.62 | 1287.6 | 6.09 | 5.79 | 1210.58 | 95% | Work in progress
Silt Clearance of Main KRBC RD 11000-42000 in reaches | Haripur Irrigation Division Haripur | 0.25 | 0.225 | 12.8 | 1287.6 | 9.45 | 7.01 | 1030.08 | 80% | Work in pogress
Silt Clearance Disty No.04 RD 0-24000 in reaches. | Haripur Irrigation Division Haripur | 0.3 | 0.24 | 7.31 | 1545.12 | 7.31 | 4.87 | 1125.23 | 65% | Work in progress
Silt Clearance of Lower Siran Canal RD 14000-36500 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3142.51 | 4.26 | 0.6096 | 473.69 | 15% | Work in progress
Silt Clearance of Disty No.03 i/c Ziarat Minor and Bandi Minor in reaches. | Haripur Irrigation Division Haripur | 0.3 | 0.24 | 10.67 | 1545.12 | 10.67 | 2.13 | 309.02 | 23% | Work in porgress
Silt Clearance of Lower Siran Canal Hathi Maira Branch & Gandian Minor RD 36500 in reaches | Mansehra Irrigation Division Mansehra | 0.55 | 0.4954 | 26.21 | 2080.06 | 12.1 | 2.7432 | 471.39 | 23% | Work in progress
Silt Clearance of Disty No.1 i/c Balartop & Kamalpur Minors in reaches. | haripur Irrigation Division Haripur | 0.3 | 0.24 | 10.36 | 1545.12 | 10.36 | 5.18 | 723.12 | 60% | Work in progress
Silt Clearance of KLBC Rd 0-26000 in reaches | haripur Irrigation Division Haripur | 0.3 | 0.24 | 7.92 | 1545.12 | 7.92 | 0 | 0 | 0 | not yet started due to decisiion made in meeting with XEN WAPDA, PMO and CDA Islambad authorities and work will be started from 15th February 2023
Silt clearance of Sarai Saleh NPC Rd 30000-40000 i/c Minor No. 3 in reaches | HAripur Irrigation Division Haripur | 0.25 | 0.2 | 15.85 | 946 | 3.04 | 0 | 0 | 0 | Not yet started
Clearance of Main Rangila Irrigation system i/c Rangila Tank | Haripur Irrigation Division Haripur | 0.2 | 0.173 | 2.21 | 559 | 2.21 | 0 | 0 | 0 | Not yet started
Silt Clearance of Upper Siran Canal from RD 30000-61000 in reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2110 | 9.44 | 1.52 | 340 | 16% | Work in progress
Silt Clearance of Dhodial Minor Upper Siran Canal in reaches | Mansehra Irrigation Division Mansehra | 0.22 | 0.1981 | 5.24 | 1135 | 5.24 | 1.21 | 263 | 23% | Work in progress
Silt Clearance of Chak Muneem Minor. | Haripur Irrigation Division Haripur | 0.2 | 0.16 | 7.01 | 1030.8 | 7.01 | 0 | 0 | 0 | Not yet started
Silt Clearance of Disty No.6 from RD: 55+000 to 60+000 in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.183 | 0.155 | 22.25 |  | 0.61 | 0.61 | 100% | Completed
Silt Clearance of Disty No.6 from RD: 60+000 to 65+000 in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.157 | 0.133 | 22.25 |  | 0.45 | 0.45 | 100% | Completed
Silt Clearance of Disty No.6 from RD: 65+000 to 73+000 in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.2 | 0.169 | 22.25 |  | 0.61 | 0.61 | 100% | Completed
Silt Clearance of Nisatta Branch from RD: 0+000 to Tail in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.336 | 0.284 | 11.88 |  | 1 | 0.55 | 55% | Work in progress
Silt Clearance of Nisatta Minor from RD: 0+000 to Tail in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.218 | 0.184 | 3.35 |  | 2 | 1.7 | 85% | Work in progress
Silt Clearance of Palosa Minor from RD: 0+000 to Tail in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.253 | 0.214 | 5.03 |  | 1.35 | 1.08 | 80% | Work in progress
Silt Clearance of Zardad and Kheshki Branch in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.348 | 0.294 | 14.49 |  | 7 | 6.3 | 90% | Work in progress
Jue Shiekh Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 16.29 | 13.03 | 53.35 | 132353 | 53.35 | 35.1 | 87078 | 66% | Work is in progress
Jue Zardad Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 3.6 | 2.88 | 13.1 | 18500 | 13.1 | 9.3 | 13134 | 71% | Work is in progress
Kabul River Canal | Peshawar Canal Division, Peshawar (Kabaul River Canal Sub Division) | 27.855 | 22.284 | 60.35 | 1062085 | 60.35 | 20.4 | 359032 | 34% | Work is in progress
Hazar Khwani Branch | Peshawar Canal Division, Peshawar (Kabul River Canal Sub Division) | 23.2 | 18.56 | 28.04 | 1016303 | 28.04 | 16 | 579916 | 57% | Work is in progress
Silt clearance/removal of heaps of Disty No. 9 RD; 41000 to 85500 | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 13.41 | 599.93 | 1 | 0.95 | 569.93 | 95% | In progress
Silt clearance of Power House Minor RD 0 to tail | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 1.28 | 599.9 | 1.28 | 0.83 | 389 | 65% | The canal passing through thickly populated area of Mardan City and the adjacenet locals are throwing garbages into the canal, therefore, it is expedient to clear the remaining portion exact at the end of closure period.
Silt clearance of conduit covering portion of 2/9 Hoti Minor RD 4200 to 5000, 5800 to 7000 & 7200 to 7500 | Mardan Irrigation Division Mardan | 0.7 | 0.4546 | 0.7 | 745.53 | 0.7 | 0.48 | 511.22 | 69% | ..do…
Silt clearance of 2/9 Hoti Minor RD 0 to 4200, 5000 to 5800 & 7500 to 19000 | Mardan Irrigation Division Mardan | 0.8 | 0.5195 | 5.94 | 921.08 | 2.43 | 1.47 | 557.2 | 60% | ..do…
Silt clearance /removal of heaps of kalpani disty RD 0-51000 in reaches and clearance of syphones RD 10500 and 15000 | Mardan Irrigation Division Mardan | 0.7 | 0.4544 | 15.6 | 4463.54 | 5.07 | 4.8 | 4225.84 | 95% | In progress
Silt clearance /removal of heaps of 1/kalpani Kodinaka Minor RD 0-27000 in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 8.22 | 599.94 | 1.82 | 1.26 | 415.34 | 69% | The canal passing through thickly populated area of Mardan City and the adjacenet locals are throwing garbages into the canal, therefore, it is expedient to clear the remaining portion exact at the end of closure period.
Silt clearance /removal of heaps of 2/kalpani Taus Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 6.4 | 2801.12 | 5.5 | 5.26 | 2678.89 | 96% | In progress
Silt clearance of 3/9 Toru Minor RD 0 to 15800 | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 4.81 | 2801.12 | 4.81 | 4.55 | 2649.71 | 95% | In progress
Silt clearance of branch 2/kalpani Muhib Banda Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.175 | 0.1308 | 2.89 | 1633.98 | 2 | 1.9 | 1552.28 | 95% | In progress
Silt Clearance of Maho Dheri Minor RD: 4000 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.1493 | 4.57 | 1138.2 | 3.35 | 3.2 | 1087.24 | 96% | In progress
Silt Clearance of Rashakai Minor from RD: 7000 to 31000 in reaches | Mardan Irrigation Division Mardan | 0.6 | 0.3894 | 9.45 | 2972.29 | 7.31 | 7 | 2846.24 | 96% | In progress
Silt Clearance of Nowshera Minor RD:0 - tail in reachers | Mardan Irrigation Division Mardan | 0.35 | 0.2613 | 5.18 | 2059.85 | 3.2 | 3.06 | 1969.73 | 96% | In progress
Silt Clearance of Turlandi Minor Head to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 5.27 | 2134.4 | 4.71 | 4.71 | 2134.4 | 100% | Completed
Silt Clearance of Khan Mahi Branch from RD: 0 to 3000 and RD: 8000 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 13.41 | 2344.08 | 5.48 | 5.2 | 2224.31 | 95% | In progress
Silt Clearance of Bara Banda Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 3.04 | 1703.02 | 3.04 | 2.88 | 1613.39 | 95% | In progress
Removal of heaps of Disty No. 8 RD: 52000 to 68000 in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 9.45 | 1860.72 | 1.43 | 1.43 | 1860.72 | 100% | Completed
Silt Clearance/removal of heaps of Disty No. 7 at RD: 4000 to 14000 in reaches | Mardan Irrigation Division Mardan | 0.15 | 0.1133 | 4.26 | 1400.56 | 3.04 | 3.04 | 1400.56 | 100% | Completed
Silt Clearance/removal of heaps of Sheikh yousaf Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 5.48 | 239.97 | 2.13 | 2.05 | 230.96 | 96% | In progress
Silt Clearance/removal of heaps of 1/9 Guide Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 7 | 479.94 | 2.74 | 2.62 | 458.92 | 96% | In progress
Silt Clearance/removal of heaps of Koragh Branch RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 14.93 | 479.94 | 2.23 | 2.23 | 479.94 | 100% | Completed
Removal of heaps of Disty No.8 RD: 0 to 38000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 11.58 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
Removal of heaps of Disty No.9 RD: 0 to 41000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 12.5 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
Silt Clearance of Gandigar Irrigation Scheme Dir Upper From RD 00 To 30000 | Dir Irrigation Division Dir Lower at Timergara | 0.7 | 0.56 | 9.14 | 3543.3 | 8 | 0 | 0 | 0 | Work will be started tomorrow
Silt Clearance of Gandigar Irrigation Scheme Dir Upper From RD 30000 To 60000 | Dir Irrigation Division Dir Lower at Timergara | 0.7 | 0.56 | 9.14 | 3543.3 | 9.14 | 0 | 0 | 0 | Work will be started tomorrow
Silt Clearance of Gandigar Irrigation Scheme Dir Upper From RD 60000 To Tail and Silt Clearance of Ganorai Irrigation scheme from Head To Tail | Dir Irrigation Division Dir Lower at Timergara | 0.8 | 0.614 | 22.56 | 4049.5 | 20 | 0.9 | 250.5 | 6% | Work in progress
Silt Clearance of Darora Jughabanj Irrigation Scheme Dir Upper From RD 00 To 40000 | Dir Irrigation Division Dir Lower at Timergara | 0.6 | 0.354 | 12.19 | 3037.5 | 12.19 | 1.5 | 230.67 | 7.5% | Work in progress
Silt Clearance of Darora Jughabanj Irrigation Scheme Dir Upper From RD 40000 to Tail | Dir Irrigation Division Dir Lower at Timergara | 0.6 | 0.48 | 9.75 | 3037.5 | 9.75 | 0.15 | 45.67 | 1.5% | Work in progress
Warsak Gravity Canal | Warsak Canals Division Peshawar | 18.8 | 16.2 | 68.88 | 23089.8 | 61.26 | 17.2 | 6318.1 | 35% | Work is in progress
Warsak Minor | Warsak Canals Division Peshawar | 0.8 | 0.736 | 5.85 | 873 | 5.85 | 1.37 | 204.61 | 26% | Work is in progress
Kafoor Dheri Minor | Warsak Canals Division Peshawar | 0.4 | 0.368 | 0.94 | 900 | 0.94 | 0 | 0 | 0% | Work is in progress
Shahi Bala Minor | Warsak Canals Division Peshawar | 0.4 | 0.368 | 1.07 | 995 | 1.07 | 0 | 0 | 0% | Work is in progress
Mullazai Minor | Warsak Canals Division Peshawar | 0.3 | 0.552 | 3.35 | 1670 | 3.35 | 0.98 | 485.82 | 35% | Work is in progress
Tehkal Minor | Warsak Canals Division Peshawar | 0.6 | 0.552 | 0.99 | 360 | 0.99 | 0 | 0 | 0% | Work is in progress
Palosai Minor | Warsak Canals Division Peshawar | 0.5 | 0.46 | 0.66 | 455 | 0.66 | 0 | 0 | 0% | Work is in progress
Surizai Minor | Warsak Canals Division Peshawar | 0.4 | 0.368 | 3.02 | 1039 | 3.02 | 0.7 | 241.38 | 30% | Work is in progress
Urmar Minor | Warsak Canals Division Peshawar | 0.8 | 0.736 | 6.71 | 1490 | 6.71 | 1.66 | 369.11 | 25% | Work is in progress
Pabbi Minor | Warsak Canals Division Peshawar | 0.4 | 0.368 | 2.44 | 694 | 2.44 | 1.84 | 524.84 | 76% | Work is in progress
Warsak Lift Canal | Warsak Canals Division Peshawar | 8.39 | 6.5 | 46.63 | 7487.19 | 29.56 | 7.5 | 1852.5 | 30% | Work is in progress
Regi Minor | Warsak Canals Division Peshawar | 0.13 | 0.15 | 0.91 | 270 | 0.91 | 0 | 0 | 0% | Work is in progress
Badabher Minor | Warsak Canals Division Peshawar | 0.26 | 0.29 | 5.49 | 530 | 5.49 | 0 | 0 | 0% | Work is in progress
Warsak Left Bank Canal | Warsak Canals Division Peshawar | 1.69 | 1.554 | 19.29 | 6837.96 | 13.2 | 1.86 | 852.77 | 25% | Work is in progress
Periodical silt clearance of Fore Bay and Feeder Channel Of WPH, Sump Well, Sedimenattion Tank & Raising Main | Warsak Canals Division Peshawar | 2.2 | 1.9 | 3.22 | 4500 | 3.22 | 0 | 0 | 0% | Work is in progress
Swabi Irrigation Division-II Swabi
Clearance of Topi Lift Irrigation Channels RD;00-Tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 4.88 | 1215.87 | 4.87 | 2.44 | 607.94 | 50% | Work in progress
Clearance of Topi & Zarobi Minors from RD;00 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | Topi =4.24 Zarobi =4.27 | 1159.72 | 3.05 | 1.52 | 494.05 | 50% | Work in progress
Clearance/Repair of Badri Lift Irrigation Scheme | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 0.34 | 607.12 | 0.33 | 0.33 | 607.12 | 100% | Competed
Clearance of Kotha Disty; from RD;00 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.24 | 0.24 | 17.53 | 1389.07 | 1.89 | 1.89 | 1389.07 | 100% | Competed
Clearance of Pehur main Canal from RD;46000 to RD;54000 | Swabi Irrigation Division-II Swabi | 0.18 | 0.18 | 51.4 | 1042.24 | 0.53 | 0.53 | 1042.24 | 100% | Competed
Clearance of Pehur Main Canal from RD;54500 to RD;66000 | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 51.4 | 1130.88 | 0.55 | 0.27 | 565.44 | 50% | Work in progress
Clearance of Pehur Main Canal from RD;66000 to RD;85000 | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.92 | 0.7 | 0.4 | 793.79 | 57% | Work in progress
Clearance of Pehur Main Canal RD;85000 to RD;93000 | Swabi Irrigation Division-II Swabi | 0.16 | 0.16 | 51.4 | 976.63 | 0.63 | 0.06 | 95.65 | 10% | Work in progress
Clearance of Pehur Main Canal from RD;93500 to RD;98000 | Swabi Irrigation Division-II Swabi | 0.17 | 0.17 | 51.4 | 1033.5 | 0.32 | 0.16 | 516.75 | 50% | Work in progress
Clearance of Pehur Main Canal from RD;98500 to RD;113000 | Swabi Irrigation Division-II Swabi | 0.18 | 0.18 | 51.4 | 1094.71 | 0.61 | 0.46 | 792.24 | 75% | Work in progress
Clearance of Kaddi, Zaida, Zakarriya & Sheikhdheri Minors from RD;00 to Tail | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | Kaddi= 5.79 Zaida= 3.81 Zakary=3.43 S/Dher=2.95 | 1519.85 | 0.46 | 0.23 | 759.92 | 50% | Work in progress
Clearance of Pehur Main Canal System from RD;113000 to RD;117000 | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 51.4 | 883 | 0.4 | 0.3 | 685.62 | 77% | Work in progress
Clearance of Pehur Main Canal System from RD;117000 to RD;122000 | Swabi Irrigation Division-II Swabi | 0.12 | 0.12 | 51.4 | 729.53 | 0.22 | 0.11 | 364.76 | 50% | Work in progress
Clearance of Pehur main Canal System from RD;122000 to RD;133000 | Swabi Irrigation Division-II Swabi | 0.13 | 0.13 | 51.4 | 790.91 | 0.4 | 0.34 | 649.45 | 85% | Work in progress
Clearance of flood deposition from the bed of PMC from RD;13300 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1519.85 | 0.46 | 0.23 | 759.92 | 50% | Work in progress
Clearance of PMC System from RD;133000 to 140000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 51.4 | 1738.06 | 0.85 | 0.61 | 1214.72 | 71% | Work in progress
Clearance of PMC Systems from RD;145000 to RD;150000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.23 | 0.23 | 51.4 | 1398.26 | 0.43 | 0.21 | 699.13 | 50% | Work in progress
Clearance of PMC System from RD;150500 to RD;162000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1519.85 | 0.46 | 0.23 | 759.92 | 50% | Work in progress
Clearance of PMC System from RD;162100 to Tail & other allied Branches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.85 | 3.23 | 1.68 | 533.52 | 52% | Work in progress
Clearance of Thanodher Disty: & Bazar Minor from RD;00 to Tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | Thano=6.00 Bazar=7.47 | 1215.88 | 0.37 | 0.19 | 607.94 | 50% | Work in progress
Clearance of flood deposition and silt clearance of ¦Indus Branch RD:74500 Tail in reaches. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 18.54 | 4478 | 11.89 | 8.69 | 3001.26 | 73% | Work in progress
Silt Clearance of Dagi Minor from RD:0- 37000 in reaches i/c repair to out lets & other allied structures. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 11.28 | 4482 | 9.15 | 3.05 | 1401.7 | 33% | Work in progress
Silt Clearance of Dandoka Minor from RD:0-Tail in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.03 | 0 | 0 | 0 | 0 |  | yet to be started
Silt Clearance of Sudher Minor RD:0 - tail in reaches & other allied structures | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 2.29 | 0 | 0 | 0 | 0 | 0 | yet to be started
Silt Clearance of Yar Hussain Minor RD;0-tail | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 6.8 | 0 | 0 | 0 | 0 | 0 | yet to be started
Silt Clearance of Ghazi Kot Minor from RD: 0-tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.95 | 0 | 0 | 0 | 0 | 0 | yet to be started
Silt Clearance Daulat Minor and Gidar Minor RD; 0-tail in reaches & other allied structures | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 16.84 | 4482 | 13.11 | 12.2 | 4164.85 | 93% | Work in progress
Silt Clearance of Pirsabaq Disty and pirsabaq Minor from Rd:0-tail in reaches. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 11.75 | 4946.41 | 14.21 | 6.4 | 1947.46 | 45% | Work in progress
Silt Clearance of Chowky Disty, Chowki Minor 1 and 2 from RD: 00 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 8.23 | 0 | 0 | 0 | 0 | 0 | yet to be started
Silt Clearance of Gumbat Minor No.1 & Gumbat Branch from RD:0+0 to tail in reaches., | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 5.18 | 3096.09 | 6.46 | 2.74 | 1705.02 | 42% | Work in progress
Silt Clearance of Misri Banda from RD;0 to tal in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.73 | 2472.77 | 5.4 | 3.05 | 1691.93 | 56% | Work in progress
Silt Clearance of Ambar Branch from RD;0+0 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.35 | 0.35 | 7.88 | 0 | 0 | 0 | 0 | 0 | yet to be started
Silt Clearance of Jehangira Minor & Nandrak Minor from RD;0-tail in reaches and repair to allied structures | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 11.52 | 0 | 0 | 0 | 0 | 0 | yet to be started
Silt Clearance of Thanodher Minor & Manki Minor from RD;0-tail in reaches | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 12.42 | 0 | 0 | 0 | 0 | 0 | yet to be started
Silt Clearance of Yaqubi Minor, Sard China Minor and Naik Nam Minor from RD; 0-tail | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 10.46 | 0 | 0 | 0 | 0 | 0 | yet to be started
Silt Clearance of Dagi Disty & repair to allied structures Rd 0 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 3.23 | 0 | 0 | 0 | 0 | 0 | yet to be started
Silt Clerance of Gumbat Minor No 2 | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 4.57 | 0 | 0 | 0 | 0 | 0 | yet to be started
Silt Clearance and repair of Link Channel, Lahor Minor ,Zakaria Minor Sheik Dheri from RD; 0- to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 8.19 | 0 | 0 | 0 | 0 | 0 | yet to be started
Silt Clerance of Toru Minor | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 4.57 | 0 | 0 | 0 | 0 | 0 | yet to be started
Repair clearance of Sypon Rd 6200 & 8000 Pir Sabaq Disty | Swabi Irrigation Division-II Swabi | 0.1 | 0.1 | 0.06 | 0 | 0 | 0 | 0 | 0 | yet to be started
Repair clearance of Sypon Rd 200 Gidar Minor | Swabi Irrigation Division-II Swabi | 0.05 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | yet to be started
Clearance and dewatering of Syphons & repair to out lets Jaggan Nath Section. | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 0.15 | 0 | 0 | 0 | 0 | 0 | yet to be started
Desiltation / berm cutting/Jungle clearance of Disty No.04, RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 10.11 | 5964.26 | 5.64 | 1.69 | 1789.28 | 30% | yet to be started
Desiltation / berm cutting/Jungle clearance of Disty No.5 & its Minor and sub Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 26.31 | 7688.07 | 8.2 | 2.05 | 1992.02 | 25% | yet to be started
Desiltation / berm cutting/Jungle clearance of Dera Disty RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 16.7 | 5812.06 | 6.55 | 3.01 | 2673.55 | 46% | work in progress
Silt clearance/ jungle clearance of Muryali Minor RD. 00-15000 in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.64 | 4021.01 | 5.33 | 0 | 0 | 0% | yet to be started
Silt clearance/ jungle clearance including removal of debris of Lachra Minor/Makali Minor in reaches. | CRBC Irrigation Division DIKhan | 0.25 | 0.23 | 3.92 | 2402.7 | 11.3 | 0 | 0 | 0% | yet to be started
Desiltation / berm cutting/Jungle clearance of Mehmood Disty. RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.05 | 5737.19 | 4.42 | 1.33 | 1434.2 | 25% | yet to be started
Desiltation / berm cutting/Jungle clearance of Nawab Minor RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.3 | 0.27 | 7.62 | 2952 | 2.59 | 1.3 | 1476 | 50% | work in progress
Desiltation / berm cutting/Jungle clearance of Disty No.7, i/c Minors of Disty No.7 RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 30.53 | 7801.33 | 15.37 | 5.38 | 2730.47 | 35% | work in progress
Desiltation / berm cutting/Jungle clearance of Disty No. 8 & 8-A, RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.29 | 3999 | 3.95 | 2.17 | 2199.45 | 55% | work in progress
Desiltation / berm cutting/Jungle clearance of Disty No.9 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.71 |  |  | 0 |  | 0% | yet to be started
Desiltation / berm cutting/Jungle clearance of Disty No.10 & 10/A RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11 | 3950.22 | 3.19 | 0 |  | 0% | yet to be started
Desiltation / berm cutting/Jungle clearance of Disty No. 11 & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 9.1 | 5670.47 | 10.66 | 1.07 | 567.05 | 10% | yet to be started
Desiltation / berm cutting/Jungle clearance of Disty No. 11-A, & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 21.86 | 7695.14 | 5.93 | 0 |  | 0% | yet to be started
Desiltation / berm cutting/Jungle clearance of Disty No. 12 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.23 | 5762.51 | 4.11 | 0.8 | 1152.5 | 20% | work in progress
Desiltation /Jungle Clearance of Disty # 13 & its System RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.675 | 0.6075 | 21.655 | 4256.03 | 4.66 | 3 | 2723 | 64% | Work is in progress.
Shingling of CPR & Jungle Clearance of Disty # 14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.725 | 0.6525 | 21.616 | 4176.75 | 4.58 | 3.25 | 2923 | 70% | Work is in progress.
Shingling of CPR & Jungle Clearance of MD-14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.433 | 2145.01 | 2.43 | 1.3 | 1137 | 53% | Work is in progress.
Shingling of CPR & Jungle Clearance of Disty # 15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.7 | 0.63 | 21.494 |  | 4.5 | 0 |  | 0% | Work not yet started.
Shingling of CPR & Jungle Clearance of MD-15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.325 | 0.2925 | 5.8384 |  | 2.28 | 0 |  | 0% | Work not yet started.
Shingling of CPR & Jungle Clearance of Disty 16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 12.75 |  | 2.43 | 0 |  | 0% | Work not yet started.
Shingling of CPR & Jungle Clearance of Minor of Disty-16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.8445 |  | 2.45 | 0 |  | 0% | Work not yet started.
Desiltation / Jungle Clearance of Disty # 17 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 9.6951 |  | 2.13 | 0 |  | 0% | Work not yet started.
Shingling of CPR & Jungle Clearance of Disty # 18 its Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 18.009 |  | 4.26 | 0 |  | 0% | Work not yet started.
Shingling of CPR & Jungle Clearance of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.55 | 0.495 | 15.753 |  | 3.96 | 0 |  | 0% | Work not yet started.
Desiltation / Jungle Clearance of M-1 & M-2 of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.829 |  | 4 | 0 |  | 0% | Work not yet started.
Bazai Main Canal Head Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 |  | 21 | 21 |  | 100% | Completed
Wartair Disty | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 6 |  | 6 | 6 |  | 100% | Completed
Kharki Disty No. 02 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 3.3 |  | 3.3 | 3.3 |  | 100% | Completed
Additional Minor No. 03, 06 and Bazai Disty No. 01. | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | 16.8 |  | 16.8 | 3 |  | 100% | Completed
Bazai Main Canal, Syphon No. 4431, 5851, 12530, 13590, 14842, 18400, 47527 & 58853 | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | [5 empty] | 70% | Work in Progress
Bazai Disty No. 04, Bazai Minor No. 09, 11 and 12. | Malakand Irrigation Division Malakand | 0.27 | 0.26625 | 15.2 |  | 9 | te |  | 100% | Completed
Clearance of Syphon 79205, 93480 and 97962. | Malakand Irrigation Division Malakand | 0.1 | 0.975 |  |  |  | d |  | 20% | Work in Progress
Bazai Disty No. 03 and Bazai Minor No. 05. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | 20.5 |  | 20.5 | 7 |  | 100% | Completed
Bazai Main Canal Tail Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 |  | 0 | 0 |  | 0% | Not Yet start
KM-1 RD: 0-2976 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  |  | 0.9 | 0.9 |  | 100% | Completed
KM-1 RD: 0-1500, 22000-29000 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  |  | 2.6 | 2.6 |  | 100% | Completed
Silt & Shingle Clearance of P.C Minor from RD 0+000 To Tail in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.3395 | 12.881 | 1410.59 | 4.54 | 1.2 | 372.84 | 26.43% | Work in Progress
Clearance of Shingri Minor from RD 0-17250 in reaches. | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.309 | 530.92 | 2.499 | 1.22 | 259.19 | 48.82% | Work in Progress
Clearance of Meherdi Minor from RD 0-31000 in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2425 | 9.451 | 1809.24 | 6.858 | 3.05 | 804.63 | 44.47% | Work in Progress
Clearance of Kalu Branch from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.33 | 0.3218 | 11.563 | [5 empty] | Not yet started
Clearance of Hathian Minor from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.05 | 0.04875 | 2.35 | [5 empty] | Not yet started
Clearance of Jalala Disty from RD: 29000 to Tail in reaches | Malakand Irrigation Division Malakand | 0.37 | 0.3607 | 14.024 | 1476.73 | 5900 | 5400 | 1113.71 | 91.52% | Work in Progress
Clearance of Pirsaddo Disty, Ghano Minor and Qutab Gharh Minor from : H-Tail to Tail in reaches. | Malakand Irrigation Division Malakand | 0.35 | 0.412 | 1.88 | [5 empty] | Not yet started
Clearance of Shergarh Minor from Head to Rd:12+000 in reaches. | Malakand Irrigation Division Malakand | 0.15 | 0.146 | 7.752 | [5 empty] | Not yet started
Clearance of Shergarh Minor from Rd:12+000 tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 7.7752 | 1195.13 | 6000 | 5500 | 956.83 | 91.66% | Work in Progress
Clearance of Spokanda Disty from RD: 18000 to Tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 5.659 | [5 empty] | Not yet started
Removal of Heaps / Clearance of Bari Band Disty RD: 39+500-88+600 in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.33775 | 14.96 | 1435.76 | 8.21 | 4 | 950 | 48.72% | Work in Progress
Removal of Heaps / Clearance of Hero Shah Minor RD: 0 -38+000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 11.58 | 2446.93 | 11.58 | 6 | 1100 | 51.81% | Work in Progress
Removal of Heaps / Clearance of Kalu Shah Disty and Dundian Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.1 | 0.098 | 7.69 | 785.8 | 5 | 5 | 785.8 | 100% | Completed
Removal of Heaps / Clearance of Sarwala Disty and Lund Khwar Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 18.29 | 3172.99 | 10.06 | 6 | 1800 | 59.64% | Work in Progress
Removal of Heaps / Clearance of Said Abad Disty and Pir Abad Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 20.42 | 3113.1 | 7.31 | 5 | 1800 | 68.4% | Work in Progress
Removal of Heaps / Clearance of Katlang Disty from RD: 0-40+000 in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 12.19 | 1910.43 | 7.61 | 5 | 1200 | 65.7% | Work in Progress
Removal of Heaps / Clearance of Shamozai Disty/ Syphon and Likpani Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.392 | 17.67 | 2730.62 | 13.01 | 5 | 1200 | 38.43% | Work in Progress
Removal of Heaps / Clearance of Dheri Minor and Tail Minor Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.15 | 0.147 | 7.01 | 1211.68 | 6 | 5 | 1050 | 83.33% | Work in Progress
Shamizai Irrigation Canal | Swat Irrigation Division-II Matta | 1 | 0.779 | 20.73 | 5150 | 19.5 | 17.63 | 4657 | 90% | Work is in progress
Barwai Irrigation Canal | Swat Irrigation Division-II Matta | 0.3 | 0.2805 | 11.22 | 1300 | 6.1 | 5.55 | 1183 | 91% | Work is in progress
Nipki Khel Irrigation Scheme | Swat Irrigation Division -I | 2.2 | 1.76 | 38.87 | 10172.62 | 38.87 | 15.7622 | 4654.43 | 40.55% | Work in Progress
Silt clearance from RD:0+00 to RD:8+000 in reaches of Ghazai Khani Flow Irrigation Scheme | Swat Irrigation Division -I | 0.24 | 0.213 | 2.438 | 1339.39 | 2.44 | 1.52 | 650 | 48.53% | Work in Progress
"Silt clearance from RD:0+00 to RD:12+000 in reaches of Karshalizara Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.1199 | 3.657 | 613 | 3.66 | 1.8 | 400 | 65.25% | Work in Progress
"Silt clearance from RD:0+00 to RD:20+000 in reaches of Charorai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.15 | 0.135 | 6.096 | 766.25 | 6.1 | 3.54 | 670 | 87.44% | Work in Progress
"Silt clearance from RD:0+00 to RD:12+000 in reaches of Kuriya Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.25 | 0.225 | 3.657 | 1397.44 | 3.66 | 2.36 | 700 | 50.09% | Work in Progress
"Silt clearance from RD:0+00 to RD:9+000 in reaches of Elai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 2.743 | 613 | 2.74 | 1.94 | 300 | 48.94% | Work in Progress
"Silt clearance from RD:0+00 to RD:60+000 in reaches of Budal Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 18.287 | 672.53 | 9.14 | 5.23 | 320 | 47.58% | Work in Progress
"Silt clearance from RD:0+00 to RD:16+000 in reaches of Singarai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 4.267 | 669.7 | 4.27 | 2.56 | 280 | 41.81% | Work in Progress
"Silt clearance from RD:0+00 to RD:26+000 in reaches of Bajkata Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.08 | 0.072 | 7.924 | 408.66 | 7.92 | 4.21 | 250 | 61.18% | Work in Progress
Silt clearance from RD:0+00 to RD:34+000 in reaches of Gagra Flow Irrigation Scheme | Swat Irrigation Division -I | 0.5 | 0.4 | 10.363 | 2797 | 9.75 | 4.52 | 1600 | 57.2% | Work in Progress
Silt clearance of Doaba Canal RD. 4+600-9+100 in Reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.242 | 0.1548 | 14.7828 | 1128.21 | 0.58 | 0.522 | 902.568 | 90% | In progress
Silt clearance of Doaba Canal RD. 9+200-13+000 in Reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.343 | 0.22 | 14.7828 | 1595.38 | 0.548 | 0.465 | 1196.535 | 85% | In progress
Silt clearance of Doaba Canal RD. 13+200-17+000 in Reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.341 | 0.218 | 14.7828 | 1586.32 | 0.6 | 0.54 | 1269.056 | 90% | In progress
Silt Clearance of Doaba Canal RD.17+300-21+200 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.338 | 0.22 | 14.7828 | 1572.55 | 0.672 | 0.604 | 1289.491 | 89% | In progress
Silt Clearance of Doaba Canal RD.21+250-24+475 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.312 | 0.2 | 14.7828 | 1454.79 | 0.74 | 0.629 | 1091.0925 | 85% | In progress
Silt clearance of New Michni Branch RD. 0+000-4+100 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.3439 | 0.22 | 11.027 | 741.2 | 0.685 | 0.65 | 652.256 | 95% | In progress
Silt clearance of New Michni Branch RD. 4+200-8+300 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.332 | 0.212 | 11.027 | 715.46 | 0.731 | 0.69 | 643.914 | 95% | In progress
Silt clearance of New Michni Branch RD 8+500-12+000 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.32 | 0.2 | 11.027 | 689.67 | 0.609 | 0.548 | 551.736 | 90% | In progress
Silt Clearance of Dalazak Minor RD. 0+000-4+000 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.1244 | 0.796 | 3.96 | 451.34 | 0.67 | 0.569 | 333.99 | 85% | In progress
Silt Clearance of Subhan Khwar Disty RD.0+000-4+500 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.315 | 0.201 | 4.81 | 680.17 | 0.84 | 0.714 | 442.11 | 85% | In progress
Silt clearance of Ichri Branch RD. 0-4366 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.15 | 0.096 | 1.33 | 576.89 | 0.67 | 0.536 | 346.134 | 80% | In progress
Silt Clearance of Shabqadar Branch RD.0+000-15+000 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.38 | 0.24 | 4.5 | 819.21 | 1.645 | 1.316 | 573.447 | 80% | In progress
Silt Clearance of Iceland Canal RD..0+00-Tail in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.35 | 0.224 | 8.83 | 2045.2 | 2.103 | 1.0515 | 1022.6 | 50% | In progress
Silt Clearance of Samkana Branch RD.0+000-30+000 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.3 | 0.192 | 9.14 | 2041.66 | 2.103 | 1.261 | 1224.96 | 60% | In progress
Swabi Irrigation Division-I Swabi
Shahbaz Garhi Sub Division
Clearance from the bed of Jamal Garhi Disty from 00-tail in reaches. | Swabi Irrigation Division-I Swabi | 300000 | 111000 | 55273 | 1692.37 | 4.7 | 4 |  |  | In-Progress
Silt Clearance from the bed of Buxali Disty & Kot Minor from 00-tail in reaches | Swabi Irrigation Division-I Swabi | 650000 | 357500 | 69940 | 4715.26 | 9.42 | 7 |  |  | In-Progress
Removal of debris and heaps from Machai Branch RD 105+000 to 142+000 in reaches | Swabi Irrigation Division-I Swabi | 350000 | 129500 | 37000 | 4521.89 | 0.48 | 0.34 |  |  | In-Progress
Removal of debris and heaps from Machai Branch RD 142+000 to 186+000 in reaches | Swabi Irrigation Division-I Swabi | 350000 | 129500 | 44000 | 4513.02 | 0.35 | 0.33 |  |  | In-Progress
Silt Clearance from the bed of Chura Minor , Sawal Dher Minor & Mala Minor from RD: 00-tail in reaches. | Swabi Irrigation Division-I Swabi | 300000 | 111000 | 45971 | 1698.88 | 7 | 5 |  |  | In-Progress
Silt clearance from the bed Shahbaz Garhi Disty and its sub System from RD:00-tail in reaches | Swabi Irrigation Division-I Swabi | 800000 | 440000 | 60000 | 4522.69 | 14.85 | 12 |  |  | In-Progress
Silt Clearance from the bed of Ismalia Disty and its sub system from 00-tail in reaches | Swabi Irrigation Division-I Swabi | 900000 | 495000 | 74850 | 6469.09 | 13.26 | 12 |  |  | In-Progress
Silt Clearance from the bed of Adina Minor and adina Minor Branch from Head to tail in reaches | Swabi Irrigation Division-I Swabi | 350000 | 192500 | 25840 | 1980.17 | 5.59 | 5 |  |  | In-Progress

## 03-02-2023
S# | Name of Canal | Name of Division | Estimated Cost(RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Total Quantity of Silt to be removed (m3) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Total Quantity of Silt removed till date (m3) | Progress Till date in % | Remarks
1 | Silt clearance from RD:0+00 to RD:8+000 in reaches of Ghazai Khani Flow Irrigation Scheme | Swat Irrigation Division -I | 0.24 | 0.213 | 2.438 | 1339.39 | 2.44 | 1.94 | 700 | 52.26% | Work in Progress
2 | "Silt clearance from RD:0+00 to RD:12+000 in reaches of Karshalizara Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.1199 | 3.657 | 613 | 3.66 | 2.1 | 450 | 73.41% | Work in Progress
3 | "Silt clearance from RD:0+00 to RD:20+000 in reaches of Charorai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.15 | 0.135 | 6.096 | 766.25 | 6.1 | 4.1 | 675 | 88.09% | Work in Progress
4 | "Silt clearance from RD:0+00 to RD:12+000 in reaches of Kuriya Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.25 | 0.225 | 3.657 | 1397.44 | 3.66 | 2.4 | 720 | 51.52% | Work in Progress
5 | "Silt clearance from RD:0+00 to RD:9+000 in reaches of Elai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 2.743 | 613 | 2.74 | 2.1 | 300 | 48.94% | Work in Progress
6 | "Silt clearance from RD:0+00 to RD:60+000 in reaches of Budal Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 18.287 | 672.53 | 9.14 | 5.45 | 330 | 49.07% | Work in Progress
7 | "Silt clearance from RD:0+00 to RD:16+000 in reaches of Singarai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 4.267 | 669.7 | 4.27 | 2.62 | 320 | 47.78% | Work in Progress
8 | "Silt clearance from RD:0+00 to RD:26+000 in reaches of Bajkata Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.08 | 0.072 | 7.924 | 408.66 | 7.92 | 4.32 | 260 | 63.62% | Work in Progress
9 | Silt clearance from RD:0+00 to RD:34+000 in reaches of Gagra Flow Irrigation Scheme | Swat Irrigation Division -I | 0.5 | 0.4 | 10.363 | 2797 | 9.75 | 4.94 | 1650 | 58.99% | Work in Progress
10 | Silt clearance of Doaba Canal RD. 4+600-9+100 in Reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.242 | 0.1548 | 14.7828 | 1128.21 | 0.58 | 0.522 | 902.568 | 90% | In progress
11 | Silt clearance of Doaba Canal RD. 9+200-13+000 in Reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.343 | 0.22 | 14.7828 | 1595.38 | 0.548 | 0.465 | 1196.535 | 85% | In progress
12 | Silt clearance of Doaba Canal RD. 13+200-17+000 in Reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.341 | 0.218 | 14.7828 | 1586.32 | 0.6 | 0.54 | 1269.056 | 90% | In progress
13 | Silt Clearance of Doaba Canal RD.17+300-21+200 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.338 | 0.22 | 14.7828 | 1572.55 | 0.672 | 0.604 | 1289.491 | 89% | In progress
14 | Silt Clearance of Doaba Canal RD.21+250-24+475 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.312 | 0.2 | 14.7828 | 1454.79 | 0.74 | 0.629 | 1091.0925 | 85% | In progress
15 | Silt clearance of New Michni Branch RD. 0+000-4+100 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.3439 | 0.22 | 11.027 | 741.2 | 0.685 | 0.65 | 652.256 | 95% | In progress
16 | Silt clearance of New Michni Branch RD. 4+200-8+300 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.332 | 0.212 | 11.027 | 715.46 | 0.731 | 0.69 | 643.914 | 95% | In progress
17 | Silt clearance of New Michni Branch RD 8+500-12+000 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.32 | 0.2 | 11.027 | 689.67 | 0.609 | 0.548 | 551.736 | 90% | In progress
18 | Silt Clearance of Dalazak Minor RD. 0+000-4+000 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.1244 | 0.796 | 3.96 | 451.34 | 0.67 | 0.569 | 333.99 | 85% | In progress
19 | Silt Clearance of Subhan Khwar Disty RD.0+000-4+500 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.315 | 0.201 | 4.81 | 680.17 | 0.84 | 0.714 | 442.11 | 85% | In progress
20 | Silt clearance of Ichri Branch RD. 0-4366 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.15 | 0.096 | 1.33 | 576.89 | 0.67 | 0.536 | 346.134 | 80% | In progress
21 | Silt Clearance of Shabqadar Branch RD.0+000-15+000 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.38 | 0.24 | 4.5 | 819.21 | 1.645 | 1.316 | 573.447 | 80% | In progress
22 | Silt Clearance of Iceland Canal RD..0+00-Tail in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.35 | 0.224 | 8.83 | 2045.2 | 2.103 | 1.0515 | 1022.6 | 50% | In progress
23 | Silt Clearance of Samkana Branch RD.0+000-30+000 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.3 | 0.192 | 9.14 | 2041.66 | 2.103 | 1.261 | 1224.96 | 60% | In progress
HARIPUR IRRIGATION DIVISION HARIPUR
24 | Silt clearance of Sarai Saleh NPC Rd 0-10000 in reaches | Haripur Irrigation Division Haripur | 0.35 | 0.283 | 15.85 | 1271 | 3.04 | 2.75 | 1108.9 | 88% | In progress
25 | Silt clearance of Sarai Saleh NPC Rd 10000-17000 i/c Minor No.1 in reaches | Haripur Irrigation Division Haripur | 0.3 | 0.24 | 15.85 | 1131.96 | 2.13 | 1.15 | 565 | 36% | In progress
26 | Silt clearance of Sarai Saleh NPC Rd 17000-30000 i/c Minor No.2 in reaches | Haripur Irrigation Division Haripur | 0.35 | 0.28 | 15.85 | 1347 | 3.96 | 1.85 | 705.65 | 40% | In progress
27 | Clearance of Daur Main Canal Rd 0-tail | Haripur Irrigation Division Haripur | 0.15 | 0.1216 | 0.838 | 555.2 | 0.838 | 0.838 | 555.2 | 100% | Work completed
28 | Silt Clearance of Disty No.02 RD 0-20000 in reaches. | Haripur Irrigation Division Haripur | 0.25 | 0.2 | 6.62 | 1287.6 | 6.09 | 5.79 | 1210.58 | 95% | In progress
29 | Silt Clearance of Main KRBC RD 11000-42000 in reaches | Haripur Irrigation Division Haripur | 0.25 | 0.225 | 12.8 | 1287.6 | 9.45 | 7.5 | 1150 | 88% | In progress
30 | Silt Clearance Disty No.04 RD 0-24000 in reaches. | Haripur Irrigation Division Haripur | 0.3 | 0.24 | 7.31 | 1545.12 | 7.31 | 5.45 | 1238.9 | 73% | In progress
31 | Silt Clearance of Disty No.03 i/c Ziarat Minor and Bandi Minor in reaches. | Haripur Irrigation Division Haripur | 0.3 | 0.24 | 10.67 | 1545.12 | 10.67 | 3.05 | 570.75 | 35% | In progress
32 | Silt Clearance of Disty No.1 i/c Balartop & Kamalpur Minors in reaches. | haripur Irrigation Division Haripur | 0.3 | 0.24 | 10.36 | 1545.12 | 10.36 | 6.07 | 905.88 | 70% | In progress
33 | Silt Clearance of KLBC Rd 0-26000 in reaches | haripur Irrigation Division Haripur | 0.3 | 0.24 | 7.92 | 1545.12 | 7.92 | 0 | 0 | 0 | not yet started due to decisiion made in meeting with XEN WAPDA, PMO and CDA Islambad authorities and work will be started from 15th February 2023
34 | Silt clearance of Sarai Saleh NPC Rd 30000-40000 i/c Minor No. 3 in reaches | HAripur Irrigation Division Haripur | 0.25 | 0.2 | 15.85 | 946 | 3.04 | 0.3 | 105.88 | 15% | In progress
35 | Clearance of Main Rangila Irrigation system i/c Rangila Tank | Haripur Irrigation Division Haripur | 0.2 | 0.173 | 2.21 | 559 | 2.21 | 0 | 0 | 0 | Not yet started
36 | Silt Clearance of Chak Muneem Minor. | Haripur Irrigation Division Haripur | 0.2 | 0.16 | 7.01 | 1030.8 | 7.01 | 0 | 0 | 0 | Not yet started
37 | Swabi Irrigation Division-I Swabi
38 | Shahbaz Garhi Sub Division
39 | Clearance from the bed of Jamal Garhi Disty from 00-tail in reaches. | Swabi Irrigation Division-I Swabi | 0.3 | 0.11 | 16.81 | 1692.37 | 4.7 | 4 | 1429.7 | 84.48% | In-Progress
40 | Silt Clearance from the bed of Buxali Disty & Kot Minor from 00-tail in reaches | Swabi Irrigation Division-I Swabi | 0.65 | 0.36 | 21.34 | 4715.26 | 9.42 | 7 | 3873.2 | 82.14% | In-Progress
41 | Removal of debris and heaps from Machai Branch RD 105+000 to 142+000 in reaches | Swabi Irrigation Division-I Swabi | 0.35 | 0.13 | 247.58 | 4521.89 | 0.48 | 0.34 | 2946.9 | 65.17% | In-Progress
42 | Removal of debris and heaps from Machai Branch RD 142+000 to 186+000 in reaches | Swabi Irrigation Division-I Swabi | 0.35 | 0.13 | 247.58 | 4513.02 | 0.35 | 0.33 | 3595.54 | 79.67% | In-Progress
43 | Silt Clearance from the bed of Chura Minor , Sawal Dher Minor & Mala Minor from RD: 00-tail in reaches. | Swabi Irrigation Division-I Swabi | 0.3 | 0.11 | 14.38 | 1698.88 | 7 | 5 | 1511.59 | 88.98% | In-Progress
44 | Silt clearance from the bed Shahbaz Garhi Disty and its sub System from RD:00-tail in reaches | Swabi Irrigation Division-I Swabi | 0.8 | 0.44 | 18.29 | 4522.69 | 14.85 | 12 | 3194.76 | 70.64% | In-Progress
45 | Silt Clearance from the bed of Ismalia Disty and its sub system from 00-tail in reaches | Swabi Irrigation Division-I Swabi | 0.9 | 0.5 | 18.29 | 6469.09 | 13.26 | 12 | 5003.92 | 77.35% | In-Progress
46 | Silt Clearance from the bed of Adina Minor and adina Minor Branch from Head to tail in reaches | Swabi Irrigation Division-I Swabi | 0.35 | 0.19 | 7.89 | 1980.17 | 5.59 | 5 | 1563.08 | 78.94% | In-Progress
47
48 | Gohati Irrigation Sub Division Gohati | Swabi Irr:Divn-1 Swabi
49 | Silt Clearance of Machai Branch at RD: 186000-252000 in reaches | Swabi Irr:Divn-1 Swabi | 1 | 0.45 | 24.764 | 9344.56 | 3.2 | 2.74 | 6977.84 | 75% | In progress
50 | Silt Clearance of Kalu Khan Disty and its sub system from RD: 00-tail in reaches | Swabi Irr:Divn-1 Swabi | 1 | 0.45 | 53.87 | 17414 | 27.54 | 15.85 | 9333.74 | 54% | In progress
51 | Silt Clearance of Nawan Killi Minor ,Sarbandi Minor, Shagai Minor RD:00- tail in reaches | Swabi Irr:Divn-1 Swabi | 0.3 | 0.155 | 4.69 2.92 5.18 12.79 | 2288.51 | 8.8 | 3.99 | 1274.97 | 56% | In progress
52 | Silt Clearance of , Naranji Disty & Naranji Minor No.1 & 2 RD: 00-tail in reaches | Swabi Irr:Divn-1 Swabi | 0.3 | 0.15 | 10.3963 3.04 1.58 15.01 | 2465 | 9.14 | 3.35 | 1397.07 | 37% | In progress
53 | Silt Clearance of Old Indus branch & Zaida Minor RD:0-Tail in reaches | Swabi Irr:Divn-1 Swabi | 0.4 | 0.2 | 9.84 2.97 12.81 | 4193 | 8.84 | 4.88 | 2950 | 21% | In progress
54 | Silt Clearance of Pehur branch and its sub system RD:0-Tail in reaches | Swabi Irr:Divn-1 Swabi | 1 | 0.55 | 30.69 | 8240 | 15.85 | 10.36 | 5044.3 | 19% | In progress
55 | Swabi Irrigation Division-II Swabi
56 | Clearance of Topi Lift Irrigation Channels RD;00-Tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 4.88 | 1161.77 | 4.87 | 2.44 | 615.96 | 50% | Work in progress
57 | Clearance of Topi & Zarobi Minors from RD;00 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | Topi =4.24 Zarobi =4.27 | 1159.72 | 3.05 | 2.13 | 701.9 | 70% | Work in progress
58 | Clearance/Repair of Badri Lift Irrigation Scheme | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 0.34 | 607.12 | 0.33 | 0.33 | 607.12 | 100% | Competed
59 | Clearance of Kotha Disty; from RD;00 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.24 | 0.24 | 17.53 | 1389.07 | 1.89 | 1.89 | 1389.07 | 100% | Competed
60 | Clearance of Pehur main Canal from RD;46000 to RD;54000 | Swabi Irrigation Division-II Swabi | 0.18 | 0.18 | 51.4 | 1042.24 | 0.53 | 0.53 | 1042.24 | 100% | Competed
61 | Clearance of Pehur Main Canal from RD;54500 to RD;66000 | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 51.4 | 1130.88 | 0.55 | 0.27 | 565.44 | 50% | Work in progress
62 | Clearance of Pehur Main Canal from RD;66000 to RD;85000 | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.92 | 0.7 | 0.4 | 793.79 | 57% | Work in progress
63 | Clearance of Pehur Main Canal RD;85000 to RD;93000 | Swabi Irrigation Division-II Swabi | 0.16 | 0.16 | 51.4 | 976.63 | 0.63 | 0.15 | 236.76 | 24% | Work in progress
64 | Clearance of Pehur Main Canal from RD;93500 to RD;98000 | Swabi Irrigation Division-II Swabi | 0.17 | 0.17 | 51.4 | 1033.5 | 0.32 | 0.16 | 516.75 | 50% | Work in progress
65 | Clearance of Pehur Main Canal from RD;98500 to RD;113000 | Swabi Irrigation Division-II Swabi | 0.18 | 0.18 | 51.4 | 1094.71 | 0.61 | 0.46 | 792.24 | 75% | Work in progress
66 | Clearance of Kaddi, Zaida, Zakarriya & Sheikhdheri Minors from RD;00 to Tail | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | Kaddi= 5.79 Zaida= 3.81 Zakary=3.43 S/Dher=2.95 | 1292.45 | 0.39 | 0.2 | 702.12 | 50% | Work in progress
67 | Clearance of Pehur Main Canal System from RD;113000 to RD;117000 | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 51.4 | 883 | 0.4 | 0.3 | 685.62 | 77% | Work in progress
68 | Clearance of Pehur Main Canal System from RD;117000 to RD;122000 | Swabi Irrigation Division-II Swabi | 0.12 | 0.12 | 51.4 | 729.53 | 0.22 | 0.11 | 364.76 | 50% | Work in progress
69 | Clearance of Pehur main Canal System from RD;122000 to RD;133000 | Swabi Irrigation Division-II Swabi | 0.13 | 0.13 | 51.4 | 790.91 | 0.4 | 0.34 | 649.45 | 85% | Work in progress
70 | Clearance of flood deposition from the bed of PMC from RD;13300 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1519.85 | 0.46 | 0.23 | 759.92 | 50% | Work in progress
71 | Clearance of PMC System from RD;133000 to 140000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 51.4 | 1738.06 | 0.85 | 0.61 | 1214.72 | 71% | Work in progress
72 | Clearance of PMC Systems from RD;145000 to RD;150000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.23 | 0.23 | 51.4 | 1398.26 | 0.43 | 0.21 | 699.13 | 50% | Work in progress
73 | Clearance of PMC System from RD;150500 to RD;162000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1519.85 | 0.46 | 0.23 | 759.92 | 50% | Work in progress
74 | Clearance of PMC System from RD;162100 to Tail & other allied Branches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.85 | 3.23 | 2.29 | 1076.33 | 71% | Work in progress
75 | Clearance of Thanodher Disty: & Bazar Minor from RD;00 to Tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | Thano=6.00 Bazar=7.47 | 1157.95 | 0.35 | 0.18 | 679.53 | 50% | Work in progress
76 | Clearance of flood deposition and silt clearance of ¦Indus Branch RD:74500 Tail in reaches. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 18.54 | 4478 | 11.89 | 8.69 | 3001.26 | 73% | Work in progress
77 | Silt Clearance of Dagi Minor from RD:0- 37000 in reaches i/c repair to out lets & other allied structures. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 11.28 | 4482 | 9.15 | 4.05 | 1982.19 | 44% | Work in progress
78 | Silt Clearance of Dandoka Minor from RD:0-Tail in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.03 | 0 | 0 | 0 | 0 |  | contractor deployed
79 | Silt Clearance of Sudher Minor RD:0 - tail in reaches & other allied structures | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 2.29 | 0 | 0 | 0 | 0 |  | contractor deployed
80 | Silt Clearance of Yar Hussain Minor RD;0-tail | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 6.8 | 2803.37 | 5.79 | 0.91 | 467.23 | 16% | Work in progress
81 | Silt Clearance of Ghazi Kot Minor from RD: 0-tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.95 | 0 | 0 | 0 | 0 |  | contractor deployed
82 | Silt Clearance Daulat Minor and Gidar Minor RD; 0-tail in reaches & other allied structures | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 16.84 | 4482 | 13.11 | 12.65 | 4219.21 | 97% | Work in progress
83 | Silt Clearance of Pirsabaq Disty and pirsabaq Minor from Rd:0-tail in reaches. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 11.75 | 4946.41 | 14.21 | 6.4 | 1947.46 | 45% | Work in progress
84 | Silt Clearance of Chowky Disty, Chowki Minor 1 and 2 from RD: 00 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 8.23 | 0 | 7.01 | 0 | 0 |  | contractor deployed
85 | Silt Clearance of Gumbat Minor No.1 & Gumbat Branch from RD:0+0 to tail in reaches., | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 5.18 | 3096.09 | 6.46 | 2.74 | 1705.02 | 42% | Work in progress
86 | Silt Clearance of Misri Banda from RD;0 to tal in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.73 | 2472.77 | 5.4 | 3.05 | 1691.93 | 56% | Work in progress
87 | Silt Clearance of Ambar Branch from RD;0+0 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.35 | 0.35 | 7.88 | 0 | 0 | 0 | 0 |  | contractor deployed
88 | Silt Clearance of Jehangira Minor & Nandrak Minor from RD;0-tail in reaches and repair to allied structures | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 11.52 | 0 | 0 | 0 | 0 |  | contractor deployed
89 | Silt Clearance of Thanodher Minor & Manki Minor from RD;0-tail in reaches | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 12.42 | 0 | 0 | 0 | 0 |  | contractor deployed
90 | Silt Clearance of Yaqubi Minor, Sard China Minor and Naik Nam Minor from RD; 0-tail | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 10.46 | 0 | 0 | 0 | 0 |  | contractor deployed
91 | Silt Clearance of Dagi Disty & repair to allied structures Rd 0 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 3.23 | 0 | 0 | 0 | 0 |  | contractor deployed
92 | Silt Clerance of Gumbat Minor No 2 | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 4.57 | 0 | 0 | 0 | 0 |  | contractor deployed
93 | Silt Clearance and repair of Link Channel, Lahor Minor ,Zakaria Minor Sheik Dheri from RD; 0- to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 8.19 | 0 | 0 | 0 | 0 |  | contractor deployed
94 | Silt Clerance of Toru Minor | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 4.57 | 0 | 0 | 0 | 0 |  | contractor deployed
95 | Repair clearance of Sypon Rd 6200 & 8000 Pir Sabaq Disty | Swabi Irrigation Division-II Swabi | 0.1 | 0.1 | 0.06 | 0 | 0 | 0 | 0 |  | contractor deployed
96 | Repair clearance of Sypon Rd 200 Gidar Minor | Swabi Irrigation Division-II Swabi | 0.05 | 0.05 | 0.05 | 0 | 0 | 0 | 0 |  | contractor deployed
97 | Clearance and dewatering of Syphons & repair to out lets Jaggan Nath Section. | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 0.15 | 0 | 0 | 0 | 0 |  | contractor deployed
98 | Silt clearance/removal of heaps of Disty No. 9 RD; 41000 to 85500 | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 13.41 | 599.93 | 1 | 0.95 | 569.93 | 95% | In progress
99 | Silt clearance of Power House Minor RD 0 to tail | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 1.28 | 599.9 | 1.28 | 0.83 | 389 | 65% | The canal passing through thickly populated area of Mardan City and the adjacenet locals are throwing garbages into the canal, therefore, it is expedient to clear the remaining portion exact at the end of closure period.
100 | Silt clearance of conduit covering portion of 2/9 Hoti Minor RD 4200 to 5000, 5800 to 7000 & 7200 to 7500 | Mardan Irrigation Division Mardan | 0.7 | 0.4546 | 0.7 | 745.53 | 0.7 | 0.48 | 511.22 | 69% | ..do…
101 | Silt clearance of 2/9 Hoti Minor RD 0 to 4200, 5000 to 5800 & 7500 to 19000 | Mardan Irrigation Division Mardan | 0.8 | 0.5195 | 5.94 | 921.08 | 2.43 | 1.47 | 557.2 | 60% | ..do…
102 | Silt clearance /removal of heaps of kalpani disty RD 0-51000 in reaches and clearance of syphones RD 10500 and 15000 | Mardan Irrigation Division Mardan | 0.7 | 0.4544 | 15.6 | 4463.54 | 5.07 | 4.8 | 4225.84 | 95% | In progress
103 | Silt clearance /removal of heaps of 1/kalpani Kodinaka Minor RD 0-27000 in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 8.22 | 599.94 | 1.82 | 1.26 | 415.34 | 69% | The canal passing through thickly populated area of Mardan City and the adjacenet locals are throwing garbages into the canal, therefore, it is expedient to clear the remaining portion exact at the end of closure period.
104 | Silt clearance /removal of heaps of 2/kalpani Taus Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 6.4 | 2801.12 | 5.5 | 5.26 | 2678.89 | 96% | In progress
105 | Silt clearance of 3/9 Toru Minor RD 0 to 15800 | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 4.81 | 2801.12 | 4.81 | 4.55 | 2649.71 | 95% | In progress
106 | Silt clearance of branch 2/kalpani Muhib Banda Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.175 | 0.1308 | 2.89 | 1633.98 | 2 | 1.9 | 1552.28 | 95% | In progress
107 | Silt Clearance of Maho Dheri Minor RD: 4000 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.1493 | 4.57 | 1138.2 | 3.35 | 3.2 | 1087.24 | 96% | In progress
108 | Silt Clearance of Rashakai Minor from RD: 7000 to 31000 in reaches | Mardan Irrigation Division Mardan | 0.6 | 0.3894 | 9.45 | 2972.29 | 7.31 | 7 | 2846.24 | 96% | In progress
109 | Silt Clearance of Nowshera Minor RD:0 - tail in reachers | Mardan Irrigation Division Mardan | 0.35 | 0.2613 | 5.18 | 2059.85 | 3.2 | 3.06 | 1969.73 | 96% | In progress
110 | Silt Clearance of Turlandi Minor Head to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 5.27 | 2134.4 | 4.71 | 4.71 | 2134.4 | 100% | Completed
111 | Silt Clearance of Khan Mahi Branch from RD: 0 to 3000 and RD: 8000 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 13.41 | 2344.08 | 5.48 | 5.2 | 2224.31 | 95% | In progress
112 | Silt Clearance of Bara Banda Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 3.04 | 1703.02 | 3.04 | 2.88 | 1613.39 | 95% | In progress
113 | Removal of heaps of Disty No. 8 RD: 52000 to 68000 in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 9.45 | 1860.72 | 1.43 | 1.43 | 1860.72 | 100% | Completed
114 | Silt Clearance/removal of heaps of Disty No. 7 at RD: 4000 to 14000 in reaches | Mardan Irrigation Division Mardan | 0.15 | 0.1133 | 4.26 | 1400.56 | 3.04 | 3.04 | 1400.56 | 100% | Completed
115 | Silt Clearance/removal of heaps of Sheikh yousaf Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 5.48 | 239.97 | 2.13 | 2.05 | 230.96 | 96% | In progress
116 | Silt Clearance/removal of heaps of 1/9 Guide Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 7 | 479.94 | 2.74 | 2.62 | 458.92 | 96% | In progress
117 | Silt Clearance/removal of heaps of Koragh Branch RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 14.93 | 479.94 | 2.23 | 2.23 | 479.94 | 100% | Completed
118 | Removal of heaps of Disty No.8 RD: 0 to 38000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 11.58 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
119 | Removal of heaps of Disty No.9 RD: 0 to 41000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 12.5 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
120 | Shamizai Irrigation Canal | Swat Irrigation Division-II Matta | 1 | 0.779 | 20.73 | 5150 | 19.5 | 18.04 | 4765 | 93% | Work is in progress
121 | Barwai Irrigation Canal | Swat Irrigation Division-II Matta | 0.3 | 0.2805 | 11.22 | 1300 | 6.1 | 5.55 | 1183 | 91% | Work is in progress
122 | Nipki Khel Irrigation Scheme | Swat Irrigation Division -I | 2.2 | 1.76 | 38.87 | 10172.62 | 38.87 | 15.9451 | 4691 | 41.02% | Work in Progress
123 | Desiltation / berm cutting/Jungle clearance of Disty No.04, RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 10.11 | 5964.26 | 5.64 | 1.97 | 2087.49 | 35% | yet to be started
124 | Desiltation / berm cutting/Jungle clearance of Disty No.5 & its Minor and sub Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 26.31 | 7688.07 | 8.2 | 2.3 | 2152.66 | 28% | yet to be started
125 | Desiltation / berm cutting/Jungle clearance of Dera Disty RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 16.7 | 5812.06 | 6.55 | 3.01 | 2673.55 | 46% | work in progress
126 | Silt clearance/ jungle clearance of Muryali Minor RD. 00-15000 in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.64 | 4021.01 | 5.33 | 0 | 0 | 0% | yet to be started
127 | Silt clearance/ jungle clearance including removal of debris of Lachra Minor/Makali Minor in reaches. | CRBC Irrigation Division DIKhan | 0.25 | 0.23 | 3.92 | 2402.7 | 11.3 | 0 | 0 | 0% | yet to be started
128 | Desiltation / berm cutting/Jungle clearance of Mehmood Disty. RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.05 | 5737.19 | 4.42 | 1.77 | 2294.88 | 40% | yet to be started
129 | Desiltation / berm cutting/Jungle clearance of Nawab Minor RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.3 | 0.27 | 7.62 | 2952 | 2.59 | 1.3 | 1476 | 50% | work in progress
130 | Desiltation / berm cutting/Jungle clearance of Disty No.7, i/c Minors of Disty No.7 RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 30.53 | 7801.33 | 15.37 | 5.38 | 2730.47 | 35% | work in progress
131 | Desiltation / berm cutting/Jungle clearance of Disty No. 8 & 8-A, RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.29 | 3999 | 3.95 | 3.16 | 3199.2 | 80% | work in progress
132 | Desiltation / berm cutting/Jungle clearance of Disty No.9 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.71 | 3560.86 | 2.9 | 0 |  | 0% | yet to be started
133 | Desiltation / berm cutting/Jungle clearance of Disty No.10 & 10/A RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11 | 3950.22 | 3.19 | 0 |  | 0% | yet to be started
134 | Desiltation / berm cutting/Jungle clearance of Disty No. 11 & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 9.1 | 5670.47 | 10.66 | 2.66 | 1417.62 | 25% | yet to be started
135 | Desiltation / berm cutting/Jungle clearance of Disty No. 11-A, & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 21.86 | 7695.14 | 5.93 | 0 |  | 0% | yet to be started
136 | Desiltation / berm cutting/Jungle clearance of Disty No. 12 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.23 | 5762.51 | 4.11 | 1.02 | 2881.25 | 50% | work in progress
137 | Desiltation /Jungle Clearance of Disty # 13 & its System RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.675 | 0.6075 | 21.655 | 4256.03 | 4.66 | 3 | 2723 | 64% | Work is in progress.
138 | Shingling of CPR & Jungle Clearance of Disty # 14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.725 | 0.6525 | 21.616 | 4176.75 | 4.58 | 3.25 | 2923 | 70% | Work is in progress.
139 | Shingling of CPR & Jungle Clearance of MD-14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.433 | 2145.01 | 2.43 | 1.57 | 1394 | 65% | Work is in progress.
140 | Shingling of CPR & Jungle Clearance of Disty # 15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.7 | 0.63 | 21.494 |  | 4.5 | 0 |  | 0% | Work not yet started.
141 | Shingling of CPR & Jungle Clearance of MD-15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.325 | 0.2925 | 5.8384 |  | 2.28 | 0 |  | 0% | Work not yet started.
142 | Shingling of CPR & Jungle Clearance of Disty 16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 12.75 |  | 2.43 | 0 |  | 0% | Work not yet started.
143 | Shingling of CPR & Jungle Clearance of Minor of Disty-16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.8445 |  | 2.45 | 0 |  | 0% | Work not yet started.
144 | Desiltation / Jungle Clearance of Disty # 17 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 9.6951 |  | 2.13 | 0 |  | 0% | Work not yet started.
145 | Shingling of CPR & Jungle Clearance of Disty # 18 its Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 18.009 |  | 4.26 | 0 |  | 0% | Work not yet started.
146 | Shingling of CPR & Jungle Clearance of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.55 | 0.495 | 15.753 |  | 3.96 | 0 |  | 0% | Work not yet started.
147 | Desiltation / Jungle Clearance of M-1 & M-2 of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.829 |  | 4 | 0 |  | 0% | Work not yet started.
148 | Mansehra Irrigation Division Mansehra
149 | Silt Clearance of Lower Siran Canal RD 0-14000 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3110.16 | 3.04 | 0.2743 | 515 | 17% | In progress
150 | Silt Clearance of Lower Siran Canal RD 14000-36500 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3142.51 | 4.26 | 0.701 | 773.69 | 25% | In progress
151 | Silt Clearance of Lower Siran Canal Hathi Maira Branch & Gandian Minor RD 36500 in reaches | Mansehra Irrigation Division Mansehra | 0.55 | 0.4954 | 26.21 | 2080.06 | 12.1 | 2.8194 | 721.39 | 35% | In progress
152 | Silt Clearance of Upper Siran Canal from RD 0-30000 In reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2065 | 3.048 | 0.1524 | 103.25 | 5% | In progress
153 | Silt Clearance of Upper Siran Canal from RD 30000-61000 in reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2110 | 9.44 | 1.824 | 408 | 19% | In progress
154 | Silt Clearance of Upper Siran Canal from RD 61000-tail in reaches | Mansehra Irrigation Division Mansehra | 0.18 | 0.1623 | 23.86 | 930 | 5.27 | 0.3048 | 53.75 | 6% | In progress
155 | Silt Clearance of Dhodial Minor Upper Siran Canal in reaches | Mansehra Irrigation Division Mansehra | 0.22 | 0.1981 | 5.24 | 1135 | 5.24 | 1.514 | 328 | 29% | In progress
156 | Bazai Main Canal Head Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 |  | 21 | 21 |  | 100% | Completed
157 | Wartair Disty | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 6 |  | 6 | 6 |  | 100% | Completed
158 | Kharki Disty No. 02 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 3.3 |  | 3.3 | 3.3 |  | 100% | Completed
159 | Additional Minor No. 03, 06 and Bazai Disty No. 01. | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | 16.8 |  | 16.8 | 3 |  | 100% | Completed
160 | Bazai Main Canal, Syphon No. 4431, 5851, 12530, 13590, 14842, 18400, 47527 & 58853 | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | [5 empty] | 70% | Work in Progress
161 | Bazai Disty No. 04, Bazai Minor No. 09, 11 and 12. | Malakand Irrigation Division Malakand | 0.27 | 0.26625 | 15.2 |  | 9 | 8 |  | 100% | Completed
162 | Clearance of Syphon 79205, 93480 and 97962. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | [5 empty] | 20% | Work in Progress
163 | Bazai Disty No. 03 and Bazai Minor No. 05. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | 20.5 |  | 20.5 | 7 |  | 100% | Completed
164 | Bazai Main Canal Tail Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 |  | 0 | 0 |  | 0% | Not Yet start
165 | KM-1 RD: 0-2976 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  |  | 0.9 | 0.9 |  | 100% | Completed
166 | KM-1 RD: 0-1500, 22000-29000 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  |  | 2.6 | 2.6 |  | 100% | Completed
167 | Bazai Main Canal RD: 79500 to RD: 84500 | Malakand Irrigation Division Malakand | 0.302 | 0.296 |  |  | 1.5 | 0.3 |  | 20% | Work in Progress
168 | Silt & Shingle Clearance of P.C Minor from RD 0+000 To Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.388 | 12.881 | 1851.77 | 7.62 | 1.2 | 372.84 | 15.74% | Work in Progress
169 | Clearance of Shingri Minor from RD 0-17250 in reaches. | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.309 | 530.92 | 2.499 | 1.585 | 259.19 | 63.42% | Work in Progress
170 | Clearance of Meherdi Minor from RD 0-31000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 9.451 | 1809.24 | 8.382 | 5.792 | 804.63 | 69% | Work in Progress
171 | Clearance of Kalu Branch from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.33 | 0.3218 | 11.563 | [5 empty] | Not yet started
172 | Clearance of Hathian Minor from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.05 | 0.04875 | 2.35 | [5 empty] | Not yet started
173 | Clearance of Jalala Disty from RD: 29000 to Tail in reaches | Malakand Irrigation Division Malakand | 0.37 | 0.3607 | 14.024 | 1476.73 | 5900 | 5400 | 1113.71 | 91.52% | Work in Progress
174 | Clearance of Pirsaddo Disty, Ghano Minor and Qutab Gharh Minor from : H-Tail to Tail in reaches. | Malakand Irrigation Division Malakand | 0.35 | 0.341 | 1.88 | [5 empty] | Not yet started
175 | Clearance of Shergarh Minor from Head to Rd:12+000 in reaches. | Malakand Irrigation Division Malakand | 0.15 | 0.146 | 7.752 | [5 empty] | Not yet started
176 | Clearance of Shergarh Minor from Rd:12+000 tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 7.752 | 1195.13 | 6000 | 5500 | 956.83 | 91.66% | Work in Progress
177 | Clearance of Spokanda Disty from RD: 18000 to Tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 5.659 | [5 empty] | Not yet started
178 | Silt & Shingle Clearance of Spokanda Disty from 0-18000 | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.488 | 771.85 | 2.743 | 1.1 |  | 40% | Work in Progress
179 | Removal of Heaps / Clearance of Bari Band Disty RD: 39+500-88+600 in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.33775 | 14.96 | 1435.76 | 8.21 | 4.5 | 1000 | 54.81% | Work in Progress
180 | Removal of Heaps / Clearance of Hero Shah Minor RD: 0 -38+000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 11.58 | 2446.93 | 11.58 | 6.5 | 1300 | 56.13% | Work in Progress
181 | Removal of Heaps / Clearance of Kalu Shah Disty and Dundian Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.1 | 0.098 | 7.69 | 785.8 | 5 | 5 | 785.8 | 100% | Completed
182 | Removal of Heaps / Clearance of Sarwala Disty and Lund Khwar Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 18.29 | 3172.99 | 10.06 | 6.5 | 2000 | 64.61% | Work in Progress
183 | Removal of Heaps / Clearance of Said Abad Disty and Pir Abad Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 20.42 | 3113.1 | 7.31 | 5.5 | 2000 | 75.24% | Work in Progress
184 | Removal of Heaps / Clearance of Katlang Disty from RD: 0-40+000 in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 12.19 | 1910.43 | 7.61 | 5.5 | 1350 | 72.27% | Work in Progress
185 | Removal of Heaps / Clearance of Shamozai Disty/ Syphon and Likpani Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.392 | 17.67 | 2730.62 | 13.01 | 6.5 | 1500 | 49.96% | Work in Progress
186 | Removal of Heaps / Clearance of Dheri Minor and Tail Minor Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.15 | 0.147 | 7.01 | 1211.68 | 6 | 5 | 1050 | 83.33% | Work in Progress
187 | Jue Shiekh Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 16.29 | 13.03 | 53.35 | 132353 | 53.35 | 35.1 | 87078 | 66% | Work is in progress
188 | Jue Zardad Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 3.6 | 2.88 | 13.1 | 18500 | 13.1 | 9.3 | 13134 | 71% | Work is in progress
189 | Kabul River Canal | Peshawar Canal Division, Peshawar (Kabaul River Canal Sub Division) | 27.855 | 22.284 | 60.35 | 1062085 | 60.35 | 20.4 | 359032 | 34% | Work is in progress
190 | Hazar Khwani Branch | Peshawar Canal Division, Peshawar (Kabul River Canal Sub Division) | 23.2 | 18.56 | 28.04 | 1016303 | 28.04 | 16 | 579916 | 57% | Work is in progress
191 | Silt Clearance of Badwan Kharif Irrigation Scheme at RD 0+00 To Tail. | Chakdara Irrigation Sub Division ,Dir Division | 0.9 | 0.8957 | 22.18 | 4635.35 | 22.18 | 3.65 | 1001.85 | 21.61% | Work In progress
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086

## 04-02-2023
S# | Name of Canal | Name of Division | Estimated Cost(RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Total Quantity of Silt to be removed (m3) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Total Quantity of Silt removed till date (m3) | Progress Till date in % | Remarks
1 | Silt clearance/removal of heaps of Disty No. 9 RD; 41000 to 85500 | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 13.41 | 599.93 | 1 | 0.95 | 569.93 | 95% | In progress
2 | Silt clearance of Power House Minor RD 0 to tail | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 1.28 | 599.9 | 1.28 | 0.83 | 389 | 65% | The canal passing through thickly populated area of Mardan City and the adjacenet locals are throwing garbages into the canal, therefore, it is expedient to clear the remaining portion exact at the end of closure period.
3 | Silt clearance of conduit covering portion of 2/9 Hoti Minor RD 4200 to 5000, 5800 to 7000 & 7200 to 7500 | Mardan Irrigation Division Mardan | 0.7 | 0.4546 | 0.7 | 745.53 | 0.7 | 0.48 | 511.22 | 69% | ..do…
4 | Silt clearance of 2/9 Hoti Minor RD 0 to 4200, 5000 to 5800 & 7500 to 19000 | Mardan Irrigation Division Mardan | 0.8 | 0.5195 | 5.94 | 921.08 | 2.43 | 1.47 | 557.2 | 60% | ..do…
5 | Silt clearance /removal of heaps of kalpani disty RD 0-51000 in reaches and clearance of syphones RD 10500 and 15000 | Mardan Irrigation Division Mardan | 0.7 | 0.4544 | 15.6 | 4463.54 | 5.07 | 4.8 | 4225.84 | 95% | In progress
6 | Silt clearance /removal of heaps of 1/kalpani Kodinaka Minor RD 0-27000 in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 8.22 | 599.94 | 1.82 | 1.26 | 415.34 | 69% | The canal passing through thickly populated area of Mardan City and the adjacenet locals are throwing garbages into the canal, therefore, it is expedient to clear the remaining portion exact at the end of closure period.
7 | Silt clearance /removal of heaps of 2/kalpani Taus Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 6.4 | 2801.12 | 5.5 | 5.26 | 2678.89 | 96% | In progress
8 | Silt clearance of 3/9 Toru Minor RD 0 to 15800 | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 4.81 | 2801.12 | 4.81 | 4.55 | 2649.71 | 95% | In progress
9 | Silt clearance of branch 2/kalpani Muhib Banda Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.175 | 0.1308 | 2.89 | 1633.98 | 2 | 1.9 | 1552.28 | 95% | In progress
10 | Silt Clearance of Maho Dheri Minor RD: 4000 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.1493 | 4.57 | 1138.2 | 3.35 | 3.2 | 1087.24 | 96% | In progress
11 | Silt Clearance of Rashakai Minor from RD: 7000 to 31000 in reaches | Mardan Irrigation Division Mardan | 0.6 | 0.3894 | 9.45 | 2972.29 | 7.31 | 7 | 2846.24 | 96% | In progress
12 | Silt Clearance of Nowshera Minor RD:0 - tail in reachers | Mardan Irrigation Division Mardan | 0.35 | 0.2613 | 5.18 | 2059.85 | 3.2 | 3.06 | 1969.73 | 96% | In progress
13 | Silt Clearance of Turlandi Minor Head to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 5.27 | 2134.4 | 4.71 | 4.71 | 2134.4 | 100% | Completed
14 | Silt Clearance of Khan Mahi Branch from RD: 0 to 3000 and RD: 8000 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 13.41 | 2344.08 | 5.48 | 5.2 | 2224.31 | 95% | In progress
15 | Silt Clearance of Bara Banda Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 3.04 | 1703.02 | 3.04 | 2.88 | 1613.39 | 95% | In progress
16 | Removal of heaps of Disty No. 8 RD: 52000 to 68000 in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 9.45 | 1860.72 | 1.43 | 1.43 | 1860.72 | 100% | Completed
17 | Silt Clearance/removal of heaps of Disty No. 7 at RD: 4000 to 14000 in reaches | Mardan Irrigation Division Mardan | 0.15 | 0.1133 | 4.26 | 1400.56 | 3.04 | 3.04 | 1400.56 | 100% | Completed
18 | Silt Clearance/removal of heaps of Sheikh yousaf Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 5.48 | 239.97 | 2.13 | 2.05 | 230.96 | 96% | In progress
19 | Silt Clearance/removal of heaps of 1/9 Guide Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 7 | 479.94 | 2.74 | 2.62 | 458.92 | 96% | In progress
20 | Silt Clearance/removal of heaps of Koragh Branch RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 14.93 | 479.94 | 2.23 | 2.23 | 479.94 | 100% | Completed
21 | Removal of heaps of Disty No.8 RD: 0 to 38000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 11.58 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
22 | Removal of heaps of Disty No.9 RD: 0 to 41000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 12.5 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
23 | Shamizai Irrigation Canal | Swat Irrigation Division-II Matta | 1 | 0.779 | 20.73 | 5150 | 19.5 | 18.56 | 4902 | 95% | Work is in progress
24 | Barwai Irrigation Canal | Swat Irrigation Division-II Matta | 0.3 | 0.2805 | 11.22 | 1300 | 6.1 | 5.71 | 1219 | 94% | Work is in progress
25 | Silt & Shingle Clearance of P.C Minor from RD 0+000 To Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.388 | 12.881 | 1851.77 | 7.62 | 1.2 | 372.84 | 15.74% | Work in Progress
26 | Clearance of Shingri Minor from RD 0-17250 in reaches. | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.309 | 530.92 | 2.347 | 1.906 | 259.19 | 81.21% | Work in Progress
27 | Clearance of Meherdi Minor from RD 0-31000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 9.451 | 2167.5 | 8.382 | 6.113 | 804.63 | 72.93% | Work in Progress
28 | Clearance of Kalu Branch from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.33 | 0.3218 | 11.563 | [5 empty] | Not yet started
29 | Clearance of Hathian Minor from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.05 | 0.04875 | 2.35 | [5 empty] | Not yet started
30 | Clearance of Jalala Disty from RD: 29000 to Tail in reaches | Malakand Irrigation Division Malakand | 0.37 | 0.3607 | 14.024 | 1476.73 | 5900 | 5400 | 1113.71 | 91.52% | Work in Progress
31 | Clearance of Pirsaddo Disty, Ghano Minor and Qutab Gharh Minor from : H-Tail to Tail in reaches. | Malakand Irrigation Division Malakand | 0.35 | 0.341 | 1.88 | [5 empty] | Not yet started
32 | Clearance of Shergarh Minor from Head to Rd:12+000 in reaches. | Malakand Irrigation Division Malakand | 0.15 | 0.146 | 7.752 | [5 empty] | Not yet started
33 | Clearance of Shergarh Minor from Rd:12+000 tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 7.752 | 1195.13 | 6000 | 5500 | 956.83 | 91.66% | Work in Progress
34 | Clearance of Spokanda Disty from RD: 18000 to Tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 5.659 | [5 empty] | Not yet started
35 | Silt & Shingle Clearance of Spokanda Disty from 0-18000 | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.488 | 771.85 | 2.743 | 1.1 |  | 40% | Work in Progress
36 | Removal of Heaps / Clearance of Bari Band Disty RD: 39+500-88+600 in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.33775 | 14.96 | 1435.76 | 8.21 | 5 | 1200 | 60.9% | Work in Progress
37 | Removal of Heaps / Clearance of Hero Shah Minor RD: 0 -38+000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 11.58 | 2446.93 | 11.58 | 7 | 1600 | 60.44% | Work in Progress
38 | Removal of Heaps / Clearance of Kalu Shah Disty and Dundian Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.1 | 0.098 | 7.69 | 785.8 | 5 | 5 | 785.8 | 100% | Completed
39 | Removal of Heaps / Clearance of Sarwala Disty and Lund Khwar Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 18.29 | 3172.99 | 10.06 | 7.5 | 2300 | 74.55% | Work in Progress
40 | Removal of Heaps / Clearance of Said Abad Disty and Pir Abad Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 20.42 | 3113.1 | 7.31 | 6 | 2500 | 82.07% | Work in Progress
41 | Removal of Heaps / Clearance of Katlang Disty from RD: 0-40+000 in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 12.19 | 1910.43 | 7.61 | 6 | 1600 | 78.84% | Work in Progress
42 | Removal of Heaps / Clearance of Shamozai Disty/ Syphon and Likpani Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.392 | 17.67 | 2730.62 | 13.01 | 8 | 2000 | 61.49% | Work in Progress
43 | Removal of Heaps / Clearance of Dheri Minor and Tail Minor Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.15 | 0.147 | 7.01 | 1211.68 | 6 | 5.5 | 1100 | 91.66% | Work in Progress
44 | Bazai Main Canal Head Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 |  | 21 | 21 |  | 100% | Completed
45 | Wartair Disty | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 6 |  | 6 | 6 |  | 100% | Completed
46 | Kharki Disty No. 02 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 3.3 |  | 3.3 | 3.3 |  | 100% | Completed
47 | Additional Minor No. 03, 06 and Bazai Disty No. 01. | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | 16.8 |  | 16.8 | 3 |  | 100% | Completed
48 | Bazai Main Canal, Syphon No. 4431, 5851, 12530, 13590, 14842, 18400, 47527 & 58853 | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | [5 empty] | 70% | Work in Progress
49 | Bazai Disty No. 04, Bazai Minor No. 09, 11 and 12. | Malakand Irrigation Division Malakand | 0.27 | 0.26625 | 15.2 |  | 9 | 8 |  | 100% | Completed
50 | Clearance of Syphon 79205, 93480 and 97962. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | [5 empty] | 20% | Work in Progress
51 | Bazai Disty No. 03 and Bazai Minor No. 05. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | 20.5 |  | 20.5 | 7 |  | 100% | Completed
52 | Bazai Main Canal Tail Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 |  | 0 | 0 |  | 0% | Not Yet start
53 | KM-1 RD: 0-2976 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  |  | 0.9 | 0.9 |  | 100% | Completed
54 | KM-1 RD: 0-1500, 22000-29000 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  |  | 2.6 | 2.6 |  | 100% | Completed
55 | Bazai Main Canal RD: 79500 to RD: 84500 | Malakand Irrigation Division Malakand | 0.302 | 0.296 |  |  | 1.5 | 0.3 |  | 20% | Work in Progress
56 | Nipki Khel Irrigation Scheme | Swat Irrigation Division -I | 2.2 | 1.76 | 38.87 | 10172.62 | 38.87 | 16.1585 | 4710 | 41.57% | Work in Progress
57 | Swabi Irrigation Division-I Swabi
58 | Shahbaz Garhi Sub Division
59 | Clearance from the bed of Jamal Garhi Disty from 00-tail in reaches. | Swabi Irrigation Division-I Swabi | 0.3 | 0.11 | 16.81 | 1692.37 | 4.7 | 4 | 1523.13 | 90% | In-Progress
60 | Silt Clearance from the bed of Buxali Disty & Kot Minor from 00-tail in reaches | Swabi Irrigation Division-I Swabi | 0.65 | 0.36 | 21.34 | 4715.26 | 9.42 | 8 | 4007.97 | 85% | In-Progress
61 | Removal of debris and heaps from Machai Branch RD 105+000 to 142+000 in reaches | Swabi Irrigation Division-I Swabi | 0.35 | 0.13 | 247.58 | 4521.89 | 0.48 | 0.36 | 3391.42 | 75% | In-Progress
62 | Removal of debris and heaps from Machai Branch RD 142+000 to 186+000 in reaches | Swabi Irrigation Division-I Swabi | 0.35 | 0.13 | 247.58 | 4513.02 | 0.35 | 0.33 | 4287 | 94.99% | In-Progress
63 | Silt Clearance from the bed of Chura Minor , Sawal Dher Minor & Mala Minor from RD: 00-tail in reaches. | Swabi Irrigation Division-I Swabi | 0.3 | 0.11 | 14.38 | 1698.88 | 7 | 6 | 1528.92 | 90% | In-Progress
64 | Silt clearance from the bed Shahbaz Garhi Disty and its sub System from RD:00-tail in reaches | Swabi Irrigation Division-I Swabi | 0.8 | 0.44 | 18.29 | 4522.69 | 14.85 | 13 | 3844.28 | 85% | In-Progress
65 | Silt Clearance from the bed of Ismalia Disty and its sub system from 00-tail in reaches | Swabi Irrigation Division-I Swabi | 0.9 | 0.5 | 18.29 | 6469.09 | 13.26 | 12 | 5822.18 | 90% | In-Progress
66 | Silt Clearance from the bed of Adina Minor and adina Minor Branch from Head to tail in reaches | Swabi Irrigation Division-I Swabi | 0.35 | 0.19 | 7.89 | 1980.17 | 5.59 | 5 | 1782.15 | 90% | In-Progress
67 | Dir Irrigation Division at Timargara
68 | Silt Clearance of Badwan Kharif Irrigation Scheme at RD 0+00 To Tail. | Chakdara Irrigation Sub Division ,Dir Division | 0.9 | 0.8957 | 22.18 | 4635.35 | 22.18 | 5.936 | 1498.85 | 32.33% | Work In progress
69 | Mansehra Irrigation Division Mansehra
70 | Silt Clearance of Lower Siran Canal RD 0-14000 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3110.16 | 3.04 | 0.3657 | 915 | 29% | In progress
71 | Silt Clearance of Lower Siran Canal RD 14000-36500 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3142.51 | 4.26 | 0.8076 | 1123.69 | 36% | In progress
72 | Silt Clearance of Lower Siran Canal Hathi Maira Branch & Gandian Minor RD 36500 in reaches | Mansehra Irrigation Division Mansehra | 0.55 | 0.4954 | 26.21 | 2080.06 | 12.1 | 2.9413 | 921.39 | 44% | In progress
73 | Silt Clearance of Upper Siran Canal from RD 0-30000 In reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2065 | 3.048 | 0.2286 | 154.87 | 7% | In progress
74 | Silt Clearance of Upper Siran Canal from RD 30000-61000 in reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2110 | 9.44 | 2.4336 | 544 | 26% | In progress
75 | Silt Clearance of Upper Siran Canal from RD 61000-tail in reaches | Mansehra Irrigation Division Mansehra | 0.18 | 0.1623 | 23.86 | 930 | 5.27 | 0.5478 | 96.75 | 10% | In progress
76 | Silt Clearance of Dhodial Minor Upper Siran Canal in reaches | Mansehra Irrigation Division Mansehra | 0.22 | 0.1981 | 5.24 | 1135 | 5.24 | 1.818 | 393 | 35% | In progress
77 | Jue Shiekh Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 16.29 | 13.03 | 53.35 | 132353 | 53.35 | 38.5 | 95512 | 72% | Work is in progress
78 | Jue Zardad Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 3.6 | 2.88 | 13.1 | 18500 | 13.1 | 11 | 15534 | 84% | Work is in progress
79 | Kabul River Canal | Peshawar Canal Division, Peshawar (Kabaul River Canal Sub Division) | 27.855 | 22.284 | 60.35 | 1062085 | 60.35 | 23.5 | 413591 | 39% | Work is in progress
80 | Hazar Khwani Branch | Peshawar Canal Division, Peshawar (Kabul River Canal Sub Division) | 23.2 | 18.56 | 28.04 | 1016303 | 28.04 | 19.3 | 699524 | 69% | Work is in progress
81 | Warsak Gravity Canal | Warsak Canals Division Peshawar | 18.8 | 16.2 | 68.88 | 23089.8 | 61.26 | 18.3 | 6318.1 | 41% | Work is in progress
82 | Warsak Minor | Warsak Canals Division Peshawar | 0.8 | 0.736 | 5.85 | 873 | 5.85 | 1.41 | 204.61 | 29% | Work is in progress
83 | Kafoor Dheri Minor | Warsak Canals Division Peshawar | 0.4 | 0.368 | 0.94 | 900 | 0.94 | 0 | 0 | 0% | Work is in progress
84 | Shahi Bala Minor | Warsak Canals Division Peshawar | 0.4 | 0.368 | 1.07 | 995 | 1.07 | 0 | 0 | 0% | Work is in progress
85 | Mullazai Minor | Warsak Canals Division Peshawar | 0.3 | 0.552 | 3.35 | 1670 | 3.35 | 0.98 | 485.82 | 35% | Work is in progress
86 | Tehkal Minor | Warsak Canals Division Peshawar | 0.6 | 0.552 | 0.99 | 360 | 0.99 | 0 | 0 | 0% | Work is in progress
87 | Palosai Minor | Warsak Canals Division Peshawar | 0.5 | 0.46 | 0.66 | 455 | 0.66 | 0 | 0 | 0% | Work is in progress
88 | Surizai Minor | Warsak Canals Division Peshawar | 0.4 | 0.368 | 3.02 | 1039 | 3.02 | 0.91 | 241.38 | 35% | Work is in progress
89 | Urmar Minor | Warsak Canals Division Peshawar | 0.8 | 0.736 | 6.71 | 1490 | 6.71 | 1.78 | 369.11 | 29% | Work is in progress
90 | Pabbi Minor | Warsak Canals Division Peshawar | 0.4 | 0.368 | 2.44 | 694 | 2.44 | 1.92 | 524.84 | 79% | Work is in progress
91 | Warsak Lift Canal | Warsak Canals Division Peshawar | 8.39 | 6.5 | 46.63 | 7487.19 | 29.56 | 8.3 | 1852.5 | 34% | Work is in progress
92 | Regi Minor | Warsak Canals Division Peshawar | 0.13 | 0.15 | 0.91 | 270 | 0.91 | 0 | 0 | 0% | Work is in progress
93 | Badabher Minor | Warsak Canals Division Peshawar | 0.26 | 0.29 | 5.49 | 530 | 5.49 | 0 | 0 | 0% | Work is in progress
94 | Warsak Left Bank Canal | Warsak Canals Division Peshawar | 1.69 | 1.554 | 19.29 | 6837.96 | 13.2 | 2.13 | 852.77 | 28% | Work is in progress
95 | Periodical silt clearance of Fore Bay and Feeder Channel Of WPH, Sump Well, Sedimenattion Tank & Raising Main | Warsak Canals Division Peshawar | 2.2 | 1.9 | 3.22 | 4500 | 3.22 | 0 | 0 | 0% | Work is in progress
96 | Silt clearance from RD:0+00 to RD:8+000 in reaches of Ghazai Khani Flow Irrigation Scheme | Swat Irrigation Division -I | 0.24 | 0.213 | 2.438 | 1339.39 | 2.44 | 2.05 | 720 | 53.76% | Work in Progress
97 | "Silt clearance from RD:0+00 to RD:12+000 in reaches of Karshalizara Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.1199 | 3.657 | 613 | 3.66 | 2.34 | 475 | 77.49% | Work in Progress
98 | "Silt clearance from RD:0+00 to RD:20+000 in reaches of Charorai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.15 | 0.135 | 6.096 | 766.25 | 6.1 | 4.5 | 680 | 88.74% | Work in Progress
99 | "Silt clearance from RD:0+00 to RD:12+000 in reaches of Kuriya Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.25 | 0.225 | 3.657 | 1397.44 | 3.66 | 2.6 | 750 | 53.67% | Work in Progress
100 | "Silt clearance from RD:0+00 to RD:9+000 in reaches of Elai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 2.743 | 613 | 2.74 | 2.2 | 350 | 57.1% | Work in Progress
101 | "Silt clearance from RD:0+00 to RD:60+000 in reaches of Budal Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 18.287 | 672.53 | 9.14 | 5.9 | 340 | 50.56% | Work in Progress
102 | "Silt clearance from RD:0+00 to RD:16+000 in reaches of Singarai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 4.267 | 669.7 | 4.27 | 2.75 | 350 | 52.26% | Work in Progress
103 | "Silt clearance from RD:0+00 to RD:26+000 in reaches of Bajkata Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.24 | 0.216 | 7.924 | 408.66 | 7.92 | 4.5 | 280 | 68.52% | Work in Progress
104 | Silt clearance from RD:0+00 to RD:34+000 in reaches of Gagra Flow Irrigation Scheme | Swat Irrigation Division -I | 0.5 | 0.4 | 10.363 | 2797 | 9.75 | 5.1 | 1750 | 62.57% | Work in Progress
105 | Swabi Irrigation Division-II Swabi
106 | Clearance of Topi Lift Irrigation Channels RD;00-Tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 4.88 | 1161.77 | 4.87 | 2.44 | 615.96 | 50% | Work in progress
107 | Clearance of Topi & Zarobi Minors from RD;00 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | Topi =4.24 Zarobi =4.27 | 1159.72 | 3.05 | 2.13 | 701.9 | 70% | Work in progress
108 | Clearance/Repair of Badri Lift Irrigation Scheme | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 0.34 | 607.12 | 0.33 | 0.33 | 607.12 | 100% | Competed
109 | Clearance of Kotha Disty; from RD;00 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.24 | 0.24 | 17.53 | 1389.07 | 1.89 | 1.89 | 1389.07 | 100% | Competed
110 | Clearance of Pehur main Canal from RD;46000 to RD;54000 | Swabi Irrigation Division-II Swabi | 0.18 | 0.18 | 51.4 | 1042.24 | 0.53 | 0.53 | 1042.24 | 100% | Competed
111 | Clearance of Pehur Main Canal from RD;54500 to RD;66000 | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 51.4 | 1130.88 | 0.55 | 0.27 | 565.44 | 50% | Work in progress
112 | Clearance of Pehur Main Canal from RD;66000 to RD;85000 | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.92 | 0.7 | 0.4 | 793.79 | 57% | Work in progress
113 | Clearance of Pehur Main Canal RD;85000 to RD;93000 | Swabi Irrigation Division-II Swabi | 0.16 | 0.16 | 51.4 | 976.63 | 0.63 | 0.46 | 695.7 | 72% | Work in progress
114 | Clearance of Pehur Main Canal from RD;93500 to RD;98000 | Swabi Irrigation Division-II Swabi | 0.17 | 0.17 | 51.4 | 1033.5 | 0.32 | 0.16 | 516.75 | 50% | Work in progress
115 | Clearance of Pehur Main Canal from RD;98500 to RD;113000 | Swabi Irrigation Division-II Swabi | 0.18 | 0.18 | 51.4 | 1094.71 | 0.61 | 0.46 | 792.24 | 75% | Work in progress
116 | Clearance of Kaddi, Zaida, Zakarriya & Sheikhdheri Minors from RD;00 to Tail | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | Kaddi= 5.79 Zaida= 3.81 Zakary=3.43 S/Dher=2.95 | 1292.45 | 0.39 | 0.2 | 702.12 | 50% | Work in progress
117 | Clearance of Pehur Main Canal System from RD;113000 to RD;117000 | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 51.4 | 883 | 0.4 | 0.3 | 685.62 | 77% | Work in progress
118 | Clearance of Pehur Main Canal System from RD;117000 to RD;122000 | Swabi Irrigation Division-II Swabi | 0.12 | 0.12 | 51.4 | 729.53 | 0.22 | 0.11 | 364.76 | 50% | Work in progress
119 | Clearance of Pehur main Canal System from RD;122000 to RD;133000 | Swabi Irrigation Division-II Swabi | 0.13 | 0.13 | 51.4 | 790.91 | 0.4 | 0.34 | 649.45 | 85% | Work in progress
120 | Clearance of flood deposition from the bed of PMC from RD;13300 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 67.38 | 0.02 | 0.01 | 8.95 | 50% | Work in progress
121 | Clearance of PMC System from RD;133000 to 140000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 51.4 | 1738.06 | 0.85 | 0.85 | 1738.06 | 100% | Competed
122 | Clearance of PMC Systems from RD;145000 to RD;150000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.23 | 0.23 | 51.4 | 1332.82 | 0.41 | 0.2 | 666.41 | 50% | Work in progress
123 | Clearance of PMC System from RD;150500 to RD;162000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.81 | 0.44 | 0.22 | 988.94 | 50% | Work in progress
124 | Clearance of PMC System from RD;162100 to Tail & other allied Branches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.85 | 3.23 | 2.59 | 1191.93 | 80% | Work in progress
125 | Clearance of Thanodher Disty: & Bazar Minor from RD;00 to Tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | Thano=6.00 Bazar=7.47 | 1157.95 | 0.35 | 0.18 | 844.83 | 50% | Work in progress
126 | Clearance of flood deposition and silt clearance of ¦Indus Branch RD:74500 Tail in reaches. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 18.54 | 4478 | 11.89 | 8.69 | 3001.26 | 73% | Work in progress
127 | Silt Clearance of Dagi Minor from RD:0- 37000 in reaches i/c repair to out lets & other allied structures. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 11.28 | 4482 | 9.15 | 4.05 | 1982.19 | 44% | Work in progress
128 | Silt Clearance of Dandoka Minor from RD:0-Tail in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.03 | 0 | 0 | 0 | 0 |  | contractor deployed
129 | Silt Clearance of Sudher Minor RD:0 - tail in reaches & other allied structures | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 2.29 | 0 | 0 | 0 | 0 |  | contractor deployed
130 | Silt Clearance of Yar Hussain Minor RD;0-tail | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 6.8 | 2803.37 | 5.79 | 0.91 | 467.23 | 16% | Work in progress
131 | Silt Clearance of Ghazi Kot Minor from RD: 0-tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.95 | 0 | 0 | 0 | 0 |  | contractor deployed
132 | Silt Clearance Daulat Minor and Gidar Minor RD; 0-tail in reaches & other allied structures | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 16.84 | 4482 | 13.11 | 12.65 | 4219.21 | 97% | Work in progress
133 | Silt Clearance of Pirsabaq Disty and pirsabaq Minor from Rd:0-tail in reaches. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 11.75 | 4946.41 | 14.21 | 6.4 | 1947.46 | 45% | Work in progress
134 | Silt Clearance of Chowky Disty, Chowki Minor 1 and 2 from RD: 00 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 8.23 | 0 | 7.01 | 0 | 0 |  | contractor deployed
135 | Silt Clearance of Gumbat Minor No.1 & Gumbat Branch from RD:0+0 to tail in reaches., | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 5.18 | 3096.09 | 6.46 | 2.74 | 1705.02 | 42% | Work in progress
136 | Silt Clearance of Misri Banda from RD;0 to tal in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.73 | 2472.77 | 5.4 | 3.05 | 1691.93 | 56% | Work in progress
137 | Silt Clearance of Ambar Branch from RD;0+0 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.35 | 0.35 | 7.88 | 0 | 0 | 0 | 0 |  | contractor deployed
138 | Silt Clearance of Jehangira Minor & Nandrak Minor from RD;0-tail in reaches and repair to allied structures | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 11.52 | 0 | 0 | 0 | 0 |  | contractor deployed
139 | Silt Clearance of Thanodher Minor & Manki Minor from RD;0-tail in reaches | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 12.42 | 0 | 0 | 0 | 0 |  | contractor deployed
140 | Silt Clearance of Yaqubi Minor, Sard China Minor and Naik Nam Minor from RD; 0-tail | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 10.46 | 0 | 0 | 0 | 0 |  | contractor deployed
141 | Silt Clearance of Dagi Disty & repair to allied structures Rd 0 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 3.23 | 0 | 0 | 0 | 0 |  | contractor deployed
142 | Silt Clerance of Gumbat Minor No 2 | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 4.57 | 0 | 0 | 0 | 0 |  | contractor deployed
143 | Silt Clearance and repair of Link Channel, Lahor Minor ,Zakaria Minor Sheik Dheri from RD; 0- to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 8.19 | 0 | 0 | 0 | 0 |  | contractor deployed
144 | Silt Clerance of Toru Minor | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 4.57 | 0 | 0 | 0 | 0 |  | contractor deployed
145 | Repair clearance of Sypon Rd 6200 & 8000 Pir Sabaq Disty | Swabi Irrigation Division-II Swabi | 0.1 | 0.1 | 0.06 | 0 | 0 | 0 | 0 |  | contractor deployed
146 | Repair clearance of Sypon Rd 200 Gidar Minor | Swabi Irrigation Division-II Swabi | 0.05 | 0.05 | 0.05 | 0 | 0 | 0 | 0 |  | contractor deployed
147 | Clearance and dewatering of Syphons & repair to out lets Jaggan Nath Section. | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 0.15 | 0 | 0 | 0 | 0 |  | contractor deployed
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086

## 05-02-2023
S# | Name of Canal | Name of Division | Estimated Cost(RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Total Quantity of Silt to be removed (m3) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Total Quantity of Silt removed till date (m3) | Progress Till date in % | Remarks
1 | Silt clearance of Sarai Saleh NPC Rd 0-10000 in reaches | Haripur Irrigation Division Haripur | 0.35 | 0.283 | 15.85 | 1271 | 3.04 | 2.9 | 1205.95 | 92% | In progress
2 | Silt clearance of Sarai Saleh NPC Rd 10000-17000 i/c Minor No.1 in reaches | Haripur Irrigation Division Haripur | 0.3 | 0.24 | 15.85 | 1131.96 | 2.13 | 1.5 | 745.9 | 40% | In progress
3 | Silt clearance of Sarai Saleh NPC Rd 17000-30000 i/c Minor No.2 in reaches | Haripur Irrigation Division Haripur | 0.35 | 0.28 | 15.85 | 1347 | 3.96 | 1.85 | 705.65 | 40% | In progress
4 | Clearance of Daur Main Canal Rd 0-tail | Haripur Irrigation Division Haripur | 0.15 | 0.1216 | 0.838 | 555.2 | 0.838 | 0.838 | 555.2 | 100% | Work completed
5 | Silt Clearance of Disty No.02 RD 0-20000 in reaches. | Haripur Irrigation Division Haripur | 0.25 | 0.2 | 6.62 | 1287.6 | 6.09 | 5.79 | 1210.58 | 95% | In progress
6 | Silt Clearance of Main KRBC RD 11000-42000 in reaches | Haripur Irrigation Division Haripur | 0.25 | 0.225 | 12.8 | 1287.6 | 9.45 | 7.5 | 1150 | 88% | In progress
7 | Silt Clearance Disty No.04 RD 0-24000 in reaches. | Haripur Irrigation Division Haripur | 0.3 | 0.24 | 7.31 | 1545.12 | 7.31 | 5.45 | 1238.9 | 73% | In progress
8 | Silt Clearance of Disty No.03 i/c Ziarat Minor and Bandi Minor in reaches. | Haripur Irrigation Division Haripur | 0.3 | 0.24 | 10.67 | 1545.12 | 10.67 | 3.05 | 570.75 | 35% | In progress
9 | Silt Clearance of Disty No.1 i/c Balartop & Kamalpur Minors in reaches. | haripur Irrigation Division Haripur | 0.3 | 0.24 | 10.36 | 1545.12 | 10.36 | 6.07 | 905.88 | 70% | In progress
10 | Silt Clearance of KLBC Rd 0-26000 in reaches | haripur Irrigation Division Haripur | 0.3 | 0.24 | 7.92 | 1545.12 | 7.92 | 0 | 0 | 0 | not yet started due to decisiion made in meeting with XEN WAPDA, PMO and CDA Islambad authorities and work will be started from 15th February 2023
11 | Silt clearance of Sarai Saleh NPC Rd 30000-40000 i/c Minor No. 3 in reaches | HAripur Irrigation Division Haripur | 0.25 | 0.2 | 15.85 | 946 | 3.04 | 0.35 | 190.8 | 20% | In progress
12 | Clearance of Main Rangila Irrigation system i/c Rangila Tank | Haripur Irrigation Division Haripur | 0.2 | 0.173 | 2.21 | 559 | 2.21 | 0 | 0 | 0 | Not yet started
13 | Silt Clearance of Chak Muneem Minor. | Haripur Irrigation Division Haripur | 0.2 | 0.16 | 7.01 | 1030.8 | 7.01 | 0 | 0 | 0 | Not yet started
14 | Silt clearance/removal of heaps of Disty No. 9 RD; 41000 to 85500 | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 13.41 | 599.93 | 1 | 0.95 | 569.93 | 95% | In progress
15 | Silt clearance of Power House Minor RD 0 to tail | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 1.28 | 599.9 | 1.28 | 0.87 | 407.74 | 68% | The canal passing through thickly populated area of Mardan City and the adjacenet locals are throwing garbages into the canal, therefore, it is expedient to clear the remaining portion exact at the end of closure period.
16 | Silt clearance of conduit covering portion of 2/9 Hoti Minor RD 4200 to 5000, 5800 to 7000 & 7200 to 7500 | Mardan Irrigation Division Mardan | 0.7 | 0.4546 | 0.7 | 745.53 | 0.7 | 0.48 | 511.22 | 69% | ..do…
17 | Silt clearance of 2/9 Hoti Minor RD 0 to 4200, 5000 to 5800 & 7500 to 19000 | Mardan Irrigation Division Mardan | 0.8 | 0.5195 | 5.94 | 921.08 | 2.43 | 1.47 | 557.2 | 60% | ..do…
18 | Silt clearance /removal of heaps of kalpani disty RD 0-51000 in reaches and clearance of syphones RD 10500 and 15000 | Mardan Irrigation Division Mardan | 0.7 | 0.4544 | 15.6 | 4463.54 | 5.07 | 4.8 | 4225.84 | 95% | In progress
19 | Silt clearance /removal of heaps of 1/kalpani Kodinaka Minor RD 0-27000 in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 8.22 | 599.94 | 1.82 | 1.3 | 428.53 | 71% | The canal passing through thickly populated area of Mardan City and the adjacenet locals are throwing garbages into the canal, therefore, it is expedient to clear the remaining portion exact at the end of closure period.
20 | Silt clearance /removal of heaps of 2/kalpani Taus Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 6.4 | 2801.12 | 5.5 | 5.26 | 2678.89 | 96% | In progress
21 | Silt clearance of 3/9 Toru Minor RD 0 to 15800 | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 4.81 | 2801.12 | 4.81 | 4.55 | 2649.71 | 95% | In progress
22 | Silt clearance of branch 2/kalpani Muhib Banda Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.175 | 0.1308 | 2.89 | 1633.98 | 2 | 1.9 | 1552.28 | 95% | In progress
23 | Silt Clearance of Maho Dheri Minor RD: 4000 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.1493 | 4.57 | 1138.2 | 3.35 | 3.28 | 1114.42 | 98% | In progress
24 | Silt Clearance of Rashakai Minor from RD: 7000 to 31000 in reaches | Mardan Irrigation Division Mardan | 0.6 | 0.3894 | 9.45 | 2972.29 | 7.31 | 7.18 | 2919.43 | 98% | In progress
25 | Silt Clearance of Nowshera Minor RD:0 - tail in reachers | Mardan Irrigation Division Mardan | 0.35 | 0.2613 | 5.18 | 2059.85 | 3.2 | 3.12 | 2008.35 | 98% | In progress
26 | Silt Clearance of Turlandi Minor Head to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 5.27 | 2134.4 | 4.71 | 4.71 | 2134.4 | 100% | Completed
27 | Silt Clearance of Khan Mahi Branch from RD: 0 to 3000 and RD: 8000 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 13.41 | 2344.08 | 5.48 | 5.35 | 2288.47 | 98% | In progress
28 | Silt Clearance of Bara Banda Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 3.04 | 1703.02 | 3.04 | 2.98 | 1669.41 | 98% | In progress
29 | Removal of heaps of Disty No. 8 RD: 52000 to 68000 in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 9.45 | 1860.72 | 1.43 | 1.43 | 1860.72 | 100% | Completed
30 | Silt Clearance/removal of heaps of Disty No. 7 at RD: 4000 to 14000 in reaches | Mardan Irrigation Division Mardan | 0.15 | 0.1133 | 4.26 | 1400.56 | 3.04 | 3.04 | 1400.56 | 100% | Completed
31 | Silt Clearance/removal of heaps of Sheikh yousaf Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 5.48 | 239.97 | 2.13 | 2.08 | 234.34 | 98% | In progress
32 | Silt Clearance/removal of heaps of 1/9 Guide Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 7 | 479.94 | 2.74 | 2.68 | 469.43 | 98% | In progress
33 | Silt Clearance/removal of heaps of Koragh Branch RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 14.93 | 479.94 | 2.23 | 2.23 | 479.94 | 100% | Completed
34 | Removal of heaps of Disty No.8 RD: 0 to 38000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 11.58 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
35 | Removal of heaps of Disty No.9 RD: 0 to 41000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 12.5 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
36 | Silt Clearance of Badwan Kharif Irrigation Scheme at RD 0+00 To Tail. | Chakdara Irrigation Sub Division ,Dir Division | 0.9 | 0.8957 | 22.18 | 4635.35 | 22.18 | 6.096 | 1587.38 | 34.24% | In progress
37 | Silt Clearance of Gandigar Irrigation Scheme Dir Upper From RD 00 To 30000 | Dir Irrigation Division Dir Lower at Timergara | 0.7 | 0.56 | 9.14 | 3543.3 | 8 | 0 | 0 | 0 | Work will be started after concrete work in head divertion bund
38 | Silt Clearance of Gandigar Irrigation Scheme Dir Upper From RD 30000 To 60000 | Dir Irrigation Division Dir Lower at Timergara | 0.7 | 0.56 | 9.14 | 3543.3 | 9.14 | 0.5 | 190.5 | 5.5% | Work in progress
39 | Silt Clearance of Gandigar Irrigation Scheme Dir Upper From RD 60000 To Tail and Silt Clearance of Ganorai Irrigation scheme from Head To Tail | Dir Irrigation Division Dir Lower at Timergara | 0.8 | 0.614 | 22.56 | 4049.5 | 20 | 1.2 | 360.5 | 9% | Work in progress
40 | Silt Clearance of Darora Jughabanj Irrigation Scheme Dir Upper From RD 00 To 40000 | Dir Irrigation Division Dir Lower at Timergara | 0.6 | 0.354 | 12.19 | 3037.5 | 12.19 | 2 | 350.13 | 11.5%% | Work in progress
41 | Silt Clearance of Darora Jughabanj Irrigation Scheme Dir Upper From RD 40000 to Tail | Dir Irrigation Division Dir Lower at Timergara | 0.6 | 0.48 | 9.75 | 3037.5 | 9.75 | 0.5 | 90.5 | 3% | Work in progress
42 | Shamizai Irrigation Canal | Swat Irrigation Division-II Matta | 1 | 0.779 | 20.73 | 5150 | 19.5 | 18.91 | 4995 | 97% | Work is in progress
43 | Barwai Irrigation Canal | Swat Irrigation Division-II Matta | 0.3 | 0.2805 | 11.22 | 1300 | 6.1 | 5.94 | 1268 | 98% | Work is in progress
44 | Warsak Gravity Canal | Warsak Canals Division Peshawar | 18.8 | 16.2 | 68.88 | 23089.8 | 61.26 | 19.4 | 6318.1 | 45% | Work is in progress
45 | Warsak Minor | Warsak Canals Division Peshawar | 0.8 | 0.736 | 5.85 | 873 | 5.85 | 1.66 | 204.61 | 32% | Work is in progress
46 | Kafoor Dheri Minor | Warsak Canals Division Peshawar | 0.4 | 0.368 | 0.94 | 900 | 0.94 | 0 | 0 | 0% | Work is in progress
47 | Shahi Bala Minor | Warsak Canals Division Peshawar | 0.4 | 0.368 | 1.07 | 995 | 1.07 | 0 | 0 | 0% | Work is in progress
48 | Mullazai Minor | Warsak Canals Division Peshawar | 0.3 | 0.552 | 3.35 | 1670 | 3.35 | 1.23 | 485.82 | 37% | Work is in progress
49 | Tehkal Minor | Warsak Canals Division Peshawar | 0.6 | 0.552 | 0.99 | 360 | 0.99 | 0 | 0 | 0% | Work is in progress
50 | Palosai Minor | Warsak Canals Division Peshawar | 0.5 | 0.46 | 0.66 | 455 | 0.66 | 0 | 0 | 0% | Work is in progress
51 | Surizai Minor | Warsak Canals Division Peshawar | 0.4 | 0.368 | 3.02 | 1039 | 3.02 | 0.97 | 241.38 | 37% | Work is in progress
52 | Urmar Minor | Warsak Canals Division Peshawar | 0.8 | 0.736 | 6.71 | 1490 | 6.71 | 1.81 | 369.11 | 30% | Work is in progress
53 | Pabbi Minor | Warsak Canals Division Peshawar | 0.4 | 0.368 | 2.44 | 694 | 2.44 | 1.95 | 524.84 | 80% | Work is in progress
54 | Warsak Lift Canal | Warsak Canals Division Peshawar | 8.39 | 6.5 | 46.63 | 7487.19 | 29.56 | 9.15 | 1852.5 | 35% | Work is in progress
55 | Regi Minor | Warsak Canals Division Peshawar | 0.13 | 0.15 | 0.91 | 270 | 0.91 | 0 | 0 | 0% | Work is in progress
56 | Badabher Minor | Warsak Canals Division Peshawar | 0.26 | 0.29 | 5.49 | 530 | 5.49 | 0 | 0 | 0% | Work is in progress
57 | Warsak Left Bank Canal | Warsak Canals Division Peshawar | 1.69 | 1.554 | 19.29 | 6837.96 | 13.2 | 2.41 | 852.77 | 30% | Work is in progress
58 | Periodical silt clearance of Fore Bay and Feeder Channel Of WPH, Sump Well, Sedimenattion Tank & Raising Main | Warsak Canals Division Peshawar | 2.2 | 1.9 | 3.22 | 4500 | 3.22 | 0 | 0 | 0% | Work is in progress
59 | Nipki Khel Irrigation Scheme | Swat Irrigation Division -I | 2.2 | 1.76 | 38.87 | 10172.62 | 38.87 | 17.378 | 4853.5 | 44.71% | Work in Progress
60 | Silt clearance from RD:0+00 to RD:8+000 in reaches of Ghazai Khani Flow Irrigation Scheme | Swat Irrigation Division -I | 0.24 | 0.213 | 2.438 | 1339.39 | 2.44 | 2.1 | 730 | 54.5% | Work in Progress
61 | "Silt clearance from RD:0+00 to RD:12+000 in reaches of Karshalizara Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.1199 | 3.657 | 613 | 3.66 | 2.4 | 485 | 79.12% | Work in Progress
62 | "Silt clearance from RD:0+00 to RD:20+000 in reaches of Charorai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.15 | 0.135 | 6.096 | 766.25 | 6.1 | 4.6 | 690 | 90.05% | Work in Progress
63 | "Silt clearance from RD:0+00 to RD:12+000 in reaches of Kuriya Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.25 | 0.225 | 3.657 | 1397.44 | 3.66 | 2.7 | 780 | 55.82% | Work in Progress
64 | "Silt clearance from RD:0+00 to RD:9+000 in reaches of Elai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 2.743 | 613 | 2.74 | 2.25 | 360 | 58.73% | Work in Progress
65 | "Silt clearance from RD:0+00 to RD:60+000 in reaches of Budal Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 18.287 | 672.53 | 9.14 | 6.05 | 350 | 52.04% | Work in Progress
66 | "Silt clearance from RD:0+00 to RD:16+000 in reaches of Singarai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 4.267 | 669.7 | 4.27 | 2.8 | 360 | 53.76% | Work in Progress
67 | "Silt clearance from RD:0+00 to RD:26+000 in reaches of Bajkata Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.24 | 0.216 | 7.924 | 408.66 | 7.92 | 4.6 | 290 | 70.96% | Work in Progress
68 | Silt clearance from RD:0+00 to RD:34+000 in reaches of Gagra Flow Irrigation Scheme | Swat Irrigation Division -I | 0.5 | 0.4 | 10.363 | 2797 | 9.75 | 5.2 | 1800 | 64.35% | Work in Progress
69 | Removal of Heaps / Clearance of Bari Band Disty RD: 39+500-88+600 in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.33775 | 14.96 | 1435.76 | 8.21 | 6 | 1300 | 73.08% | Work in Progress
70 | Removal of Heaps / Clearance of Hero Shah Minor RD: 0 -38+000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 11.58 | 2446.93 | 11.58 | 9 | 1800 | 77.72% | Work in Progress
71 | Removal of Heaps / Clearance of Kalu Shah Disty and Dundian Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.1 | 0.098 | 7.69 | 785.8 | 5 | 5 | 785.8 | 100% | Completed
72 | Removal of Heaps / Clearance of Sarwala Disty and Lund Khwar Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 18.29 | 3172.99 | 10.06 | 8.5 | 2500 | 84.49% | Work in Progress
73 | Removal of Heaps / Clearance of Said Abad Disty and Pir Abad Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 20.42 | 3113.1 | 7.31 | 6.5 | 2650 | 88.91% | Work in Progress
74 | Removal of Heaps / Clearance of Katlang Disty from RD: 0-40+000 in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 12.19 | 1910.43 | 7.61 | 6.5 | 1700 | 85.41% | Work in Progress
75 | Removal of Heaps / Clearance of Shamozai Disty/ Syphon and Likpani Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.392 | 17.67 | 2730.62 | 13.01 | 9.5 | 2200 | 73.02% | Work in Progress
76 | Removal of Heaps / Clearance of Dheri Minor and Tail Minor Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.15 | 0.147 | 7.01 | 1211.68 | 6 | 5.75 | 1150 | 95.83% | Work in Progress
77 | Bazai Main Canal Head Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 |  | 21 | 21 |  | 100% | Completed
78 | Wartair Disty | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 6 |  | 6 | 6 |  | 100% | Completed
79 | Kharki Disty No. 02 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 3.3 |  | 3.3 | 3.3 |  | 100% | Completed
80 | Additional Minor No. 03, 06 and Bazai Disty No. 01. | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | 16.8 |  | 16.8 | 3 |  | 100% | Completed
81 | Bazai Main Canal, Syphon No. 4431, 5851, 12530, 13590, 14842, 18400, 47527 & 58853 | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | [5 empty] | 70% | Work in Progress
82 | Bazai Disty No. 04, Bazai Minor No. 09, 11 and 12. | Malakand Irrigation Division Malakand | 0.27 | 0.26625 | 15.2 |  | 9 | 8 |  | 100% | Completed
83 | Clearance of Syphon 79205, 93480 and 97962. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | [5 empty] | 20% | Work in Progress
84 | Bazai Disty No. 03 and Bazai Minor No. 05. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | 20.5 |  | 20.5 | 7 |  | 100% | Completed
85 | Bazai Main Canal Tail Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 |  | 0 | 0 |  | 0% | Not Yet start
86 | KM-1 RD: 0-2976 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  |  | 0.9 | 0.9 |  | 100% | Completed
87 | KM-1 RD: 0-1500, 22000-29000 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  |  | 2.6 | 2.6 |  | 100% | Completed
88 | Bazai Main Canal RD: 79500 to RD: 84500 | Malakand Irrigation Division Malakand | 0.302 | 0.296 |  |  | 1.5 | 0.3 |  | 20% | Work in Progress
89 | Silt & Shingle Clearance of P.C Minor from RD 0+000 To Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.388 | 12.881 | 1851.77 | 7.62 | 1.2 | 372.84 | 15.74% | Work in Progress
90 | Clearance of Shingri Minor from RD 0-17250 in reaches. | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.309 | 530.92 | 2.347 | 1.906 | 259.19 | 81.21% | Work in Progress
91 | Clearance of Meherdi Minor from RD 0-31000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 9.451 | 2167.5 | 8.382 | 6.113 | 804.63 | 72.93% | Work in Progress
92 | Clearance of Kalu Branch from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.33 | 0.3218 | 11.563 | [5 empty] | Not yet started
93 | Clearance of Hathian Minor from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.05 | 0.04875 | 2.35 | [5 empty] | Not yet started
94 | Clearance of Jalala Disty from RD: 29000 to Tail in reaches | Malakand Irrigation Division Malakand | 0.37 | 0.3607 | 14.024 | 1476.73 | 5900 | 5400 | 1113.71 | 91.52% | Work in Progress
95 | Clearance of Pirsaddo Disty, Ghano Minor and Qutab Gharh Minor from : H-Tail to Tail in reaches. | Malakand Irrigation Division Malakand | 0.35 | 0.341 | 1.88 | [5 empty] | Not yet started
96 | Clearance of Shergarh Minor from Head to Rd:12+000 in reaches. | Malakand Irrigation Division Malakand | 0.15 | 0.146 | 7.752 | [5 empty] | Not yet started
97 | Clearance of Shergarh Minor from Rd:12+000 tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 7.752 | 1195.13 | 6000 | 5500 | 956.83 | 91.66% | Work in Progress
98 | Clearance of Spokanda Disty from RD: 18000 to Tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 5.659 | [5 empty] | Not yet started
99 | Silt & Shingle Clearance of Spokanda Disty from 0-18000 | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.488 | 771.85 | 2.743 | 1.1 |  | 40% | Work in Progress
100 | Mansehra Irrigation Division Mansehra
101 | Silt Clearance of Lower Siran Canal RD 0-14000 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3110.16 | 3.04 | 0.8839 | 1605.93 | 52% | In progress
102 | Silt Clearance of Lower Siran Canal RD 14000-36500 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3142.51 | 4.26 | 1.1124 | 1265.27 | 40% | In progress
103 | Silt Clearance of Lower Siran Canal Hathi Maira Branch & Gandian Minor RD 36500 in reaches | Mansehra Irrigation Division Mansehra | 0.55 | 0.4954 | 26.21 | 2080.06 | 12.1 | 3.2765 | 1108.28 | 53% | In progress
104 | Silt Clearance of Upper Siran Canal from RD 0-30000 In reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2065 | 3.048 | 0.3048 | 206.49 | 10% | In progress
105 | Silt Clearance of Upper Siran Canal from RD 30000-61000 in reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2110 | 9.44 | 3.0432 | 680 | 32% | In progress
106 | Silt Clearance of Upper Siran Canal from RD 61000-tail in reaches | Mansehra Irrigation Division Mansehra | 0.18 | 0.1623 | 23.86 | 930 | 5.27 | 0.7916 | 139.75 | 15% | In progress
107 | Silt Clearance of Dhodial Minor Upper Siran Canal in reaches | Mansehra Irrigation Division Mansehra | 0.22 | 0.1981 | 5.24 | 1135 | 5.24 | 2.1228 | 458 | 40% | In progress
108 | Jue Shiekh Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 16.29 | 13.03 | 53.35 | 132353 | 53.35 | 40.1 | 99482 | 75% | Work is in progress
109 | Jue Zardad Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 3.6 | 2.88 | 13.1 | 18500 | 13.1 | 11.5 | 16240 | 88% | Work is in progress
110 | Kabul River Canal | Peshawar Canal Division, Peshawar (Kabaul River Canal Sub Division) | 27.855 | 22.284 | 60.35 | 1062085 | 60.35 | 27 | 475190 | 45% | Work is in progress
111 | Hazar Khwani Branch | Peshawar Canal Division, Peshawar (Kabul River Canal Sub Division) | 23.2 | 18.56 | 28.04 | 1016303 | 28.04 | 21.2 | 768389 | 76% | Work is in progress
112 | Swabi Irrigation Division-II Swabi
113 | Clearance of Topi Lift Irrigation Channels RD;00-Tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 4.88 | 1161.77 | 4.87 | 2.44 | 889.64 | 50% | Work in progress
114 | Clearance of Topi & Zarobi Minors from RD;00 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | Topi =4.24 Zarobi =4.27 | 1159.72 | 3.05 | 2.44 | 900.47 | 80% | Work in progress
115 | Clearance/Repair of Badri Lift Irrigation Scheme | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 0.34 | 607.12 | 0.33 | 0.33 | 607.12 | 100% | Competed
116 | Clearance of Kotha Disty; from RD;00 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.24 | 0.24 | 17.53 | 1389.07 | 1.89 | 1.89 | 1389.07 | 100% | Competed
117 | Clearance of Pehur main Canal from RD;46000 to RD;54000 | Swabi Irrigation Division-II Swabi | 0.18 | 0.18 | 51.4 | 1042.24 | 0.53 | 0.53 | 1042.24 | 100% | Competed
118 | Clearance of Pehur Main Canal from RD;54500 to RD;66000 | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 51.4 | 1130.88 | 0.55 | 0.43 | 894.59 | 78% | Work in progress
119 | Clearance of Pehur Main Canal from RD;66000 to RD;85000 | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.92 | 0.7 | 0.61 | 1101.73 | 87% | Work in progress
120 | Clearance of Pehur Main Canal RD;85000 to RD;93000 | Swabi Irrigation Division-II Swabi | 0.16 | 0.16 | 51.4 | 976.63 | 0.63 | 0.46 | 695.7 | 72% | Work in progress
121 | Clearance of Pehur Main Canal from RD;93500 to RD;98000 | Swabi Irrigation Division-II Swabi | 0.17 | 0.17 | 51.4 | 1033.5 | 0.32 | 0.16 | 516.75 | 50% | Work in progress
122 | Clearance of Pehur Main Canal from RD;98500 to RD;113000 | Swabi Irrigation Division-II Swabi | 0.18 | 0.18 | 51.4 | 1094.71 | 0.61 | 0.46 | 792.24 | 75% | Work in progress
123 | Clearance of Kaddi, Zaida, Zakarriya & Sheikhdheri Minors from RD;00 to Tail | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | Kaddi= 5.79 Zaida= 3.81 Zakary=3.43 S/Dher=2.95 | 1292.45 | 0.39 | 0.2 | 702.12 | 50% | Work in progress
124 | Clearance of Pehur Main Canal System from RD;113000 to RD;117000 | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 51.4 | 883 | 0.4 | 0.3 | 685.62 | 77% | Work in progress
125 | Clearance of Pehur Main Canal System from RD;117000 to RD;122000 | Swabi Irrigation Division-II Swabi | 0.12 | 0.12 | 51.4 | 729.53 | 0.22 | 0.11 | 364.76 | 50% | Work in progress
126 | Clearance of Pehur main Canal System from RD;122000 to RD;133000 | Swabi Irrigation Division-II Swabi | 0.13 | 0.13 | 51.4 | 790.91 | 0.4 | 0.34 | 649.45 | 85% | Work in progress
127 | Clearance of flood deposition from the bed of PMC from RD;13300 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 67.38 | 0.02 | 0.01 | 8.95 | 50% | Work in progress
128 | Clearance of PMC System from RD;133000 to 140000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 51.4 | 1738.06 | 0.85 | 0.85 | 1738.06 | 100% | Competed
129 | Clearance of PMC Systems from RD;145000 to RD;150000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.23 | 0.23 | 51.4 | 1332.82 | 0.41 | 0.2 | 666.41 | 50% | Work in progress
130 | Clearance of PMC System from RD;150500 to RD;162000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.81 | 0.44 | 0.22 | 988.94 | 50% | Work in progress
131 | Clearance of PMC System from RD;162100 to Tail & other allied Branches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.85 | 3.23 | 2.59 | 1191.93 | 80% | Work in progress
132 | Clearance of Thanodher Disty: & Bazar Minor from RD;00 to Tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | Thano=6.00 Bazar=7.47 | 1157.95 | 0.35 | 0.18 | 844.83 | 50% | Work in progress
133 | Clearance of flood deposition and silt clearance of ¦Indus Branch RD:74500 Tail in reaches. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 18.54 | 4478 | 11.89 | 8.69 | 3001.26 | 73% | Work in progress
134 | Silt Clearance of Dagi Minor from RD:0- 37000 in reaches i/c repair to out lets & other allied structures. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 11.28 | 4482 | 9.15 | 4.05 | 1982.19 | 44% | Work in progress
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086

## 06-02-2023
S# | Name of Canal | Name of Division | Estimated Cost(RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Total Quantity of Silt to be removed (m3) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Total Quantity of Silt removed till date (m3) | Progress Till date in % | Remarks
1 | Warsak Gravity Canal | Warsak Canals Division Peshawar | 18.8 | 16.2 | 68.88 | 23089.8 | 61.26 | 41.45 | 15622.95 | 68% | Work is in progress
2 | Warsak Minor | Warsak Canals Division Peshawar | 0.8 | 0.736 | 5.85 | 873 | 5.85 | 1.52 | 227.34 | 26% | Work is in progress
3 | Kafoor Dheri Minor | Warsak Canals Division Peshawar | 0.4 | 0.368 | 0.94 | 900 | 0.94 | 0.85 | 812.9 | 90% | Work is in progress
4 | Shahi Bala Minor | Warsak Canals Division Peshawar | 0.4 | 0.368 | 1.07 | 995 | 1.07 | 0.15 | 142.14 | 14% | Work is in progress
5 | Mullazai Minor | Warsak Canals Division Peshawar | 0.3 | 0.552 | 3.35 | 1670 | 3.35 | 1.07 | 531.36 | 32% | Work is in progress
6 | Tehkal Minor | Warsak Canals Division Peshawar | 0.6 | 0.552 | 0.99 | 360 | 0.99 | 0.24 | 88.62 | 25% | Work is in progress
7 | Palosai Minor | Warsak Canals Division Peshawar | 0.5 | 0.46 | 0.66 | 455 | 0.66 | 0.12 | 84.65 | 19% | Work is in progress
8 | Surizai Minor | Warsak Canals Division Peshawar | 0.4 | 0.368 | 3.02 | 1039 | 3.02 | 0.87 | 299.11 | 29% | Work is in progress
9 | Urmar Minor | Warsak Canals Division Peshawar | 0.8 | 0.736 | 6.71 | 1490 | 6.71 | 3.35 | 745 | 50% | Work is in progress
10 | Pabbi Minor | Warsak Canals Division Peshawar | 0.4 | 0.368 | 2.44 | 694 | 2.44 | 2.29 | 650.63 | 94% | Work is in progress
11 | Warsak Lift Canal | Warsak Canals Division Peshawar | 8.39 | 6.5 | 46.63 | 7487.19 | 29.56 | 10.67 | 2701.56 | 36% | Work is in progress
12 | Regi Minor | Warsak Canals Division Peshawar | 0.13 | 0.15 | 0.91 | 270 | 0.91 | 0 | 0 | 0% | Work is in progress
13 | Badabher Minor | Warsak Canals Division Peshawar | 0.26 | 0.29 | 5.49 | 530 | 5.49 | 1.07 | 103.06 | 19% | Work is in progress
14 | Warsak Left Bank Canal | Warsak Canals Division Peshawar | 1.69 | 1.554 | 19.29 | 6837.96 | 13.2 | 3.66 | 1895.05 | 28% | Work is in progress
15 | Periodical silt clearance of Fore Bay and Feeder Channel Of WPH, Sump Well, Sedimenattion Tank & Raising Main | Warsak Canals Division Peshawar | 2.2 | 1.9 | 3.22 | 4500 | 3.22 | 0 | 0 | 0% | Work is in progress
16 | Jue Shiekh Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 16.29 | 13.03 | 53.35 | 132353 | 53.35 | 43 | 106676 | 81% | Work is in progress
17 | Jue Zardad Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 3.6 | 2.88 | 13.1 | 18500 | 13.1 | 12.3 | 17370 | 94% | Work is in progress
18 | Kabul River Canal | Peshawar Canal Division, Peshawar (Kabaul River Canal Sub Division) | 27.855 | 22.284 | 60.35 | 1062085 | 60.35 | 30.6 | 538549 | 51% | Work is in progress
19 | Hazar Khwani Branch | Peshawar Canal Division, Peshawar (Kabul River Canal Sub Division) | 23.2 | 18.56 | 28.04 | 1016303 | 28.04 | 23.7 | 859001 | 85% | Work is in progress
20 | Nipki Khel Irrigation Scheme | Swat Irrigation Division -I | 2.2 | 1.76 | 38.87 | 10172.62 | 38.87 | 17.378 | 4853.5 | 44.71% | Work is in progress
21 | Silt Clearance of Badwan Kharif Irrigation Scheme at RD 0+00 To Tail. | Chakdara Irrigation Sub Division ,Dir Division | 0.9 | 0.8957 | 22.18 | 4635.35 | 22.18 | 6.858 | 1869.42 | 40.32% | Work is in progress
22 | Silt clearance/removal of heaps of Disty No. 9 RD; 41000 to 85500 | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 13.41 | 599.93 | 1 | 0.97 | 581.93 | 97% | In progress
23 | Silt clearance of Power House Minor RD 0 to tail | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 1.28 | 599.9 | 1.28 | 0.97 | 454.61 | 76% | The canal passing through thickly populated area of Mardan City and the adjacenet locals are throwing garbages into the canal, therefore, it is expedient to clear the remaining portion exact at the end of closure period.
24 | Silt clearance of conduit covering portion of 2/9 Hoti Minor RD 4200 to 5000, 5800 to 7000 & 7200 to 7500 | Mardan Irrigation Division Mardan | 0.7 | 0.4546 | 0.7 | 745.53 | 0.7 | 0.48 | 511.22 | 69% | ..do…
25 | Silt clearance of 2/9 Hoti Minor RD 0 to 4200, 5000 to 5800 & 7500 to 19000 | Mardan Irrigation Division Mardan | 0.8 | 0.5195 | 5.94 | 921.08 | 2.43 | 1.47 | 557.2 | 60% | ..do…
26 | Silt clearance /removal of heaps of kalpani disty RD 0-51000 in reaches and clearance of syphones RD 10500 and 15000 | Mardan Irrigation Division Mardan | 0.7 | 0.4544 | 15.6 | 4463.54 | 5.07 | 4.8 | 4225.84 | 95% | In progress
27 | Silt clearance /removal of heaps of 1/kalpani Kodinaka Minor RD 0-27000 in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 8.22 | 599.94 | 1.82 | 1.39 | 458.2 | 76% | The canal passing through thickly populated area of Mardan City and the adjacenet locals are throwing garbages into the canal, therefore, it is expedient to clear the remaining portion exact at the end of closure period.
28 | Silt clearance /removal of heaps of 2/kalpani Taus Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 6.4 | 2801.12 | 5.5 | 5.26 | 2678.89 | 96% | In progress
29 | Silt clearance of 3/9 Toru Minor RD 0 to 15800 | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 4.81 | 2801.12 | 4.81 | 4.68 | 2725.41 | 97% | In progress
30 | Silt clearance of branch 2/kalpani Muhib Banda Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.175 | 0.1308 | 2.89 | 1633.98 | 2 | 1.95 | 1593.13 | 98% | In progress
31 | Silt Clearance of Maho Dheri Minor RD: 4000 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.1493 | 4.57 | 1138.2 | 3.35 | 3.28 | 1114.42 | 98% | In progress
32 | Silt Clearance of Rashakai Minor from RD: 7000 to 31000 in reaches | Mardan Irrigation Division Mardan | 0.6 | 0.3894 | 9.45 | 2972.29 | 7.31 | 7.18 | 2919.43 | 98% | In progress
33 | Silt Clearance of Nowshera Minor RD:0 - tail in reachers | Mardan Irrigation Division Mardan | 0.35 | 0.2613 | 5.18 | 2059.85 | 3.2 | 3.12 | 2008.35 | 98% | In progress
34 | Silt Clearance of Turlandi Minor Head to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 5.27 | 2134.4 | 4.71 | 4.71 | 2134.4 | 100% | Completed
35 | Silt Clearance of Khan Mahi Branch from RD: 0 to 3000 and RD: 8000 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 13.41 | 2344.08 | 5.48 | 5.35 | 2288.47 | 98% | In progress
36 | Silt Clearance of Bara Banda Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 3.04 | 1703.02 | 3.04 | 2.98 | 1669.41 | 98% | In progress
37 | Removal of heaps of Disty No. 8 RD: 52000 to 68000 in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 9.45 | 1860.72 | 1.43 | 1.43 | 1860.72 | 100% | Completed
38 | Silt Clearance/removal of heaps of Disty No. 7 at RD: 4000 to 14000 in reaches | Mardan Irrigation Division Mardan | 0.15 | 0.1133 | 4.26 | 1400.56 | 3.04 | 3.04 | 1400.56 | 100% | Completed
39 | Silt Clearance/removal of heaps of Sheikh yousaf Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 5.48 | 239.97 | 2.13 | 2.08 | 234.34 | 98% | In progress
40 | Silt Clearance/removal of heaps of 1/9 Guide Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 7 | 479.94 | 2.74 | 2.68 | 469.43 | 98% | In progress
41 | Silt Clearance/removal of heaps of Koragh Branch RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 14.93 | 479.94 | 2.23 | 2.23 | 479.94 | 100% | Completed
42 | Removal of heaps of Disty No.8 RD: 0 to 38000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 11.58 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
43 | Removal of heaps of Disty No.9 RD: 0 to 41000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 12.5 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
44 | Swabi Irrigation Division-II Swabi
45 | Clearance of Topi Lift Irrigation Channels RD;00-Tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 4.88 | 1161.77 | 4.87 | 2.44 | 889.64 | 50% | Work in progress
46 | Clearance of Topi & Zarobi Minors from RD;00 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | Topi =4.24 Zarobi =4.27 | 1159.72 | 3.05 | 2.44 | 900.47 | 80% | Work in progress
47 | Clearance/Repair of Badri Lift Irrigation Scheme | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 0.34 | 607.12 | 0.33 | 0.33 | 607.12 | 100% | Competed
48 | Clearance of Kotha Disty; from RD;00 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.24 | 0.24 | 17.53 | 1389.07 | 1.89 | 1.89 | 1389.07 | 100% | Competed
49 | Clearance of Pehur main Canal from RD;46000 to RD;54000 | Swabi Irrigation Division-II Swabi | 0.18 | 0.18 | 51.4 | 1042.24 | 0.53 | 0.53 | 1042.24 | 100% | Competed
50 | Clearance of Pehur Main Canal from RD;54500 to RD;66000 | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 51.4 | 1130.88 | 0.55 | 0.43 | 894.59 | 78% | Work in progress
51 | Clearance of Pehur Main Canal from RD;66000 to RD;85000 | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.92 | 0.7 | 0.61 | 1101.73 | 87% | Work in progress
52 | Clearance of Pehur Main Canal RD;85000 to RD;93000 | Swabi Irrigation Division-II Swabi | 0.16 | 0.16 | 51.4 | 976.63 | 0.63 | 0.46 | 695.7 | 72% | Work in progress
53 | Clearance of Pehur Main Canal from RD;93500 to RD;98000 | Swabi Irrigation Division-II Swabi | 0.17 | 0.17 | 51.4 | 1033.5 | 0.32 | 0.21 | 689 | 67% | Work in progress
54 | Clearance of Pehur Main Canal from RD;98500 to RD;113000 | Swabi Irrigation Division-II Swabi | 0.18 | 0.18 | 51.4 | 1094.71 | 0.61 | 0.46 | 792.24 | 75% | Work in progress
55 | Clearance of Kaddi, Zaida, Zakarriya & Sheikhdheri Minors from RD;00 to Tail | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | Kaddi= 5.79 Zaida= 3.81 Zakary=3.43 S/Dher=2.95 | 1292.45 | 0.39 | 0.2 | 702.12 | 50% | Work in progress
56 | Clearance of Pehur Main Canal System from RD;113000 to RD;117000 | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 51.4 | 883 | 0.4 | 0.3 | 685.62 | 77% | Work in progress
57 | Clearance of Pehur Main Canal System from RD;117000 to RD;122000 | Swabi Irrigation Division-II Swabi | 0.12 | 0.12 | 51.4 | 729.53 | 0.22 | 0.15 | 486.35 | 67% | Work in progress
58 | Clearance of Pehur main Canal System from RD;122000 to RD;133000 | Swabi Irrigation Division-II Swabi | 0.13 | 0.13 | 51.4 | 790.91 | 0.4 | 0.34 | 649.45 | 85% | Work in progress
59 | Clearance of PMC System from RD;133000 to 140000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 51.4 | 1738.06 | 0.85 | 0.85 | 1738.06 | 100% | Competed
60 | Clearance of PMC Systems from RD;145000 to RD;150000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.23 | 0.23 | 51.4 | 1332.82 | 0.41 | 0.2 | 666.41 | 50% | Work in progress
61 | Clearance of PMC System from RD;150500 to RD;162000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.81 | 0.44 | 0.22 | 988.94 | 50% | Work in progress
62 | Clearance of PMC System from RD;162100 to Tail & other allied Branches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.85 | 3.23 | 2.59 | 1191.93 | 80% | Work in progress
63 | Clearance of Thanodher Disty: & Bazar Minor from RD;00 to Tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | Thano=6.00 Bazar=7.47 | 1157.95 | 0.35 | 0.18 | 844.83 | 50% | Work in progress
64 | Clearance of flood deposition and silt clearance of ¦Indus Branch RD:74500 Tail in reaches. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 18.54 | 4478 | 11.89 | 8.69 | 3001.26 | 73% | Work in progress
65 | Silt Clearance of Dagi Minor from RD:0- 37000 in reaches i/c repair to out lets & other allied structures. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 11.28 | 4482 | 9.15 | 6.89 | 3539.62 | 75% | Work in progress
66 | Silt Clearance of Dandoka Minor from RD:0-Tail in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.03 | 0 | 0 | 0 | 0 |  | contractor deployed
67 | Silt Clearance of Sudher Minor RD:0 - tail in reaches & other allied structures | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 2.29 | 0 | 0 | 0 | 0 |  | contractor deployed
68 | Silt Clearance of Yar Hussain Minor RD;0-tail | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 6.8 | 2803.37 | 5.79 | 1.22 | 622.97 | 21% | Work in progress
69 | Silt Clearance of Ghazi Kot Minor from RD: 0-tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.95 | 0 | 0 | 0 | 0 |  | contractor deployed
70 | Silt Clearance Daulat Minor and Gidar Minor RD; 0-tail in reaches & other allied structures | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 16.84 | 4482 | 13.11 | 13.08 | 4308.54 | 100% | Competed
71 | Silt Clearance of Pirsabaq Disty and pirsabaq Minor from Rd:0-tail in reaches. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 11.75 | 4946.41 | 14.21 | 10.67 | 3984.01 | 75% | Work in progress
72 | Silt Clearance of Chowky Disty, Chowki Minor 1 and 2 from RD: 00 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 8.23 | 3710.22 | 11.1 | 6.16 | 2766.7 | 55% | Work in progress
73 | Silt Clearance of Gumbat Minor No.1 & Gumbat Branch from RD:0+0 to tail in reaches., | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 5.18 | 3096.09 | 6.46 | 4.57 | 2731.49 | 71% | Work in progress
74 | Silt Clearance of Misri Banda from RD;0 to tal in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.73 | 2472.77 | 5.4 | 3.96 | 2063.58 | 73% | Work in progress
75 | Silt Clearance of Ambar Branch from RD;0+0 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.35 | 0.35 | 7.88 | 0 | 0 | 0 | 0 |  | contractor deployed
76 | Silt Clearance of Jehangira Minor & Nandrak Minor from RD;0-tail in reaches and repair to allied structures | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 11.52 | 0 | 0 | 0 | 0 |  | contractor deployed
77 | Silt Clearance of Thanodher Minor & Manki Minor from RD;0-tail in reaches | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 12.42 | 1090.2 | 5.18 | 3.66 | 757.4 | 71% | Work in progress
78 | Silt Clearance of Yaqubi Minor, Sard China Minor and Naik Nam Minor from RD; 0-tail | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 10.46 | 1684.86 | 7.44 | 1.83 | 382.27 | 25% | Work in progress
79 | Silt Clearance of Dagi Disty & repair to allied structures Rd 0 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 3.23 | 0 | 0 | 0 | 0 |  | contractor deployed
80 | Silt Clerance of Gumbat Minor No 2 | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 4.57 | 1855.74 | 4.12 | 2.13 | 953.14 | 52% | Work in progress
81 | Silt Clearance and repair of Link Channel, Lahor Minor ,Zakaria Minor Sheik Dheri from RD; 0- to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 8.19 | 948.62 | 1.52 | 1.52 | 948.62 | 100% | Competed
82 | Silt Clerance of Toru Minor | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 4.57 | 0 | 0 | 0 | 0 |  | contractor deployed
83 | Repair clearance of Sypon Rd 6200 & 8000 Pir Sabaq Disty | Swabi Irrigation Division-II Swabi | 0.1 | 0.1 | 0.06 | 0 | 0 | 0 | 0 |  | contractor deployed
84 | Repair clearance of Sypon Rd 200 Gidar Minor | Swabi Irrigation Division-II Swabi | 0.05 | 0.05 | 0.05 | 0 | 0 | 0 | 0 |  | contractor deployed
85 | Clearance and dewatering of Syphons & repair to out lets Jaggan Nath Section. | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 0.15 | 0 | 0 | 0 | 0 |  | contractor deployed
86 | Shamizai Irrigation Canal | Swat Irrigation Division-II Matta | 1 | 0.779 | 20.73 | 5150 | 19.5 | 19.2 | 5071 | 98% | Work is in progress
87 | Barwai Irrigation Canal | Swat Irrigation Division-II Matta | 0.3 | 0.2805 | 11.22 | 1300 | 6.1 | 6.1 | 1300 | 100% | Completed
88
89 | Desiltation / berm cutting/Jungle clearance of Disty No.04, RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 10.11 | 5964.26 | 5.64 | 3.21 | 3399.63 | 57% | yet to be started
90 | Desiltation / berm cutting/Jungle clearance of Disty No.5 & its Minor and sub Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 26.31 | 7688.07 | 8.2 | 3.28 | 3075.25 | 40% | yet to be started
91 | Desiltation / berm cutting/Jungle clearance of Dera Disty RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 16.7 | 5812.06 | 6.55 | 4.26 | 3777.84 | 65% | work in progress
92 | Silt clearance/ jungle clearance of Muryali Minor RD. 00-15000 in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.64 | 4021.01 | 5.33 | 0 | 0 | 0% | yet to be started
93 | Silt clearance/ jungle clearance including removal of debris of Lachra Minor/Makali Minor in reaches. | CRBC Irrigation Division DIKhan | 0.25 | 0.23 | 3.92 | 2402.7 | 11.3 | 0 | 0 | 0% | yet to be started
94 | Desiltation / berm cutting/Jungle clearance of Mehmood Disty. RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.05 | 5737.19 | 4.42 | 2.65 | 3442.31 | 60% | yet to be started
95 | Desiltation / berm cutting/Jungle clearance of Nawab Minor RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.3 | 0.27 | 7.62 | 2952 | 2.59 | 1.63 | 1859.76 | 63% | work in progress
96 | Desiltation / berm cutting/Jungle clearance of Disty No.7, i/c Minors of Disty No.7 RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 30.53 | 7801.33 | 15.37 | 6.15 | 3120.53 | 40% | work in progress
97 | Desiltation / berm cutting/Jungle clearance of Disty No. 8 & 8-A, RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.29 | 3999 | 3.95 | 3.3 | 3399.1 | 85% | work in progress
98 | Desiltation / berm cutting/Jungle clearance of Disty No.9 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.71 | 3560.86 | 2.9 | 1.45 | 1780.43 | 5% | yet to be started
99 | Desiltation / berm cutting/Jungle clearance of Disty No.10 & 10/A RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11 | 3950.22 | 3.19 | 0 |  | 0% | yet to be started
100 | Desiltation / berm cutting/Jungle clearance of Disty No. 11 & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 9.1 | 5670.47 | 10.66 | 4.26 | 2268.19 | 40% | yet to be started
101 | Desiltation / berm cutting/Jungle clearance of Disty No. 11-A, & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 21.86 | 7695.14 | 5.93 | 0 |  | 10% | yet to be started
102 | Desiltation / berm cutting/Jungle clearance of Disty No. 12 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.23 | 5762.51 | 4.11 | 2.9 | 4033.76 | 70% | work in progress
103 | Desiltation /Jungle Clearance of Disty # 13 & its System RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.675 | 0.6075 | 21.655 | 4256.03 | 4.66 | 3.96 | 3618 | 85% | Work is in progress.
104 | Shingling of CPR & Jungle Clearance of Disty # 14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.725 | 0.6525 | 21.616 | 4176.75 | 4.58 | 3.66 | 3341 | 80% | Work is in progress.
105 | Shingling of CPR & Jungle Clearance of MD-14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.433 | 2145.01 | 2.43 | 1.82 | 1609 | 75% | Work is in progress.
106 | Shingling of CPR & Jungle Clearance of Disty # 15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.7 | 0.63 | 21.494 | 3752 | 3.65 | 1.09 | 1126 | 30% | Work not yet started.
107 | Shingling of CPR & Jungle Clearance of MD-15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.325 | 0.2925 | 5.8384 | 1862.55 | 2.28 | 0 |  | 0% | Work not yet started.
108 | Shingling of CPR & Jungle Clearance of Disty 16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 12.75 |  | 2.43 | 0 |  | 0% | Work not yet started.
109 | Shingling of CPR & Jungle Clearance of Minor of Disty-16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.8445 |  | 2.45 | 0 |  | 0% | Work not yet started.
110 | Desiltation / Jungle Clearance of Disty # 17 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 9.6951 |  | 2.13 | 0 |  | 0% | Work not yet started.
111 | Shingling of CPR & Jungle Clearance of Disty # 18 its Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 18.009 |  | 4.26 | 0 |  | 0% | Work not yet started.
112 | Shingling of CPR & Jungle Clearance of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.55 | 0.495 | 15.753 |  | 3.96 | 0 |  | 0% | Work not yet started.
113 | Desiltation / Jungle Clearance of M-1 & M-2 of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.829 |  | 4 | 0 |  | 0% | Work not yet started.
114 | Silt Clearance of Lower Siran Canal RD 0-14000 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3110.16 | 3.04 | 1.0058 | 1639.91 | 53% | In progress
115 | Silt Clearance of Lower Siran Canal RD 14000-36500 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3142.51 | 4.26 | 1.1886 | 1286.5 | 41% | In progress
116 | Silt Clearance of Lower Siran Canal Hathi Maira Branch & Gandian Minor RD 36500 in reaches | Mansehra Irrigation Division Mansehra | 0.55 | 0.4954 | 26.21 | 2080.06 | 12.1 | 3.3679 | 1133.76 | 55% | In progress
117 | Silt Clearance of Upper Siran Canal from RD 0-30000 In reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2065 | 3.048 | 0.381 | 227.72 | 11% | In progress
118 | Silt Clearance of Upper Siran Canal from RD 30000-61000 in reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2110 | 9.44 | 3.287 | 747.96 | 35% | In progress
119 | Silt Clearance of Upper Siran Canal from RD 61000-tail in reaches | Mansehra Irrigation Division Mansehra | 0.18 | 0.1623 | 23.86 | 930 | 5.27 | 0.944 | 182.22 | 20% | In progress
120 | Silt Clearance of Dhodial Minor Upper Siran Canal in reaches | Mansehra Irrigation Division Mansehra | 0.22 | 0.1981 | 5.24 | 1135 | 5.24 | 2.3056 | 508.97 | 45% | In progress
121 | Removal of Heaps / Clearance of Bari Band Disty RD: 39+500-88+600 in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.33775 | 14.96 | 1435.76 | 8.21 | 6 | 1300 | 73.08% | Work in Progress
122 | Removal of Heaps / Clearance of Hero Shah Minor RD: 0 -38+000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 11.58 | 2446.93 | 11.58 | 9 | 1800 | 77.72% | Work in Progress
123 | Removal of Heaps / Clearance of Kalu Shah Disty and Dundian Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.1 | 0.098 | 7.69 | 785.8 | 5 | 5 | 785.8 | 100% | Completed
124 | Removal of Heaps / Clearance of Sarwala Disty and Lund Khwar Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 18.29 | 3172.99 | 10.06 | 8.5 | 2500 | 84.49% | Work in Progress
125 | Removal of Heaps / Clearance of Said Abad Disty and Pir Abad Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 20.42 | 3113.1 | 7.31 | 6.5 | 2650 | 88.91% | Work in Progress
126 | Removal of Heaps / Clearance of Katlang Disty from RD: 0-40+000 in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 12.19 | 1910.43 | 7.61 | 6.5 | 1700 | 85.41% | Work in Progress
127 | Removal of Heaps / Clearance of Shamozai Disty/ Syphon and Likpani Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.392 | 17.67 | 2730.62 | 13.01 | 9.5 | 2200 | 73.02% | Work in Progress
128 | Removal of Heaps / Clearance of Dheri Minor and Tail Minor Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.15 | 0.147 | 7.01 | 1211.68 | 6 | 5.75 | 1150 | 95.83% | Work in Progress
129 | Bazai Main Canal Head Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 21 | 21 | 1168.075 | 100% | Completed
130 | Wartair Disty | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 6 | 587.93 | 6 | 6 | 587.93 | 100% | Completed
131 | Kharki Disty No. 02 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 3.3 | 1272.34 | 3.3 | 3.3 | 1272.34 | 100% | Completed
132 | Additional Minor No. 03, 06 and Bazai Disty No. 01. | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | 16.8 | 1272.14 | 16.8 | 3 | 1272.14 | 100% | Completed
133 | Bazai Main Canal, Syphon No. 4431, 5851, 12530, 13590, 14842, 18400, 47527 & 58853 | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | [5 empty] | 70% | Work in Progress
134 | Bazai Disty No. 04, Bazai Minor No. 09, 11 and 12. | Malakand Irrigation Division Malakand | 0.27 | 0.26625 | 15.2 | 4070 | 9 | 9 | 4070 | 100% | Completed
135 | Clearance of Syphon 79205, 93480 and 97962. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | [5 empty] | 20% | Work in Progress
136 | Bazai Disty No. 03 and Bazai Minor No. 05. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | 20.5 | 1907.82 | 20.5 | 7 | 1907.82 | 100% | Completed
137 | Bazai Main Canal Tail Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 0 | 0 | 0 | 0% | Not Yet start
138 | KM-1 RD: 0-2976 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 143.26 | 0.9 | 0.9 | 143.26 | 100% | Completed
139 | KM-1 RD: 0-1500, 22000-29000 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 410.62 | 2.6 | 2.6 | 410.62 | 100% | Completed
140 | Bazai Main Canal RD: 79500 to RD: 84500 | Malakand Irrigation Division Malakand | 0.302 | 0.296 |  | 649.87 | 1.5 | 0.9 | 389.92 | 60% | Work in Progress
141 | Silt & Shingle Clearance of P.C Minor from RD 0+000 To Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.388 | 12.881 | 1851.77 | 7.62 | 1.2 | 372.84 | 15.74% | Work in Progress
142 | Clearance of Shingri Minor from RD 0-17250 in reaches. | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.309 | 530.92 | 2.347 | 1.906 | 259.19 | 81.21% | Work in Progress
143 | Clearance of Meherdi Minor from RD 0-31000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 9.451 | 2167.5 | 8.382 | 6.113 | 804.63 | 72.93% | Work in Progress
144 | Clearance of Kalu Branch from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.33 | 0.3218 | 11.563 | [5 empty] | Not yet started
145 | Clearance of Hathian Minor from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.05 | 0.04875 | 2.35 | [5 empty] | Not yet started
146 | Clearance of Jalala Disty from RD: 29000 to Tail in reaches | Malakand Irrigation Division Malakand | 0.37 | 0.3607 | 14.024 | 1476.73 | 5900 | 5400 | 1113.71 | 91.52% | Work in Progress
147 | Clearance of Pirsaddo Disty, Ghano Minor and Qutab Gharh Minor from : H-Tail to Tail in reaches. | Malakand Irrigation Division Malakand | 0.35 | 0.341 | 1.88 | [5 empty] | Not yet started
148 | Clearance of Shergarh Minor from Head to Rd:12+000 in reaches. | Malakand Irrigation Division Malakand | 0.15 | 0.146 | 7.752 | [5 empty] | Not yet started
149 | Clearance of Shergarh Minor from Rd:12+000 tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 7.752 | 1195.13 | 6000 | 5500 | 956.83 | 91.66% | Work in Progress
150 | Clearance of Spokanda Disty from RD: 18000 to Tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 5.659 | [5 empty] | Not yet started
151 | Silt & Shingle Clearance of Spokanda Disty from 0-18000 | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.488 | 771.85 | 2.743 | 1.1 |  | 40% | Work in Progress
152 | Silt clearance from RD:0+00 to RD:8+000 in reaches of Ghazai Khani Flow Irrigation Scheme | Swat Irrigation Division -I | 0.24 | 0.213 | 2.438 | 1339.39 | 2.44 | 2.2 | 740 | 55.25% | Work in Progress
153 | "Silt clearance from RD:0+00 to RD:12+000 in reaches of Karshalizara Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.1199 | 3.657 | 613 | 3.66 | 2.5 | 490 | 79.93% | Work in Progress
154 | "Silt clearance from RD:0+00 to RD:20+000 in reaches of Charorai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.15 | 0.135 | 6.096 | 766.25 | 6.1 | 4.7 | 695 | 90.7% | Work in Progress
155 | "Silt clearance from RD:0+00 to RD:12+000 in reaches of Kuriya Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.25 | 0.225 | 3.657 | 1397.44 | 3.66 | 2.8 | 785 | 56.17% | Work in Progress
156 | "Silt clearance from RD:0+00 to RD:9+000 in reaches of Elai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 2.743 | 613 | 2.74 | 2.3 | 365 | 59.54% | Work in Progress
157 | "Silt clearance from RD:0+00 to RD:60+000 in reaches of Budal Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 18.287 | 672.53 | 9.14 | 6.1 | 355 | 52.79% | Work in Progress
158 | "Silt clearance from RD:0+00 to RD:16+000 in reaches of Singarai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 4.267 | 669.7 | 4.27 | 2.9 | 365 | 54.5% | Work in Progress
159 | "Silt clearance from RD:0+00 to RD:26+000 in reaches of Bajkata Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.24 | 0.216 | 7.924 | 408.66 | 7.92 | 4.7 | 295 | 72.19% | Work in Progress
160 | Silt clearance from RD:0+00 to RD:34+000 in reaches of Gagra Flow Irrigation Scheme | Swat Irrigation Division -I | 0.5 | 0.4 | 10.363 | 2797 | 9.75 | 5.3 | 1810 | 64.71% | Work in Progress
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086

## 07-02-2023
S# | Name of Canal | Name of Division | Estimated Cost(RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Total Quantity of Silt to be removed (m3) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Total Quantity of Silt removed till date (M3) | Progress Till date in % | Remarks
1 | Barwai Irrigation Canal | Swat Irrigation Division-II Matta | 0.3 | 0.2805 | 11.22 | 1300 | 6.1 | 6.1 | 1300 | 100% | Completed
2 | Shamizai Irrigation Canal | Swat Irrigation Division-II Matta | 1 | 0.779 | 20.73 | 5150 | 19.5 | 19.5 | 5150 | 100% | Completed
3
4 | Swabi Irrigation Division-I Swabi
5 | Shahbaz Garhi Sub Division
6 | Clearance from the bed of Jamal Garhi Disty from 00-tail in reaches. | Swabi Irrigation Division-I Swabi | 0.3 | 0.11 | 16.81 | 1692.37 | 4.7 | 4.3 | 1556.98 | 92% | In-Progress
7 | Silt Clearance from the bed of Buxali Disty & Kot Minor from 00-tail in reaches | Swabi Irrigation Division-I Swabi | 0.65 | 0.36 | 21.34 | 4715.26 | 9.42 | 7.5 | 4243.73 | 90% | In-Progress
8 | Removal of debris and heaps from Machai Branch RD 105+000 to 142+000 in reaches | Swabi Irrigation Division-I Swabi | 0.35 | 0.13 | 247.58 | 4521.89 | 0.48 | 0.3 | 3617.51 | 80% | In-Progress
9 | Removal of debris and heaps from Machai Branch RD 142+000 to 186+000 in reaches | Swabi Irrigation Division-I Swabi | 0.35 | 0.13 | 247.58 | 4513.02 | 0.35 | 0.3 | 4332.5 | 96% | In-Progress
10 | Silt Clearance from the bed of Chura Minor , Sawal Dher Minor & Mala Minor from RD: 00-tail in reaches. | Swabi Irrigation Division-I Swabi | 0.3 | 0.11 | 14.38 | 1698.88 | 7 | 5.4 | 1579.96 | 93% | In-Progress
11 | Silt clearance from the bed Shahbaz Garhi Disty and its sub System from RD:00-tail in reaches | Swabi Irrigation Division-I Swabi | 0.8 | 0.44 | 18.29 | 4522.69 | 14.85 | 12.5 | 4070.42 | 90% | In-Progress
12 | Silt Clearance from the bed of Ismalia Disty and its sub system from 00-tail in reaches | Swabi Irrigation Division-I Swabi | 0.9 | 0.5 | 18.29 | 6469.09 | 13.26 | 11.7 | 6145.64 | 95% | In-Progress
13 | Silt Clearance from the bed of Adina Minor and adina Minor Branch from Head to tail in reaches | Swabi Irrigation Division-I Swabi | 0.35 | 0.19 | 7.89 | 1980.17 | 5.59 | 4.7 | 1821.76 | 92% | In-Progress
14 | Jue Shiekh Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 16.29 | 13.03 | 53.35 | 132353 | 53.35 | 45.1 | 111886 | 85% | Work is in progress
15 | Jue Zardad Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 3.6 | 2.88 | 13.1 | 18500 | 13.1 | 12.6 | 17794 | 96% | Work is in progress
16 | Kabul River Canal | Peshawar Canal Division, Peshawar (Kabaul River Canal Sub Division) | 27.855 | 22.284 | 60.35 | 1062085 | 60.35 | 34.2 | 601907 | 57% | Work is in progress
17 | Hazar Khwani Branch | Peshawar Canal Division, Peshawar (Kabul River Canal Sub Division) | 23.2 | 18.56 | 28.04 | 1016303 | 28.04 | 25.35 | 918805 | 90% | Work is in progress
18 | Silt clearance/removal of heaps of Disty No. 9 RD; 41000 to 85500 | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 13.41 | 599.93 | 1 | 0.97 | 581.93 | 97% | In progress
19 | Silt clearance of Power House Minor RD 0 to tail | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 1.28 | 599.9 | 1.28 | 1.23 | 576.47 | 96% | The canal passing through thickly populated area of Mardan City and the adjacenet locals are throwing garbages into the canal, therefore, it is expedient to clear the remaining portion exact at the end of closure period.
20 | Silt clearance of conduit covering portion of 2/9 Hoti Minor RD 4200 to 5000, 5800 to 7000 & 7200 to 7500 | Mardan Irrigation Division Mardan | 0.7 | 0.4546 | 0.7 | 745.53 | 0.7 | 0.52 | 553.82 | 74% | ..do…
21 | Silt clearance of 2/9 Hoti Minor RD 0 to 4200, 5000 to 5800 & 7500 to 19000 | Mardan Irrigation Division Mardan | 0.8 | 0.5195 | 5.94 | 921.08 | 2.43 | 1.64 | 621.63 | 67% | ..do…
22 | Silt clearance /removal of heaps of kalpani disty RD 0-51000 in reaches and clearance of syphones RD 10500 and 15000 | Mardan Irrigation Division Mardan | 0.7 | 0.4544 | 15.6 | 4463.54 | 5.07 | 4.8 | 4225.84 | 95% | In progress
23 | Silt clearance /removal of heaps of 1/kalpani Kodinaka Minor RD 0-27000 in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 8.22 | 599.94 | 1.82 | 1.5 | 494.46 | 82% | The canal passing through thickly populated area of Mardan City and the adjacenet locals are throwing garbages into the canal, therefore, it is expedient to clear the remaining portion exact at the end of closure period.
24 | Silt clearance /removal of heaps of 2/kalpani Taus Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 6.4 | 2801.12 | 5.5 | 5.26 | 2678.89 | 96% | In progress
25 | Silt clearance of 3/9 Toru Minor RD 0 to 15800 | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 4.81 | 2801.12 | 4.81 | 4.68 | 2725.41 | 97% | In progress
26 | Silt clearance of branch 2/kalpani Muhib Banda Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.175 | 0.1308 | 2.89 | 1633.98 | 2 | 1.95 | 1593.13 | 98% | In progress
27 | Silt Clearance of Maho Dheri Minor RD: 4000 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.1493 | 4.57 | 1138.2 | 3.35 | 3.28 | 1114.42 | 98% | In progress
28 | Silt Clearance of Rashakai Minor from RD: 7000 to 31000 in reaches | Mardan Irrigation Division Mardan | 0.6 | 0.3894 | 9.45 | 2972.29 | 7.31 | 7.18 | 2919.43 | 98% | In progress
29 | Silt Clearance of Nowshera Minor RD:0 - tail in reachers | Mardan Irrigation Division Mardan | 0.35 | 0.2613 | 5.18 | 2059.85 | 3.2 | 3.12 | 2008.35 | 98% | In progress
30 | Silt Clearance of Turlandi Minor Head to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 5.27 | 2134.4 | 4.71 | 4.71 | 2134.4 | 100% | Completed
31 | Silt Clearance of Khan Mahi Branch from RD: 0 to 3000 and RD: 8000 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 13.41 | 2344.08 | 5.48 | 5.35 | 2288.47 | 98% | In progress
32 | Silt Clearance of Bara Banda Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 3.04 | 1703.02 | 3.04 | 2.98 | 1669.41 | 98% | In progress
33 | Removal of heaps of Disty No. 8 RD: 52000 to 68000 in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 9.45 | 1860.72 | 1.43 | 1.43 | 1860.72 | 100% | Completed
34 | Silt Clearance/removal of heaps of Disty No. 7 at RD: 4000 to 14000 in reaches | Mardan Irrigation Division Mardan | 0.15 | 0.1133 | 4.26 | 1400.56 | 3.04 | 3.04 | 1400.56 | 100% | Completed
35 | Silt Clearance/removal of heaps of Sheikh yousaf Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 5.48 | 239.97 | 2.13 | 2.08 | 234.34 | 98% | In progress
36 | Silt Clearance/removal of heaps of 1/9 Guide Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 7 | 479.94 | 2.74 | 2.68 | 469.43 | 98% | In progress
37 | Silt Clearance/removal of heaps of Koragh Branch RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 14.93 | 479.94 | 2.23 | 2.23 | 479.94 | 100% | Completed
38 | Removal of heaps of Disty No.8 RD: 0 to 38000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 11.58 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
39 | Removal of heaps of Disty No.9 RD: 0 to 41000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 12.5 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
40 | Swabi Irrigation Division-II Swabi
41 | Clearance of Topi Lift Irrigation Channels RD;00-Tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 4.88 | 1161.77 | 2.84 | 1.42 | 1024.71 | 50% | Work in progress
42 | Clearance of Topi & Zarobi Minors from RD;00 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | Topi =4.24 Zarobi =4.27 | 1159.72 | 3.05 | 2.59 | 1025.63 | 85% | Work in progress
43 | Clearance/Repair of Badri Lift Irrigation Scheme | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 0.34 | 607.12 | 0.33 | 0.33 | 607.12 | 100% | Competed
44 | Clearance of Kotha Disty; from RD;00 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.24 | 0.24 | 17.53 | 1389.07 | 1.89 | 1.89 | 1389.07 | 100% | Competed
45 | Clearance of Pehur main Canal from RD;46000 to RD;54000 | Swabi Irrigation Division-II Swabi | 0.18 | 0.18 | 51.4 | 1042.24 | 0.53 | 0.53 | 1042.24 | 100% | Competed
46 | Clearance of Pehur Main Canal from RD;54500 to RD;66000 | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 51.4 | 1130.88 | 0.55 | 0.43 | 894.59 | 78% | Work in progress
47 | Clearance of Pehur Main Canal from RD;66000 to RD;85000 | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.92 | 0.7 | 0.61 | 1205.44 | 87% | Work in progress
48 | Clearance of Pehur Main Canal RD;85000 to RD;93000 | Swabi Irrigation Division-II Swabi | 0.16 | 0.16 | 51.4 | 976.63 | 0.63 | 0.46 | 695.7 | 72% | Work in progress
49 | Clearance of Pehur Main Canal from RD;93500 to RD;98000 | Swabi Irrigation Division-II Swabi | 0.17 | 0.17 | 51.4 | 1033.5 | 0.32 | 0.21 | 689 | 67% | Work in progress
50 | Clearance of Pehur Main Canal from RD;98500 to RD;113000 | Swabi Irrigation Division-II Swabi | 0.18 | 0.18 | 51.4 | 1094.71 | 0.61 | 0.46 | 792.24 | 75% | Work in progress
51 | Clearance of Kaddi, Zaida, Zakarriya & Sheikhdheri Minors from RD;00 to Tail | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | Kaddi= 5.79 Zaida= 3.81 Zakary=3.43 S/Dher=2.95 | 1292.45 | 0.39 | 0.2 | 702.12 | 50% | Work in progress
52 | Clearance of Pehur Main Canal System from RD;113000 to RD;117000 | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 51.4 | 883 | 0.4 | 0.4 | 883 | 100% | Competed
53 | Clearance of Pehur Main Canal System from RD;117000 to RD;122000 | Swabi Irrigation Division-II Swabi | 0.12 | 0.12 | 51.4 | 729.53 | 0.22 | 0.15 | 486.35 | 67% | Work in progress
54 | Clearance of Pehur main Canal System from RD;122000 to RD;133000 | Swabi Irrigation Division-II Swabi | 0.13 | 0.13 | 51.4 | 790.91 | 0.4 | 0.34 | 649.45 | 85% | Work in progress
55 | Clearance of PMC System from RD;133000 to 140000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 51.4 | 1738.06 | 0.85 | 0.85 | 1738.06 | 100% | Competed
56 | Clearance of PMC Systems from RD;145000 to RD;150000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.23 | 0.23 | 51.4 | 1332.82 | 0.41 | 0.2 | 1025.25 | 50% | Work in progress
57 | Clearance of PMC System from RD;150500 to RD;162000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.81 | 0.44 | 0.22 | 1212.64 | 50% | Work in progress
58 | Clearance of PMC System from RD;162100 to Tail & other allied Branches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.85 | 3.23 | 2.96 | 1364.24 | 92% | Work in progress
59 | Clearance of Thanodher Disty: & Bazar Minor from RD;00 to Tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | Thano=6.00 Bazar=7.47 | 1157.95 | 0.35 | 0.18 | 844.83 | 50% | Work in progress
60 | Clearance of flood deposition and silt clearance of ¦Indus Branch RD:74500 Tail in reaches. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 18.54 | 4478 | 11.89 | 8.69 | 3001.26 | 73% | Work in progress
61 | Silt Clearance of Dagi Minor from RD:0- 37000 in reaches i/c repair to out lets & other allied structures. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 11.28 | 4482 | 9.15 | 6.89 | 3539.62 | 75% | Work in progress
62 | Silt Clearance of Dandoka Minor from RD:0-Tail in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.03 | 0 | 0 | 0 | 0 |  | contractor deployed
63 | Silt Clearance of Sudher Minor RD:0 - tail in reaches & other allied structures | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 2.29 | 0 | 0 | 0 | 0 |  | contractor deployed
64 | Silt Clearance of Yar Hussain Minor RD;0-tail | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 6.8 | 2803.37 | 5.79 | 1.22 | 622.97 | 21% | Work in progress
65 | Silt Clearance of Ghazi Kot Minor from RD: 0-tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.95 | 0 | 0 | 0 | 0 |  | contractor deployed
66 | Silt Clearance Daulat Minor and Gidar Minor RD; 0-tail in reaches & other allied structures | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 16.84 | 4482 | 13.11 | 13.08 | 4308.54 | 100% | Competed
67 | Silt Clearance of Pirsabaq Disty and pirsabaq Minor from Rd:0-tail in reaches. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 11.75 | 4946.41 | 14.21 | 10.67 | 3984.01 | 75% | Work in progress
68 | Silt Clearance of Chowky Disty, Chowki Minor 1 and 2 from RD: 00 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 8.23 | 3710.22 | 11.1 | 6.16 | 2766.7 | 55% | Work in progress
69 | Silt Clearance of Gumbat Minor No.1 & Gumbat Branch from RD:0+0 to tail in reaches., | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 5.18 | 3096.09 | 6.46 | 4.57 | 2731.49 | 71% | Work in progress
70 | Silt Clearance of Misri Banda from RD;0 to tal in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.73 | 2472.77 | 5.4 | 3.96 | 2063.58 | 73% | Work in progress
71 | Silt Clearance of Ambar Branch from RD;0+0 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.35 | 0.35 | 7.88 | 0 | 0 | 0 | 0 |  | contractor deployed
72 | Silt Clearance of Jehangira Minor & Nandrak Minor from RD;0-tail in reaches and repair to allied structures | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 11.52 | 0 | 0 | 0 | 0 |  | contractor deployed
73 | Silt Clearance of Thanodher Minor & Manki Minor from RD;0-tail in reaches | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 12.42 | 1090.2 | 5.18 | 3.66 | 757.4 | 71% | Work in progress
74 | Silt Clearance of Yaqubi Minor, Sard China Minor and Naik Nam Minor from RD; 0-tail | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 10.46 | 1684.86 | 7.44 | 1.83 | 382.27 | 25% | Work in progress
75 | Silt Clearance of Dagi Disty & repair to allied structures Rd 0 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 3.23 | 0 | 0 | 0 | 0 |  | contractor deployed
76 | Silt Clerance of Gumbat Minor No 2 | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 4.57 | 1855.74 | 4.12 | 2.13 | 953.14 | 52% | Work in progress
77 | Silt Clearance and repair of Link Channel, Lahor Minor ,Zakaria Minor Sheik Dheri from RD; 0- to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 8.19 | 948.62 | 1.52 | 1.52 | 948.62 | 100% | Competed
78 | Silt Clerance of Toru Minor | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 4.57 | 0 | 0 | 0 | 0 |  | contractor deployed
79 | Repair clearance of Sypon Rd 6200 & 8000 Pir Sabaq Disty | Swabi Irrigation Division-II Swabi | 0.1 | 0.1 | 0.06 | 0 | 0 | 0 | 0 |  | contractor deployed
80 | Repair clearance of Sypon Rd 200 Gidar Minor | Swabi Irrigation Division-II Swabi | 0.05 | 0.05 | 0.05 | 0 | 0 | 0 | 0 |  | contractor deployed
81 | Clearance and dewatering of Syphons & repair to out lets Jaggan Nath Section. | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 0.15 | 0 | 0 | 0 | 0 |  | contractor deployed
82 | Silt Clearance of Badwan Kharif Irrigation Scheme at RD 0+00 To Tail. | Chakdara Irrigation Sub Division ,Dir Division | 0.9 | 0.8957 | 22.18 | 4635.35 | 22.18 | 7.92 | 2147.77 | 46.33% | Work is in progress
83
84 | Desiltation / berm cutting/Jungle clearance of Disty No.04, RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 10.11 | 5964.26 | 5.64 | 3.55 | 3757.48 | 63% | Work is in progress.
85 | Desiltation / berm cutting/Jungle clearance of Disty No.5 & its Minor and sub Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 26.31 | 7688.07 | 8.2 | 3.94 | 3690.27 | 48% | Work is in progress.
86 | Desiltation / berm cutting/Jungle clearance of Dera Disty RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 16.7 | 5812.06 | 6.55 | 4.59 | 4068.44 | 70% | Work is in progress.
87 | Silt clearance/ jungle clearance of Muryali Minor RD. 00-15000 in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.64 | 4021.01 | 5.33 | 0 | 0 | 0% | Work is in progress.
88 | Silt clearance/ jungle clearance including removal of debris of Lachra Minor/Makali Minor in reaches. | CRBC Irrigation Division DIKhan | 0.25 | 0.23 | 3.92 | 2402.7 | 11.3 | 0.57 | 120.14 | 5% | Work is in progress.
89 | Desiltation / berm cutting/Jungle clearance of Mehmood Disty. RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.05 | 5737.19 | 4.42 | 3.09 | 4016.03 | 70% | Work is in progress.
90 | Desiltation / berm cutting/Jungle clearance of Nawab Minor RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.3 | 0.27 | 7.62 | 2952 | 2.59 | 1.81 | 2066.9 | 70% | work in progress
91 | Desiltation / berm cutting/Jungle clearance of Disty No.7, i/c Minors of Disty No.7 RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 30.53 | 7801.33 | 15.37 | 6.92 | 3510.6 | 45% | work in progress
92 | Desiltation / berm cutting/Jungle clearance of Disty No. 8 & 8-A, RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.29 | 3999 | 3.95 | 3.56 | 3599.1 | 90% | work in progress
93 | Desiltation / berm cutting/Jungle clearance of Disty No.9 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.71 | 3560.86 | 2.9 | 0.2 | 249.26 | 7% | yet to be started
94 | Desiltation / berm cutting/Jungle clearance of Disty No.10 & 10/A RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11 | 3950.22 | 3.19 | 0 |  | 0% | yet to be started
95 | Desiltation / berm cutting/Jungle clearance of Disty No. 11 & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 9.1 | 5670.47 | 10.66 | 9.06 | 3402.28 | 60% | yet to be started
96 | Desiltation / berm cutting/Jungle clearance of Disty No. 11-A, & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 21.86 | 7695.14 | 5.93 | 1.18 | 1539.03 | 20% | yet to be started
97 | Desiltation / berm cutting/Jungle clearance of Disty No. 12 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.23 | 5762.51 | 4.11 | 3.49 | 4898.13 | 85% | work in progress
98 | Desiltation /Jungle Clearance of Disty # 13 & its System RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.675 | 0.6075 | 21.655 | 4256.03 | 4.66 | 3.96 | 3618 | 85% | Work is in progress.
99 | Shingling of CPR & Jungle Clearance of Disty # 14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.725 | 0.6525 | 21.616 | 4176.75 | 4.58 | 3.66 | 3341 | 80% | Work is in progress.
100 | Shingling of CPR & Jungle Clearance of MD-14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.433 | 2145.01 | 2.43 | 1.82 | 1609 | 75% | Work is in progress.
101 | Shingling of CPR & Jungle Clearance of Disty # 15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.7 | 0.63 | 21.494 | 3752 | 3.65 | 1.69 | 1688 | 45% | Work is in progress.
102 | Shingling of CPR & Jungle Clearance of MD-15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.325 | 0.2925 | 5.8384 | 1862.55 | 2.28 | 0 |  | 0% | Work not yet started.
103 | Shingling of CPR & Jungle Clearance of Disty 16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 12.75 |  | 2.43 | 0 |  | 0% | Work not yet started.
104 | Shingling of CPR & Jungle Clearance of Minor of Disty-16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.8445 |  | 2.45 | 0 |  | 0% | Work not yet started.
105 | Desiltation / Jungle Clearance of Disty # 17 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 9.6951 |  | 2.13 | 0 |  | 0% | Work not yet started.
106 | Shingling of CPR & Jungle Clearance of Disty # 18 its Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 18.009 |  | 4.26 | 0 |  | 0% | Work not yet started.
107 | Shingling of CPR & Jungle Clearance of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.55 | 0.495 | 15.753 |  | 3.96 | 0 |  | 0% | Work not yet started.
108 | Desiltation / Jungle Clearance of M-1 & M-2 of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.829 |  | 4 | 0 |  | 0% | Work not yet started.
109 | Removal of Heaps / Clearance of Bari Band Disty RD: 39+500-88+600 in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.33775 | 14.96 | 1435.76 | 8.21 | 7.75 | 1375 | 94.4% | Work in Progress
110 | Removal of Heaps / Clearance of Hero Shah Minor RD: 0 -38+000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 11.58 | 2446.93 | 11.58 | 10.5 | 2200 | 90.67% | Work in Progress
111 | Removal of Heaps / Clearance of Kalu Shah Disty and Dundian Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.1 | 0.098 | 7.69 | 785.8 | 5 | 5 | 785.8 | 100% | Completed
112 | Removal of Heaps / Clearance of Sarwala Disty and Lund Khwar Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 18.29 | 3172.99 | 10.06 | 10.06 | 3172.99 | 100% | Completed
113 | Removal of Heaps / Clearance of Said Abad Disty and Pir Abad Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 20.42 | 3113.1 | 7.31 | 7.31 | 3113.1 | 100% | Completed
114 | Removal of Heaps / Clearance of Katlang Disty from RD: 0-40+000 in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 12.19 | 1910.43 | 7.61 | 7.61 | 1910.43 | 100% | Completed
115 | Removal of Heaps / Clearance of Shamozai Disty/ Syphon and Likpani Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.392 | 17.67 | 2730.62 | 13.01 | 13.01 | 2730.62 | 100% | Completed
116 | Removal of Heaps / Clearance of Dheri Minor and Tail Minor Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.15 | 0.147 | 7.01 | 1211.68 | 6 | 6 | 1211.68 | 100% | Completed
117 | Bazai Main Canal Head Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 21 | 21 | 1168.075 | 100% | Completed
118 | Wartair Disty | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 6 | 587.93 | 6 | 6 | 587.93 | 100% | Completed
119 | Kharki Disty No. 02 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 3.3 | 1272.34 | 3.3 | 3.3 | 1272.34 | 100% | Completed
120 | Additional Minor No. 03, 06 and Bazai Disty No. 01. | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | 16.8 | 1272.14 | 3 | 3 | 1272.14 | 100% | Completed
121 | Bazai Main Canal, Syphon No. 4431, 5851, 12530, 13590, 14842, 18400, 47527 & 58853 | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | [5 empty] | 70% | Work in Progress
122 | Bazai Disty No. 04, Bazai Minor No. 09, 11 and 12. | Malakand Irrigation Division Malakand | 0.27 | 0.26625 | 15.2 | 4070 | 9 | 9 | 4070 | 100% | Completed
123 | Clearance of Syphon 79205, 93480 and 97962. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | [5 empty] | 20% | Work in Progress
124 | Bazai Disty No. 03 and Bazai Minor No. 05. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | 20.5 | 1907.82 | 7 | 7 | 1907.82 | 100% | Completed
125 | Bazai Main Canal Tail Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 0 | 0 | 0 | 0% | Not Yet start
126 | KM-1 RD: 0-2976 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 143.26 | 0.9 | 0.9 | 143.26 | 100% | Completed
127 | KM-1 RD: 0-1500, 22000-29000 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 410.62 | 2.6 | 2.6 | 410.62 | 100% | Completed
128 | Bazai Main Canal RD: 79500 to RD: 84500 | Malakand Irrigation Division Malakand | 0.302 | 0.296 | 39 | 649.87 | 1.5 | 1.2 | 519.89 | 80% | Work in Progress
129 | Silt & Shingle Clearance of P.C Minor from RD 0+000 To Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.388 | 12.881 | 1851.77 | 7.62 | 2.2 | 534.6 | 28.87% | Work in Progress
130 | Clearance of Shingri Minor from RD 0-17250 in reaches. | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.309 | 530.92 | 2.347 | 1.906 | 431.16 | 81.21% | Work in Progress
131 | Clearance of Meherdi Minor from RD 0-31000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 9.451 | 2167.5 | 8.382 | 6.113 | 1580.75 | 72.93% | Work in Progress
132 | Clearance of Kalu Branch from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.33 | 0.3218 | 11.563 | 1318.25 | 5 | 2 | 527.33 | 40% | Work in Progress
133 | Clearance of Hathian Minor from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.05 | 0.04875 | 2.35 | [5 empty] | Not yet started
134 | Clearance of Jalala Disty from RD: 29000 to Tail in reaches | Malakand Irrigation Division Malakand | 0.37 | 0.3607 | 14.024 | 1476.73 | 5900 | 5400 | 1351.5 | 91.52% | Work in Progress
135 | Clearance of Pirsaddo Disty, Ghano Minor and Qutab Gharh Minor from : H-Tail to Tail in reaches. | Malakand Irrigation Division Malakand | 0.35 | 0.341 | 1.88 |  |  | 0 | 0 | 0% | Not yet started
136 | Clearance of Shergarh Minor from Head to Rd:12+000 in reaches. | Malakand Irrigation Division Malakand | 0.15 | 0.146 | 7.752 |  |  | 0 | 0 | 0% | Not yet started
137 | Clearance of Shergarh Minor from Rd:12+000 tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 7.752 | 1195.13 | 6000 | 5500 | 956.83 | 91.66% | Work in Progress
138 | Clearance of Spokanda Disty from RD: 18000 to Tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 5.659 |  |  | 0 | 0 | 0% | Not yet started
139 | Silt & Shingle Clearance of Spokanda Disty from 0-18000 | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.488 | 771.85 | 2.743 | 1.1 | 308.74 | 40% | Work in Progress
140 | Silt Clearance of Lower Siran Canal RD 0-14000 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3110.16 | 3.04 | 1.1277 | 1673.89 | 54% | In progress
141 | Silt Clearance of Lower Siran Canal RD 14000-36500 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3142.51 | 4.26 | 1.6458 | 1413.92 | 45% | In progress
142 | Silt Clearance of Lower Siran Canal Hathi Maira Branch & Gandian Minor RD 36500 in reaches | Mansehra Irrigation Division Mansehra | 0.55 | 0.4954 | 26.21 | 2080.06 | 12.1 | 3.6117 | 1201.72 | 58% | In progress
143 | Silt Clearance of Ichar Canal/ Kalghan Minor RD 0-tail in reaches | Mansehra Irrigation Division Mansehra | 0.25 | 0.2254 | 5.97 | 1197.78 | 5.66 | 0.6096 | 56.63 | 5% | In progress
144 | Silt Clearance of Upper Siran Canal from RD 0-30000 In reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2065 | 3.048 | 0.8382 | 355.14 | 17% | In progress
145 | Silt Clearance of Upper Siran Canal from RD 30000-61000 in reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2110 | 9.44 | 5 | 1576 | 75% | In progress
146 | Silt Clearance of Upper Siran Canal from RD 61000-tail in reaches | Mansehra Irrigation Division Mansehra | 0.18 | 0.1623 | 23.86 | 930 | 5.27 | 1.0964 | 224.69 | 24% | In progress
147 | Silt Clearance of Dhodial Minor Upper Siran Canal in reaches | Mansehra Irrigation Division Mansehra | 0.22 | 0.1981 | 5.24 | 1135 | 5.24 | 2.4884 | 559.94 | 49% | In progress
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086

## 08-02-2023
S# | Name of Canal | Name of Division | Estimated Cost(RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Total Quantity of Silt to be removed (m3) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Total Quantity of Silt removed till date (m3) | Progress Till date in % | Remarks
1 | Swabi Irrigation Division-I Swabi
2 | Shahbaz Garhi Sub Division
3 | Clearance from the bed of Jamal Garhi Disty from 00-tail in reaches. | Swabi Irrigation Division-I Swabi | 0.3 | 0.11 | 16.81 | 1692.37 | 4.7 | 4.4 | 1590.83 | 94% | In-Progress
4 | Silt Clearance from the bed of Buxali Disty & Kot Minor from 00-tail in reaches | Swabi Irrigation Division-I Swabi | 0.65 | 0.36 | 21.34 | 4715.26 | 9.42 | 7.5 | 4338.04 | 92% | In-Progress
5 | Removal of debris and heaps from Machai Branch RD 105+000 to 142+000 in reaches | Swabi Irrigation Division-I Swabi | 0.35 | 0.13 | 247.58 | 4521.89 | 0.48 | 0.3 | 3707.95 | 82% | In-Progress
6 | Removal of debris and heaps from Machai Branch RD 142+000 to 186+000 in reaches | Swabi Irrigation Division-I Swabi | 0.35 | 0.13 | 247.58 | 4513.02 | 0.35 | 0.3 | 4377.63 | 97% | In-Progress
7 | Silt Clearance from the bed of Chura Minor , Sawal Dher Minor & Mala Minor from RD: 00-tail in reaches. | Swabi Irrigation Division-I Swabi | 0.3 | 0.11 | 14.38 | 1698.88 | 7 | 5.4 | 1596.95 | 94% | In-Progress
8 | Silt clearance from the bed Shahbaz Garhi Disty and its sub System from RD:00-tail in reaches | Swabi Irrigation Division-I Swabi | 0.8 | 0.44 | 18.29 | 4522.69 | 14.85 | 12.5 | 4115.65 | 91% | In-Progress
9 | Silt Clearance from the bed of Ismalia Disty and its sub system from 00-tail in reaches | Swabi Irrigation Division-I Swabi | 0.9 | 0.5 | 18.29 | 6469.09 | 13.26 | 11.7 | 6210.33 | 96% | In-Progress
10 | Silt Clearance from the bed of Adina Minor and adina Minor Branch from Head to tail in reaches | Swabi Irrigation Division-I Swabi | 0.35 | 0.19 | 7.89 | 1980.17 | 5.59 | 4.7 | 1841.56 | 93% | In-Progress
11 | Silt clearance from RD:0+00 to RD:8+000 in reaches of Ghazai Khani Flow Irrigation Scheme | Swat Irrigation Division -I | 0.24 | 0.213 | 2.438 | 1339.39 | 2.44 | 2.25 | 750 | 56% | Work in Progress
12 | "Silt clearance from RD:0+00 to RD:12+000 in reaches of Karshalizara Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.1199 | 3.657 | 613 | 3.66 | 2.6 | 500 | 81.57% | Work in Progress
13 | "Silt clearance from RD:0+00 to RD:20+000 in reaches of Charorai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.15 | 0.135 | 6.096 | 766.25 | 6.1 | 4.8 | 698 | 91.09% | Work in Progress
14 | "Silt clearance from RD:0+00 to RD:12+000 in reaches of Kuriya Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.25 | 0.225 | 3.657 | 1397.44 | 3.66 | 2.9 | 780 | 55.82% | Work in Progress
15 | "Silt clearance from RD:0+00 to RD:9+000 in reaches of Elai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 2.743 | 613 | 2.74 | 2.4 | 370 | 60.36% | Work in Progress
16 | "Silt clearance from RD:0+00 to RD:60+000 in reaches of Budal Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 18.287 | 672.53 | 9.14 | 6.2 | 360 | 53.53% | Work in Progress
17 | "Silt clearance from RD:0+00 to RD:16+000 in reaches of Singarai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 4.267 | 669.7 | 4.27 | 3 | 370 | 55.25% | Work in Progress
18 | "Silt clearance from RD:0+00 to RD:26+000 in reaches of Bajkata Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.24 | 0.216 | 7.924 | 408.66 | 7.92 | 4.8 | 300 | 73.41% | Work in Progress
19 | Silt clearance from RD:0+00 to RD:34+000 in reaches of Gagra Flow Irrigation Scheme | Swat Irrigation Division -I | 0.5 | 0.4 | 10.363 | 2797 | 9.75 | 5.4 | 1820 | 65.07% | Work in Progress
20 | Nipki Khel Irrigation Scheme | Swat Irrigation Division -I | 2.2 | 1.76 | 38.87 | 10172.62 | 38.87 | 19.0549 | 5000 | 49.02% | Work is in progress
21 | Warsak Gravity Canal | Warsak Canals Division Peshawar | 18.8 | 16.2 | 68.88 | 23089.8 | 61.26 | 41.45 | 15622.95 | 70% | Work is in progress
22 | Warsak Minor | Warsak Canals Division Peshawar | 0.8 | 0.736 | 5.85 | 873 | 5.85 | 1.52 | 227.34 | 28% | Work is in progress
23 | Kafoor Dheri Minor | Warsak Canals Division Peshawar | 0.4 | 0.368 | 0.94 | 900 | 0.94 | 0.85 | 812.9 | 91% | Work is in progress
24 | Shahi Bala Minor | Warsak Canals Division Peshawar | 0.4 | 0.368 | 1.07 | 995 | 1.07 | 0.15 | 142.14 | 15% | Work is in progress
25 | Mullazai Minor | Warsak Canals Division Peshawar | 0.3 | 0.552 | 3.35 | 1670 | 3.35 | 1.07 | 531.36 | 35% | Work is in progress
26 | Tehkal Minor | Warsak Canals Division Peshawar | 0.6 | 0.552 | 0.99 | 360 | 0.99 | 0.24 | 88.62 | 28% | Work is in progress
27 | Palosai Minor | Warsak Canals Division Peshawar | 0.5 | 0.46 | 0.66 | 455 | 0.66 | 0.12 | 84.65 | 22% | Work is in progress
28 | Surizai Minor | Warsak Canals Division Peshawar | 0.4 | 0.368 | 3.02 | 1039 | 3.02 | 0.87 | 299.11 | 30% | Work is in progress
29 | Urmar Minor | Warsak Canals Division Peshawar | 0.8 | 0.736 | 6.71 | 1490 | 6.71 | 3.35 | 745 | 55% | Work is in progress
30 | Pabbi Minor | Warsak Canals Division Peshawar | 0.4 | 0.368 | 2.44 | 694 | 2.44 | 2.29 | 650.63 | 94% | Work is in progress
31 | Warsak Lift Canal | Warsak Canals Division Peshawar | 8.39 | 6.5 | 46.63 | 7487.19 | 29.56 | 10.67 | 2701.56 | 36% | Work is in progress
32 | Regi Minor | Warsak Canals Division Peshawar | 0.13 | 0.15 | 0.91 | 270 | 0.91 | 0 | 0 | 0% | Work is in progress
33 | Badabher Minor | Warsak Canals Division Peshawar | 0.26 | 0.29 | 5.49 | 530 | 5.49 | 1.07 | 103.06 | 22% | Work is in progress
34 | Warsak Left Bank Canal | Warsak Canals Division Peshawar | 1.69 | 1.554 | 19.29 | 6837.96 | 13.2 | 3.66 | 1895.05 | 30% | Work is in progress
35 | Periodical silt clearance of Fore Bay and Feeder Channel Of WPH, Sump Well, Sedimenattion Tank & Raising Main | Warsak Canals Division Peshawar | 2.2 | 1.9 | 3.22 | 4500 | 3.22 | 0 | 0 | 0% | Work is in progress
36 | Silt clearance/removal of heaps of Disty No. 9 RD; 41000 to 85500 | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 13.41 | 599.93 | 1 | 1 | 599.93 | 100% | Completed
37 | Silt clearance of Power House Minor RD 0 to tail | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 1.28 | 599.9 | 1.28 | 1.25 | 585.84 | 98% | In progress
38 | Silt clearance of conduit covering portion of 2/9 Hoti Minor RD 4200 to 5000, 5800 to 7000 & 7200 to 7500 | Mardan Irrigation Division Mardan | 0.7 | 0.4546 | 0.7 | 745.53 | 0.7 | 0.57 | 607.07 | 81% | In progress
39 | Silt clearance of 2/9 Hoti Minor RD 0 to 4200, 5000 to 5800 & 7500 to 19000 | Mardan Irrigation Division Mardan | 0.8 | 0.5195 | 5.94 | 921.08 | 2.43 | 1.8 | 682.28 | 74% | In progress
40 | Silt clearance /removal of heaps of kalpani disty RD 0-51000 in reaches and clearance of syphones RD 10500 and 15000 | Mardan Irrigation Division Mardan | 0.7 | 0.4544 | 15.6 | 4463.54 | 5.07 | 5.07 | 4463.54 | 100% | Completed
41 | Silt clearance /removal of heaps of 1/kalpani Kodinaka Minor RD 0-27000 in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 8.22 | 599.94 | 1.82 | 1.62 | 534.01 | 89% | In progress
42 | Silt clearance /removal of heaps of 2/kalpani Taus Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 6.4 | 2801.12 | 5.5 | 5.5 | 2801.12 | 100% | Completed
43 | Silt clearance of 3/9 Toru Minor RD 0 to 15800 | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 4.81 | 2801.12 | 4.81 | 4.81 | 2801.12 | 100% | Completed
44 | Silt clearance of branch 2/kalpani Muhib Banda Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.175 | 0.1308 | 2.89 | 1633.98 | 2 | 2 | 1633.98 | 100% | Completed
45 | Silt Clearance of Maho Dheri Minor RD: 4000 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.1493 | 4.57 | 1138.2 | 3.35 | 3.35 | 1138.2 | 100% | Completed
46 | Silt Clearance of Rashakai Minor from RD: 7000 to 31000 in reaches | Mardan Irrigation Division Mardan | 0.6 | 0.3894 | 9.45 | 2972.29 | 7.31 | 7.31 | 2972.29 | 100% | Completed
47 | Silt Clearance of Nowshera Minor RD:0 - tail in reachers | Mardan Irrigation Division Mardan | 0.35 | 0.2613 | 5.18 | 2059.85 | 3.2 | 3.2 | 2059.85 | 100% | Completed
48 | Silt Clearance of Turlandi Minor Head to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 5.27 | 2134.4 | 4.71 | 4.71 | 2134.4 | 100% | Completed
49 | Silt Clearance of Khan Mahi Branch from RD: 0 to 3000 and RD: 8000 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 13.41 | 2344.08 | 5.48 | 5.48 | 2344.08 | 100% | Completed
50 | Silt Clearance of Bara Banda Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 3.04 | 1703.02 | 3.04 | 3.04 | 1703.02 | 100% | Completed
51 | Removal of heaps of Disty No. 8 RD: 52000 to 68000 in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 9.45 | 1860.72 | 1.43 | 1.43 | 1860.72 | 100% | Completed
52 | Silt Clearance/removal of heaps of Disty No. 7 at RD: 4000 to 14000 in reaches | Mardan Irrigation Division Mardan | 0.15 | 0.1133 | 4.26 | 1400.56 | 3.04 | 3.04 | 1400.56 | 100% | Completed
53 | Silt Clearance/removal of heaps of Sheikh yousaf Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 5.48 | 239.97 | 2.13 | 2.13 | 239.97 | 100% | Completed
54 | Silt Clearance/removal of heaps of 1/9 Guide Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 7 | 479.94 | 2.74 | 2.74 | 479.94 | 100% | Completed
55 | Silt Clearance/removal of heaps of Koragh Branch RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 14.93 | 479.94 | 2.23 | 2.23 | 479.94 | 100% | Completed
56 | Removal of heaps of Disty No.8 RD: 0 to 38000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 11.58 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
57 | Removal of heaps of Disty No.9 RD: 0 to 41000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 12.5 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
58 | Swabi Irrigation Division-II Swabi
59 | Clearance of Topi Lift Irrigation Channels RD;00-Tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 4.88 | 1161.77 | 2.84 | 2.71 | 1123.81 | 96% | Work in progress
60 | Clearance of Topi & Zarobi Minors from RD;00 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | Topi =4.24 Zarobi =4.27 | 1159.72 | 3.05 | 2.59 | 1068.95 | 85% | Work in progress
61 | Clearance/Repair of Badri Lift Irrigation Scheme | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 0.34 | 607.12 | 0.33 | 0.33 | 607.12 | 100% | Competed
62 | Clearance of Kotha Disty; from RD;00 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.24 | 0.24 | 17.53 | 1389.07 | 1.89 | 1.89 | 1389.07 | 100% | Competed
63 | Clearance of Pehur main Canal from RD;46000 to RD;54000 | Swabi Irrigation Division-II Swabi | 0.18 | 0.18 | 51.4 | 1042.24 | 0.53 | 0.53 | 1042.24 | 100% | Competed
64 | Clearance of Pehur Main Canal from RD;54500 to RD;66000 | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 51.4 | 1130.88 | 0.55 | 0.46 | 952.07 | 83% | Work in progress
65 | Clearance of Pehur Main Canal from RD;66000 to RD;85000 | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.92 | 0.7 | 0.64 | 1304.54 | 91% | Work in progress
66 | Clearance of Pehur Main Canal RD;85000 to RD;93000 | Swabi Irrigation Division-II Swabi | 0.16 | 0.16 | 51.4 | 976.63 | 0.63 | 0.52 | 794.81 | 82% | Work in progress
67 | Clearance of Pehur Main Canal from RD;93500 to RD;98000 | Swabi Irrigation Division-II Swabi | 0.17 | 0.17 | 51.4 | 1033.5 | 0.32 | 0.21 | 689 | 67% | Work in progress
68 | Clearance of Pehur Main Canal from RD;98500 to RD;113000 | Swabi Irrigation Division-II Swabi | 0.18 | 0.18 | 51.4 | 1094.71 | 0.61 | 0.52 | 891.35 | 85% | Work in progress
69 | Clearance of Kaddi, Zaida, Zakarriya & Sheikhdheri Minors from RD;00 to Tail | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | Kaddi= 5.79 Zaida= 3.81 Zakary=3.43 S/Dher=2.95 | 1292.45 | 0.39 | 0.2 | 801.23 | 50% | Work in progress
70 | Clearance of Pehur Main Canal System from RD;113000 to RD;117000 | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 51.4 | 883 | 0.4 | 0.4 | 883 | 100% | Competed
71 | Clearance of Pehur Main Canal System from RD;117000 to RD;122000 | Swabi Irrigation Division-II Swabi | 0.12 | 0.12 | 51.4 | 729.53 | 0.22 | 0.15 | 486.35 | 67% | Work in progress
72 | Clearance of Pehur main Canal System from RD;122000 to RD;133000 | Swabi Irrigation Division-II Swabi | 0.13 | 0.13 | 51.4 | 790.91 | 0.4 | 0.35 | 682.01 | 88% | Work in progress
73 | Clearance of PMC System from RD;133000 to 140000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 51.4 | 1738.06 | 0.85 | 0.85 | 1738.06 | 100% | Competed
74 | Clearance of PMC Systems from RD;145000 to RD;150000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.23 | 0.23 | 51.4 | 1332.82 | 0.41 | 0.2 | 1025.25 | 50% | Work in progress
75 | Clearance of PMC System from RD;150500 to RD;162000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.81 | 0.44 | 0.22 | 1297.59 | 50% | Work in progress
76 | Clearance of PMC System from RD;162100 to Tail & other allied Branches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.85 | 3.23 | 3.05 | 1406.71 | 94% | Work in progress
77 | Clearance of Thanodher Disty: & Bazar Minor from RD;00 to Tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | Thano=6.00 Bazar=7.47 | 1157.95 | 0.35 | 0.18 | 929.79 | 50% | Work in progress
78 | Clearance of flood deposition and silt clearance of ¦Indus Branch RD:74500 Tail in reaches. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 18.54 | 4478 | 11.89 | 11.43 | 3617.16 | 96% | Work in progress
79 | Silt Clearance of Dagi Minor from RD:0- 37000 in reaches i/c repair to out lets & other allied structures. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 11.28 | 4482 | 9.15 | 9.15 | 4482 | 100% | Competed
80 | Silt Clearance of Dandoka Minor from RD:0-Tail in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.03 | 2246.38 | 4.27 | 2.74 | 1396.88 |  | Work in progress
81 | Silt Clearance of Sudher Minor RD:0 - tail in reaches & other allied structures | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 2.29 | 1684.86 | 1.83 | 0 | 0 |  | contractor deployed
82 | Silt Clearance of Yar Hussain Minor RD;0-tail | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 6.8 | 2803.37 | 5.79 | 1.22 | 622.97 | 21% | Work in progress
83 | Silt Clearance of Ghazi Kot Minor from RD: 0-tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.95 | 2244.11 | 4.57 | 0 | 0 |  | contractor deployed
84 | Silt Clearance Daulat Minor and Gidar Minor RD; 0-tail in reaches & other allied structures | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 16.84 | 4482 | 13.11 | 13.11 | 4482 | 100% | Competed
85 | Silt Clearance of Pirsabaq Disty and pirsabaq Minor from Rd:0-tail in reaches. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 11.75 | 4946.41 | 14.21 | 10.67 | 3984.01 | 75% | Work in progress
86 | Silt Clearance of Chowky Disty, Chowki Minor 1 and 2 from RD: 00 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 8.23 | 3710.22 | 11.1 | 6.16 | 2766.7 | 55% | Work in progress
87 | Silt Clearance of Gumbat Minor No.1 & Gumbat Branch from RD:0+0 to tail in reaches., | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 5.18 | 3096.09 | 6.46 | 4.57 | 2731.49 | 71% | Work in progress
88 | Silt Clearance of Misri Banda from RD;0 to tal in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.73 | 2472.77 | 5.4 | 3.96 | 2063.58 | 73% | Work in progress
89 | Silt Clearance of Ambar Branch from RD;0+0 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.35 | 0.35 | 7.88 | 3923.31 | 3.9 | 0.3 | 283.17 |  | contractor deployed
90 | Silt Clearance of Jehangira Minor & Nandrak Minor from RD;0-tail in reaches and repair to allied structures | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 11.52 | 0 | 0 | 0 | 0 |  | contractor deployed
91 | Silt Clearance of Thanodher Minor & Manki Minor from RD;0-tail in reaches | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 12.42 | 1090.2 | 5.18 | 5.18 | 1090.15 | 100% | Competed
92 | Silt Clearance of Yaqubi Minor, Sard China Minor and Naik Nam Minor from RD; 0-tail | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 10.46 | 1684.86 | 7.44 | 7.44 | 1684.84 | 100% | Competed
93 | Silt Clearance of Dagi Disty & repair to allied structures Rd 0 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 3.23 | 1158.16 | 2.16 | 0 | 0 |  | contractor deployed
94 | Silt Clerance of Gumbat Minor No 2 | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 4.57 | 1855.74 | 4.12 | 2.13 | 953.14 | 52% | Work in progress
95 | Silt Clearance and repair of Link Channel, Lahor Minor ,Zakaria Minor Sheik Dheri from RD; 0- to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 8.19 | 948.62 | 1.52 | 1.52 | 948.62 | 100% | Competed
96 | Silt Clerance of Toru Minor | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 4.57 | 0 | 0 | 0 | 0 |  | contractor deployed
97 | Repair clearance of Sypon Rd 6200 & 8000 Pir Sabaq Disty | Swabi Irrigation Division-II Swabi | 0.1 | 0.1 | 0.06 | 0 | 0 | 0 | 0 |  | contractor deployed
98 | Repair clearance of Sypon Rd 200 Gidar Minor | Swabi Irrigation Division-II Swabi | 0.05 | 0.05 | 0.05 | 0 | 0 | 0 | 0 |  | contractor deployed
99 | Clearance and dewatering of Syphons & repair to out lets Jaggan Nath Section. | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 0.15 | 0 | 0 | 0 | 0 |  | contractor deployed
100 | De-siltation / Berm Cutting of Additional Disty RD.00-Tail in reaches i/c Link channel of Additional Disty RD.00-Tail in reaches | Paharpur Irrigation Division DIKhan | 0.3 | 0.3 | 30 | 3421 | 3 | 1.5 | 1710.5 | 50% | Work is in progress
101 | De-siltation of Chashma Minor, Bilot Disty # 2 & 3, RD 00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.35 | 0.35 | 18.27 | 3182.64 | 8.5 | 4.68 | 1750.45 | 55% | Work is in progress
102 | De-siltation/Berm cutting of Takarwah Disty RD.00-36000 in reaches | Paharpur Irrigation Division DIKhan | 0.4 | 0.4 | 10.98 | 4562 | 1.8 | 1.35 | 3421.5 | 75% | Work is in progress
103 | De-siltation of Bilot Minor & Umray Wali Minor RD.0-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.3 | 0.3 | 11.55 | 3016.72 | 4.5 | 2.52 | 1689.36 | 56% | Work is in progress
104 | De-siltation of Kot Hafiz Disty RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.4 | 0.4 | 28.35 | 3954.92 | 4.5 | 2.43 | 2135.66 | 54% | Work is in progress
105 | De-siltation of Puran Minor i/c its Minors RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.3 | 0.3 | 13.6 | 3272 | 4 | 1.28 | 1047.04 | 32% | Work is in progress
106 | De-siltation of Segra Minor RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.2 | 0.2 | 12.25 | 2280.66 | 2.5 | 0.88 | 798.23 | 35% | Work is in progress
107 | De-siltation of Takarwah Disty RD 36000-86000 in reaches. | Paharpur Irrigation Division DIKhan | 0.3 | 0.3 | 15.24 | 3420.98 | 3 | 2.13 | 2428.9 | 71% | Work is in progress
108 | De-siltation of Mala Minor RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.25 | 0.25 | 7.62 | 2850.82 | 2.5 | 0.88 | 997.79 | 35% | Work is in progress
109 | De-siltation/ Jungle Clearance of Bigwani Minor RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.4 | 0.4 | 11.54 | 4561.31 | 3.5 | 1.12 | 1459.62 | 32% | Work is in progress
110 | De-siltation of Kat Garh Minor RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.25 | 0.25 | 6.39 | 2850.82 | 3 | 1.35 | 1282.87 | 45% | Work is in progress
111 | De-siltation of Kotla Minor & Disty # 1 RD.00-Tail in reaches i/c Jungle Clearance in reaches. | Paharpur Irrigation Division DIKhan | 0.4 | 0.4 | 7.72 | 3719.23 | 4 | 2 | 1859.62 | 50% | Work is in progress
112 | De-siltation of Upstream Dicth Channels RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.25 | 0.25 | 2 | 5678 | 2 | 1.14 | 3236.46 | 57% | Work is in progress
113 | De-siltation of Downstream Ditch Channels RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.25 | 0.25 | 4 | 1841 | 2 | 1.16 | 1067.78 | 58% | Work is in progress
114 | De-siltation of Disty No.2 & Disty # 3 RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.4 | 0.4 | 8.27 | 4561.31 | 2 | 1.2 | 2736.79 | 60% | Work is in progress
115 | De-siltation of Shah Kot Minor RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.2 | 0.2 | 8.32 | 2280.66 | 3 | 1.14 | 866.65 | 38% | Work is in progress
116 | De-siltation of Shah Kot Feeder RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.35 | 0.35 | 1.5 | 3991.15 | 1.5 | 0.62 | 1636.37 | 41% | Work is in progress
117 | De-siltation of Bund Korai Minor RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.3 | 0.3 | 4.5 | 2814.59 | 3 | 1.05 | 985.11 | 35% | Work is in progress
118 | Silt clearance of Sarai Saleh NPC Rd 0-10000 in reaches | Haripur Irrigation Division Haripur | 0.35 | 0.283 | 15.85 | 1271 | 3.04 | 3 | 1250 | 95% | In progress
119 | Silt clearance of Sarai Saleh NPC Rd 10000-17000 i/c Minor No.1 in reaches | Haripur Irrigation Division Haripur | 0.3 | 0.24 | 15.85 | 1131.96 | 2.13 | 2.01 | 1095.23 | 95% | In progress
120 | Silt clearance of Sarai Saleh NPC Rd 17000-30000 i/c Minor No.2 in reaches | Haripur Irrigation Division Haripur | 0.35 | 0.28 | 15.85 | 1347 | 3.96 | 2.05 | 750.32 | 50% | In progress
121 | Clearance of Daur Main Canal Rd 0-tail | Haripur Irrigation Division Haripur | 0.15 | 0.1216 | 0.838 | 555.2 | 0.838 | 0.838 | 555.2 | 100% | Work completed
122 | Silt Clearance of Disty No.02 RD 0-20000 in reaches. | Haripur Irrigation Division Haripur | 0.25 | 0.2 | 6.62 | 1287.6 | 6.09 | 5.79 | 1210.58 | 95% | In progress
123 | Silt Clearance of Main KRBC RD 11000-42000 in reaches | Haripur Irrigation Division Haripur | 0.25 | 0.225 | 12.8 | 1287.6 | 9.45 | 8.5 | 1202.3 | 93% | In progress
124 | Silt Clearance Disty No.04 RD 0-24000 in reaches. | Haripur Irrigation Division Haripur | 0.3 | 0.24 | 7.31 | 1545.12 | 7.31 | 6.18 | 1382.99 | 85% | In progress
125 | Silt Clearance of Disty No.03 i/c Ziarat Minor and Bandi Minor in reaches. | Haripur Irrigation Division Haripur | 0.3 | 0.24 | 10.67 | 1545.12 | 10.67 | 5.02 | 785.23 | 49% | In progress
126 | Silt Clearance of Disty No.1 i/c Balartop & Kamalpur Minors in reaches. | haripur Irrigation Division Haripur | 0.3 | 0.24 | 10.36 | 1545.12 | 10.36 | 7.5 | 998.32 | 76% | In progress
127 | Silt Clearance of KLBC Rd 0-26000 in reaches | haripur Irrigation Division Haripur | 0.3 | 0.24 | 7.92 | 1545.12 | 7.92 | 0 | 0 | 0 | not yet started due to decisiion made in meeting with XEN WAPDA, PMO and CDA Islambad authorities and work will be started from 15th February 2023
128 | Silt clearance of Sarai Saleh NPC Rd 30000-40000 i/c Minor No. 3 in reaches | HAripur Irrigation Division Haripur | 0.25 | 0.2 | 15.85 | 946 | 3.04 | 1.03 | 405.2 | 40% | In progress
129 | Clearance of Main Rangila Irrigation system i/c Rangila Tank | Haripur Irrigation Division Haripur | 0.2 | 0.173 | 2.21 | 559 | 2.21 | 0.3 | 95.23 | 15% | In progress
130 | Silt Clearance of Chak Muneem Minor. | Haripur Irrigation Division Haripur | 0.2 | 0.16 | 7.01 | 1030.8 | 7.01 | 1.25 | 110.3 | 15% | In progress
131 | Silt clearance of Kharabara Dam Channel | Haripur Irrigation Division Haripur | 0.1 | 0.08 | 2.8 | 515.1 | 2.8 | 0.58 | 85.36 | 15% | In progress
132 | Silt Clearance of Badwan Kharif Irrigation Scheme at RD 0+00 To Tail. | Chakdara Irrigation Sub Division ,Dir Division | 0.9 | 0.8957 | 22.18 | 4635.35 | 22.18 | 9.6 | 2689.19 | 58.01% | Work is in progress
133 | Jue Shiekh Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 16.29 | 13.03 | 53.35 | 132353 | 53.35 | 46.3 | 114863 | 87% | Work is in progress
134 | Jue Zardad Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 3.6 | 2.88 | 13.1 | 18500 | 13.1 | 13.1 | 18500 | 100% | Completed
135 | Kabul River Canal | Peshawar Canal Division, Peshawar (Kabaul River Canal Sub Division) | 27.855 | 22.284 | 60.35 | 1062085 | 60.35 | 36.2 | 637107 | 60% | Work is in progress
136 | Hazar Khwani Branch | Peshawar Canal Division, Peshawar (Kabul River Canal Sub Division) | 23.2 | 18.56 | 28.04 | 1016303 | 28.04 | 26 | 942364 | 93% | Work is in progress
137 | Barwai Irrigation Canal | Swat Irrigation Division-II Matta | 0.3 | 0.2805 | 11.22 | 1300 | 6.1 | 6.1 | 1300 | 100% | Completed
138 | Shamizai Irrigation Canal | Swat Irrigation Division-II Matta | 1 | 0.779 | 20.73 | 5150 | 19.5 | 19.5 | 5150 | 100% | Completed
139
140 | Desiltation / berm cutting/Jungle clearance of Disty No.04, RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 10.11 | 5964.26 | 5.64 | 3.84 | 4055.7 | 68% | Work is in progress.
141 | Desiltation / berm cutting/Jungle clearance of Disty No.5 & its Minor and sub Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 26.31 | 7688.07 | 8.2 | 4.92 | 4612.84 | 60% | Work is in progress.
142 | Desiltation / berm cutting/Jungle clearance of Dera Disty RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 16.7 | 5812.06 | 6.55 | 4.91 | 4359.05 | 75% | Work is in progress.
143 | Silt clearance/ jungle clearance of Muryali Minor RD. 00-15000 in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.64 | 4021.01 | 5.33 | 0 | 0 | 0% | Work is in progress.
144 | Silt clearance/ jungle clearance including removal of debris of Lachra Minor/Makali Minor in reaches. | CRBC Irrigation Division DIKhan | 0.25 | 0.23 | 3.92 | 2402.7 | 11.3 | 0.57 | 120.14 | 5% | Work is in progress.
145 | Desiltation / berm cutting/Jungle clearance of Mehmood Disty. RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.05 | 5737.19 | 4.42 | 3.32 | 4302.89 | 75% | Work is in progress.
146 | Desiltation / berm cutting/Jungle clearance of Nawab Minor RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.3 | 0.27 | 7.62 | 2952 | 2.59 | 1.92 | 2184.48 | 74% | work in progress
147 | Desiltation / berm cutting/Jungle clearance of Disty No.7, i/c Minors of Disty No.7 RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 30.53 | 7801.33 | 15.37 | 7.69 | 3900.67 | 50% | work in progress
148 | Desiltation / berm cutting/Jungle clearance of Disty No. 8 & 8-A, RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.29 | 3999 | 3.95 | 3.75 | 3799.05 | 95% | work in progress
149 | Desiltation / berm cutting/Jungle clearance of Disty No.9 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.71 | 3560.86 | 2.9 | 0.43 | 534.13 | 15% | work in progress
150 | Desiltation / berm cutting/Jungle clearance of Disty No.10 & 10/A RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11 | 3950.22 | 3.19 | 0.48 | 592.53 | 15% | yet to be started
151 | Desiltation / berm cutting/Jungle clearance of Disty No. 11 & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 9.1 | 5670.47 | 10.66 | 3.73 | 3685.81 | 65% | work in progress
152 | Desiltation / berm cutting/Jungle clearance of Disty No. 11-A, & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 21.86 | 7695.14 | 5.93 | 1.78 | 2308.54 | 30% | work in progress
153 | Desiltation / berm cutting/Jungle clearance of Disty No. 12 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.23 | 5762.51 | 4.11 | 1.64 | 4898.13 | 85% | work in progress
154 | Desiltation /Jungle Clearance of Disty # 13 & its System RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.675 | 0.6075 | 21.655 | 4256.03 | 4.66 | 4.19 | 3830 | 90% | Work is in progress.
155 | Shingling of CPR & Jungle Clearance of Disty # 14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.725 | 0.6525 | 21.616 | 4176.75 | 4.58 | 4.12 | 3759 | 90% | Work is in progress.
156 | Shingling of CPR & Jungle Clearance of MD-14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.433 | 2145.01 | 2.43 | 2.06 | 1823 | 85% | Work is in progress.
157 | Shingling of CPR & Jungle Clearance of Disty # 15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.7 | 0.63 | 21.494 | 3752 | 3.65 | 2 | 2064 | 55% | Work is in progress.
158 | Shingling of CPR & Jungle Clearance of MD-15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.325 | 0.2925 | 5.8384 | 1862.55 | 2.28 | 0 |  | 0% | Work not yet started.
159 | Shingling of CPR & Jungle Clearance of Disty 16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 12.75 |  | 2.43 | 0 |  | 0% | Work not yet started.
160 | Shingling of CPR & Jungle Clearance of Minor of Disty-16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.8445 |  | 2.45 | 0 |  | 0% | Work not yet started.
161 | Desiltation / Jungle Clearance of Disty # 17 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 9.6951 |  | 2.13 | 0 |  | 0% | Work not yet started.
162 | Shingling of CPR & Jungle Clearance of Disty # 18 its Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 18.009 |  | 4.26 | 0 |  | 0% | Work not yet started.
163 | Shingling of CPR & Jungle Clearance of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.55 | 0.495 | 15.753 |  | 3.96 | 0 |  | 0% | Work not yet started.
164 | Desiltation / Jungle Clearance of M-1 & M-2 of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.829 |  | 4 | 0 |  | 0% | Work not yet started.
165 | Removal of Heaps / Clearance of Bari Band Disty RD: 39+500-88+600 in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.33775 | 14.96 | 1435.76 | 8.21 | 7.85 | 1390 | 95.62% | Work in Progress
166 | Removal of Heaps / Clearance of Hero Shah Minor RD: 0 -38+000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 11.58 | 2446.93 | 11.58 | 10.75 | 2250 | 92.83% | Work in Progress
167 | Removal of Heaps / Clearance of Kalu Shah Disty and Dundian Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.1 | 0.098 | 7.69 | 785.8 | 5 | 5 | 785.8 | 100% | Completed
168 | Removal of Heaps / Clearance of Sarwala Disty and Lund Khwar Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 18.29 | 3172.99 | 10.06 | 10.06 | 3172.99 | 100% | Completed
169 | Removal of Heaps / Clearance of Said Abad Disty and Pir Abad Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 20.42 | 3113.1 | 7.31 | 7.31 | 3113.1 | 100% | Completed
170 | Removal of Heaps / Clearance of Katlang Disty from RD: 0-40+000 in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 12.19 | 1910.43 | 7.61 | 7.61 | 1910.43 | 100% | Completed
171 | Removal of Heaps / Clearance of Shamozai Disty/ Syphon and Likpani Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.392 | 17.67 | 2730.62 | 13.01 | 13.01 | 2730.62 | 100% | Completed
172 | Removal of Heaps / Clearance of Dheri Minor and Tail Minor Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.15 | 0.147 | 7.01 | 1211.68 | 6 | 6 | 1211.68 | 100% | Completed
173 | Bazai Main Canal Head Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 21 | 21 | 1168.075 | 100% | Completed
174 | Wartair Disty | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 6 | 587.93 | 6 | 6 | 587.93 | 100% | Completed
175 | Kharki Disty No. 02 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 3.3 | 1272.34 | 3.3 | 3.3 | 1272.34 | 100% | Completed
176 | Additional Minor No. 03, 06 and Bazai Disty No. 01. | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | 16.8 | 1272.14 | 3 | 3 | 1272.14 | 100% | Completed
177 | Bazai Main Canal, Syphon No. 4431, 5851, 12530, 13590, 14842, 18400, 47527 & 58853 | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | [5 empty] | 70% | Work in Progress
178 | Bazai Disty No. 04, Bazai Minor No. 09, 11 and 12. | Malakand Irrigation Division Malakand | 0.27 | 0.26625 | 15.2 | 4070 | 9 | 9 | 4070 | 100% | Completed
179 | Clearance of Syphon 79205, 93480 and 97962. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | [5 empty] | 20% | Work in Progress
180 | Bazai Disty No. 03 and Bazai Minor No. 05. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | 20.5 | 1907.82 | 7 | 7 | 1907.82 | 100% | Completed
181 | Bazai Main Canal Tail Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 0 | 0 | 0 | 0% | Not Yet start
182 | KM-1 RD: 0-2976 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 143.26 | 0.9 | 0.9 | 143.26 | 100% | Completed
183 | KM-1 RD: 0-1500, 22000-29000 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 410.62 | 2.6 | 2.6 | 410.62 | 100% | Completed
184 | Bazai Main Canal RD: 79500 to RD: 84500 | Malakand Irrigation Division Malakand | 0.302 | 0.296 | 39 | 649.87 | 1.5 | 1.4 | 606.52 | 93.33% | Work in Progress
185 | Silt & Shingle Clearance of P.C Minor from RD 0+000 To Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.388 | 12.881 | 1851.77 | 7.62 | 3.1 | 753.3 | 40.68% | Work in Progress
186 | Clearance of Shingri Minor from RD 0-17250 in reaches. | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.309 | 530.92 | 2.347 | 2.04 | 461.42 | 86.91% | Work in Progress
187 | Clearance of Meherdi Minor from RD 0-31000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 9.451 | 2167.5 | 8.382 | 6.113 | 1580.75 | 72.93% | Work in Progress
188 | Clearance of Kalu Branch from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.33 | 0.3218 | 11.563 | 1318.25 | 5 | 3.05 | 804.13 | 61% | Work in Progress
189 | Clearance of Hathian Minor from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.05 | 0.04875 | 2.35 | [5 empty] | Not yet started
190 | Clearance of Jalala Disty from RD: 29000 to Tail in reaches | Malakand Irrigation Division Malakand | 0.37 | 0.3607 | 14.024 | 1476.73 | 5900 | 5400 | 1351.5 | 91.52% | Work in Progress
191 | Clearance of Pirsaddo Disty, Ghano Minor and Qutab Gharh Minor from : H-Tail to Tail in reaches. | Malakand Irrigation Division Malakand | 0.35 | 0.341 | 1.88 |  |  | 0 | 0 | 0% | Not yet started
192 | Clearance of Shergarh Minor from Head to Rd:12+000 in reaches. | Malakand Irrigation Division Malakand | 0.15 | 0.146 | 7.752 |  |  | 0 | 0 | 0% | Not yet started
193 | Clearance of Shergarh Minor from Rd:12+000 tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 7.752 | 1195.13 | 6000 | 5500 | 956.83 | 91.66% | Work in Progress
194 | Clearance of Spokanda Disty from RD: 18000 to Tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 5.659 |  |  | 0 | 0 | 0% | Not yet started
195 | Silt & Shingle Clearance of Spokanda Disty from 0-18000 | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.488 | 771.85 | 2.743 | 1.1 | 308.74 | 40% | Work in Progress
196 | Silt Clearance of Lower Siran Canal RD 0-14000 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3110.16 | 3.04 | 1.402 | 1699.37 | 55% | In progress
197 | Silt Clearance of Lower Siran Canal RD 14000-36500 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3142.51 | 4.26 | 1.8286 | 1430.82 | 46% | In progress
198 | Silt Clearance of Lower Siran Canal Hathi Maira Branch & Gandian Minor RD 36500 in reaches | Mansehra Irrigation Division Mansehra | 0.55 | 0.4954 | 26.21 | 2080.06 | 12.1 | 3.7887 | 1218.14 | 59% | In progress
199 | Silt Clearance of Ichar Canal/ Kalghan Minor RD 0-tail in reaches | Mansehra Irrigation Division Mansehra | 0.25 | 0.2254 | 5.97 | 1197.78 | 5.66 | 0.8534 | 79.28 | 7% | In progress
200 | Silt Clearance of Upper Siran Canal from RD 0-30000 In reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2065 | 3.048 | 1.0515 | 374.96 | 18% | In progress
201 | Silt Clearance of Upper Siran Canal from RD 30000-61000 in reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2110 | 9.44 | 5 | 1576 | 75% | In progress
202 | Silt Clearance of Upper Siran Canal from RD 61000-tail in reaches | Mansehra Irrigation Division Mansehra | 0.18 | 0.1623 | 23.86 | 930 | 5.27 | 1.264 | 240.26 | 26% | In progress
203 | Silt Clearance of Dhodial Minor Upper Siran Canal in reaches | Mansehra Irrigation Division Mansehra | 0.22 | 0.1981 | 5.24 | 1135 | 5.24 | 2.7017 | 579.76 | 51% | In progress
204 | Silt clearance of Doaba Canal RD. 4+600-9+100 in Reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.242 | 0.1548 | 14.7828 | 1128.21 | 0.58 | 0.58 | 1128.21 | 100% | Completed
205 | Silt clearance of Doaba Canal RD. 9+200-13+000 in Reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.343 | 0.22 | 14.7828 | 1595.38 | 0.548 | 0.548 | 1595.38 | 100% | Completed
206 | Silt clearance of Doaba Canal RD. 13+200-17+000 in Reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.341 | 0.218 | 14.7828 | 1586.32 | 0.6 | 0.6 | 1586.32 | 100% | Completed
207 | Silt Clearance of Doaba Canal RD.17+300-21+200 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.338 | 0.22 | 14.7828 | 1572.55 | 0.672 | 0.672 | 1572.55 | 100% | Completed
208 | Silt Clearance of Doaba Canal RD.21+250-24+475 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.312 | 0.2 | 14.7828 | 1454.79 | 0.74 | 0.74 | 1454.79 | 100% | Completed
209 | Silt clearance of New Michni Branch RD. 0+000-4+100 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.3439 | 0.22 | 11.027 | 741.2 | 0.685 | 0.685 | 741.2 | 100% | Completed
210 | Silt clearance of New Michni Branch RD. 4+200-8+300 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.332 | 0.212 | 11.027 | 715.46 | 0.731 | 0.731 | 715.46 | 100% | Completed
211 | Silt clearance of New Michni Branch RD 8+500-12+000 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.32 | 0.2 | 11.027 | 689.67 | 0.609 | 0.609 | 689.67 | 100% | Completed
212 | Silt Clearance of Dalazak Minor RD. 0+000-4+000 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.1244 | 0.796 | 3.96 | 451.34 | 0.67 | 0.67 | 451.34 | 100% | Completed
213 | Silt Clearance of Subhan Khwar Disty RD.0+000-4+500 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.315 | 0.201 | 4.81 | 680.17 | 0.84 | 0.84 | 680.17 | 100% | Completed
214 | Silt clearance of Ichri Branch RD. 0-4366 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.15 | 0.096 | 1.33 | 576.89 | 0.67 | 0.67 | 576.89 | 100% | Completed
215 | Silt Clearance of Shabqadar Branch RD.0+000-15+000 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.38 | 0.24 | 4.5 | 819.21 | 1.645 | 1.645 | 819.21 | 100% | Completed
216 | Silt Clearance of Iceland Canal RD..0+00-Tail in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.35 | 0.224 | 8.83 | 2045.2 | 2.103 | 2.103 | 2045.2 | 100% | Completed
217 | Silt Clearance of Samkana Branch RD.0+000-30+000 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.3 | 0.192 | 9.14 | 2041.66 | 2.103 | 2.103 | 2041.66 | 100% | Completed
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086

## 09-02-2023
S# | Name of Canal | Name of Division | Estimated Cost (RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Total Quantity of Silt to be removed (m3) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Total Quantity of Silt removed till date (m3) | Progress Till date in % | Remarks
1 | Silt clearance of Doaba Canal RD. 4+600-9+100 in Reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.242 | 0.1548 | 14.7828 | 1128.21 | 0.58 | 0.58 | 1128.21 | 100% | Completed
2 | Silt clearance of Doaba Canal RD. 9+200-13+000 in Reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.343 | 0.22 | 14.7828 | 1595.38 | 0.548 | 0.548 | 1595.38 | 100% | Completed
3 | Silt clearance of Doaba Canal RD. 13+200-17+000 in Reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.341 | 0.218 | 14.7828 | 1586.32 | 0.6 | 0.6 | 1586.32 | 100% | Completed
4 | Silt Clearance of Doaba Canal RD.17+300-21+200 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.338 | 0.22 | 14.7828 | 1572.55 | 0.672 | 0.672 | 1572.55 | 100% | Completed
5 | Silt Clearance of Doaba Canal RD.21+250-24+475 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.312 | 0.2 | 14.7828 | 1454.79 | 0.74 | 0.74 | 1454.79 | 100% | Completed
6 | Silt clearance of New Michni Branch RD. 0+000-4+100 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.3439 | 0.22 | 11.027 | 741.2 | 0.685 | 0.685 | 741.2 | 100% | Completed
7 | Silt clearance of New Michni Branch RD. 4+200-8+300 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.332 | 0.212 | 11.027 | 715.46 | 0.731 | 0.731 | 715.46 | 100% | Completed
8 | Silt clearance of New Michni Branch RD 8+500-12+000 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.32 | 0.2 | 11.027 | 689.67 | 0.609 | 0.609 | 689.67 | 100% | Completed
9 | Silt Clearance of Dalazak Minor RD. 0+000-4+000 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.1244 | 0.796 | 3.96 | 451.34 | 0.67 | 0.67 | 451.34 | 100% | Completed
10 | Silt Clearance of Subhan Khwar Disty RD.0+000-4+500 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.315 | 0.201 | 4.81 | 680.17 | 0.84 | 0.84 | 680.17 | 100% | Completed
11 | Silt clearance of Ichri Branch RD. 0-4366 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.15 | 0.096 | 1.33 | 576.89 | 0.67 | 0.67 | 576.89 | 100% | Completed
12 | Silt Clearance of Shabqadar Branch RD.0+000-15+000 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.38 | 0.24 | 4.5 | 819.21 | 1.645 | 1.645 | 819.21 | 100% | Completed
13 | Silt Clearance of Iceland Canal RD..0+00-Tail in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.35 | 0.224 | 8.83 | 2045.2 | 2.103 | 2.103 | 2045.2 | 100% | Completed
14 | Silt Clearance of Samkana Branch RD.0+000-30+000 in reaches. | Shabqadar Irrigation Sub Division Shabqadar | 0.3 | 0.192 | 9.14 | 2041.66 | 2.103 | 2.103 | 2041.66 | 100% | Completed
15 | Barwai Irrigation Canal | Swat Irrigation Division-II Matta | 0.3 | 0.2805 | 11.22 | 1300 | 6.1 | 6.1 | 1300 | 100% | Completed
16 | Shamizai Irrigation Canal | Swat Irrigation Division-II Matta | 1 | 0.779 | 20.73 | 5150 | 19.5 | 19.5 | 5150 | 100% | Completed
17 | Silt Clearance of Badwan Kharif Irrigation Scheme at RD 0+00 To Tail. | Chakdara Irrigation Sub Division ,Dir Division | 0.9 | 0.8957 | 22.18 | 4635.35 | 22.18 | 9.6 | 2689.19 | 58.01% | Work is in progress (Today Desiltation is Stope Due To Rain)
SWABI IRRIGATION DIVN-1
18 | Clearance from the bed of Jamal Garhi Disty from 00-tail in reaches. | Swabi Irrigation Division-I Swabi | 0.3 | 0.11 | 16.81 | 1692.37 | 4.7 | 4.5 | 1607.75 | 95% | In-progress
19 | Silt Clearance from the bed of Buxali Disty & Kot Minor from 00-tail in reaches | Swabi Irrigation Division-I Swabi | 0.65 | 0.36 | 21.34 | 4715.26 | 9.42 | 7.5 | 4385.19 | 93% | In-progress
20 | Removal of debris and heaps from Machai Branch RD 105+000 to 142+000 in reaches | Swabi Irrigation Division-I Swabi | 0.35 | 0.13 | 247.58 | 4521.89 | 0.48 | 0.3 | 3843.61 | 85% | In-progress
21 | Removal of debris and heaps from Machai Branch RD 142+000 to 186+000 in reaches | Swabi Irrigation Division-I Swabi | 0.35 | 0.13 | 247.58 | 4513.02 | 0.35 | 0.3 | 4422.76 | 98% | In-progress
22 | Silt Clearance from the bed of Chura Minor , Sawal Dher Minor & Mala Minor from RD: 00-tail in reaches. | Swabi Irrigation Division-I Swabi | 0.3 | 0.11 | 14.38 | 1698.88 | 7 | 5.4 | 1613.94 | 95% | In-progress
23 | Silt clearance from the bed Shahbaz Garhi Disty and its sub System from RD:00-tail in reaches | Swabi Irrigation Division-I Swabi | 0.8 | 0.44 | 18.29 | 4522.69 | 14.85 | 12.5 | 4160.87 | 92% | In-progress
24 | Silt Clearance from the bed of Ismalia Disty and its sub system from 00-tail in reaches | Swabi Irrigation Division-I Swabi | 0.9 | 0.5 | 18.29 | 6469.09 | 13.26 | 11.7 | 6275.02 | 97% | In-progress
25 | Silt Clearance from the bed of Adina Minor and adina Minor Branch from Head to tail in reaches | Swabi Irrigation Division-I Swabi | 0.35 | 0.19 | 7.89 | 1980.17 | 5.59 | 4.7 | 1861.36 | 94% | In-progress
| Silt Clearance of Machai Branch at RD: 186000-252000 in reaches | Swabi Irr:Divn-1 Swabi | 1 | 0.45 | 24.764 | 9344.56 | 3.2 | 3.2 | 8121 | 87% | In progress
| Silt Clearance of Kalu Khan Disty and its sub system from RD: 00-tail in reaches | Swabi Irr:Divn-1 Swabi | 1 | 0.45 | 53.87 | 8707 | 27.54 | 20.25 | 6313.95 | 73% | In progress
| Silt Clearance of Nawan Killi Minor ,Sarbandi Minor, Shagai Minor RD:00- tail in reaches | Swabi Irr:Divn-1 Swabi | 0.3 | 0.155 | 4.69 2.92 5.18 12.79 | 2288.51 | 8.8 | 5 | 1517.79 | 66% | In progress
| Silt Clearance of , Naranji Disty & Naranji Minor No.1 & 2 RD: 00-tail in reaches | Swabi Irr:Divn-1 Swabi | 0.3 | 0.15 | 10.3963 3.04 1.58 15.01 | 2465 | 9.14 | 4 | 1812.7 | 74% | In progress
| Silt Clearance of Old Indus branch & Zaida Minor RD:0-Tail in reaches | Swabi Irr:Divn-1 Swabi | 0.4 | 0.2 | 9.84 2.97 12.81 | 4193 | 8.84 | 4.88 | 4089.51 | 98% | In progress
| Silt Clearance of Pehur branch and its sub system RD:0-Tail in reaches | Swabi Irr:Divn-1 Swabi | 1 | 0.55 | 30.69 | 8240 | 15.85 | 10.36 | 7060.6 | 86% | In progress
26 | Swabi Irrigation Division-II Swabi
27 | Clearance of Topi Lift Irrigation Channels RD;00-Tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 4.88 | 1161.77 | 2.84 | 2.71 | 1123.81 | 96% | Work in progress
28 | Clearance of Topi & Zarobi Minors from RD;00 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | Topi =4.24 Zarobi =4.27 | 1159.72 | 3.05 | 2.59 | 1068.95 | 85% | Work in progress
29 | Clearance/Repair of Badri Lift Irrigation Scheme | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 0.34 | 607.12 | 0.33 | 0.33 | 607.12 | 100% | Competed
30 | Clearance of Kotha Disty; from RD;00 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.24 | 0.24 | 17.53 | 1389.07 | 1.89 | 1.89 | 1389.07 | 100% | Competed
31 | Clearance of Pehur main Canal from RD;46000 to RD;54000 | Swabi Irrigation Division-II Swabi | 0.18 | 0.18 | 51.4 | 1042.24 | 0.53 | 0.53 | 1042.24 | 100% | Competed
32 | Clearance of Pehur Main Canal from RD;54500 to RD;66000 | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 51.4 | 1130.88 | 0.55 | 0.46 | 952.07 | 83% | Work in progress
33 | Clearance of Pehur Main Canal from RD;66000 to RD;85000 | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.92 | 0.7 | 0.64 | 1304.54 | 91% | Work in progress
34 | Clearance of Pehur Main Canal RD;85000 to RD;93000 | Swabi Irrigation Division-II Swabi | 0.16 | 0.16 | 51.4 | 976.63 | 0.63 | 0.61 | 937.81 | 96% | Work in progress
35 | Clearance of Pehur Main Canal from RD;93500 to RD;98000 | Swabi Irrigation Division-II Swabi | 0.17 | 0.17 | 51.4 | 1033.5 | 0.32 | 0.21 | 689 | 67% | Work in progress
36 | Clearance of Pehur Main Canal from RD;98500 to RD;113000 | Swabi Irrigation Division-II Swabi | 0.18 | 0.18 | 51.4 | 1094.71 | 0.61 | 0.52 | 891.35 | 85% | Work in progress
37 | Clearance of Kaddi, Zaida, Zakarriya & Sheikhdheri Minors from RD;00 to Tail | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | Kaddi= 5.79 Zaida= 3.81 Zakary=3.43 S/Dher=2.95 | 1292.45 | 0.39 | 0.2 | 801.23 | 50% | Work in progress
38 | Clearance of Pehur Main Canal System from RD;113000 to RD;117000 | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 51.4 | 883 | 0.4 | 0.4 | 883 | 100% | Competed
39 | Clearance of Pehur Main Canal System from RD;117000 to RD;122000 | Swabi Irrigation Division-II Swabi | 0.12 | 0.12 | 51.4 | 729.53 | 0.22 | 0.15 | 486.35 | 67% | Work in progress
40 | Clearance of Pehur main Canal System from RD;122000 to RD;133000 | Swabi Irrigation Division-II Swabi | 0.13 | 0.13 | 51.4 | 790.91 | 0.4 | 0.35 | 682.01 | 88% | Work in progress
41 | Clearance of PMC System from RD;133000 to 140000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 51.4 | 1738.06 | 0.85 | 0.85 | 1738.06 | 100% | Competed
42 | Clearance of PMC Systems from RD;145000 to RD;150000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.23 | 0.23 | 51.4 | 1332.82 | 0.41 | 0.2 | 1025.25 | 50% | Work in progress
43 | Clearance of PMC System from RD;150500 to RD;162000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.81 | 0.44 | 0.22 | 1297.59 | 50% | Work in progress
44 | Clearance of PMC System from RD;162100 to Tail & other allied Branches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.85 | 3.23 | 3.05 | 1406.71 | 94% | Work in progress
45 | Clearance of Thanodher Disty: & Bazar Minor from RD;00 to Tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | Thano=6.00 Bazar=7.47 | 1157.95 | 0.35 | 0.18 | 929.79 | 50% | Work in progress
46 | Clearance of flood deposition and silt clearance of ¦Indus Branch RD:74500 Tail in reaches. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 18.54 | 4478 | 11.89 | 11.43 | 3617.16 | 96% | Work in progress
47 | Silt Clearance of Dagi Minor from RD:0- 37000 in reaches i/c repair to out lets & other allied structures. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 11.28 | 4482 | 9.15 | 9.15 | 4482 | 100% | Competed
48 | Silt Clearance of Dandoka Minor from RD:0-Tail in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.03 | 2246.38 | 4.27 | 2.74 | 1396.88 |  | Work in progress
49 | Silt Clearance of Sudher Minor RD:0 - tail in reaches & other allied structures | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 2.29 | 1684.86 | 1.83 | 0 | 0 |  | contractor deployed
50 | Silt Clearance of Yar Hussain Minor RD;0-tail | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 6.8 | 2803.37 | 5.79 | 1.22 | 622.97 | 21% | Work in progress
51 | Silt Clearance of Ghazi Kot Minor from RD: 0-tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.95 | 2244.11 | 4.57 | 0 | 0 |  | contractor deployed
52 | Silt Clearance Daulat Minor and Gidar Minor RD; 0-tail in reaches & other allied structures | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 16.84 | 4482 | 13.11 | 13.11 | 4482 | 100% | Competed
53 | Silt Clearance of Pirsabaq Disty and pirsabaq Minor from Rd:0-tail in reaches. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 11.75 | 4946.41 | 14.21 | 10.67 | 3984.01 | 75% | Work in progress
54 | Silt Clearance of Chowky Disty, Chowki Minor 1 and 2 from RD: 00 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 8.23 | 3710.22 | 11.1 | 6.16 | 2766.7 | 55% | Work in progress
55 | Silt Clearance of Gumbat Minor No.1 & Gumbat Branch from RD:0+0 to tail in reaches., | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 5.18 | 3096.09 | 6.46 | 4.57 | 2731.49 | 71% | Work in progress
56 | Silt Clearance of Misri Banda from RD;0 to tal in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.73 | 2472.77 | 5.4 | 3.96 | 2063.58 | 73% | Work in progress
57 | Silt Clearance of Ambar Branch from RD;0+0 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.35 | 0.35 | 7.88 | 3923.31 | 3.9 | 0.3 | 283.17 |  | contractor deployed
58 | Silt Clearance of Jehangira Minor & Nandrak Minor from RD;0-tail in reaches and repair to allied structures | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 11.52 | 0 | 0 | 0 | 0 |  | contractor deployed
59 | Silt Clearance of Thanodher Minor & Manki Minor from RD;0-tail in reaches | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 12.42 | 1090.2 | 5.18 | 5.18 | 1090.15 | 100% | Competed
60 | Silt Clearance of Yaqubi Minor, Sard China Minor and Naik Nam Minor from RD; 0-tail | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 10.46 | 1684.86 | 7.44 | 7.44 | 1684.84 | 100% | Competed
61 | Silt Clearance of Dagi Disty & repair to allied structures Rd 0 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 3.23 | 1158.16 | 2.16 | 0 | 0 |  | contractor deployed
62 | Silt Clerance of Gumbat Minor No 2 | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 4.57 | 1855.74 | 4.12 | 2.13 | 953.14 | 52% | Work in progress
63 | Silt Clearance and repair of Link Channel, Lahor Minor ,Zakaria Minor Sheik Dheri from RD; 0- to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 8.19 | 948.62 | 1.52 | 1.52 | 948.62 | 100% | Competed
64 | Silt Clerance of Toru Minor | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 4.57 | 0 | 0 | 0 | 0 |  | contractor deployed
65 | Repair clearance of Sypon Rd 6200 & 8000 Pir Sabaq Disty | Swabi Irrigation Division-II Swabi | 0.1 | 0.1 | 0.06 | 0 | 0 | 0 | 0 |  | contractor deployed
66 | Repair clearance of Sypon Rd 200 Gidar Minor | Swabi Irrigation Division-II Swabi | 0.05 | 0.05 | 0.05 | 0 | 0 | 0 | 0 |  | contractor deployed
67 | Clearance and dewatering of Syphons & repair to out lets Jaggan Nath Section. | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 0.15 | 0 | 0 | 0 | 0 |  | contractor deployed
68 | Silt Clearance of Lower Siran Canal RD 0-14000 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3110.16 | 3.04 | 1.402 | 1699.37 | 55% | Work is in progress (Due to the thunderstorm and heavy rain falls De-siltation has not been executed at site today)
69 | Silt Clearance of Lower Siran Canal RD 14000-36500 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3142.51 | 4.26 | 1.8286 | 1430.82 | 46% | Work is in progress (Due to the thunderstorm and heavy rain falls De-siltation has not been executed at site today)
70 | Silt Clearance of Lower Siran Canal Hathi Maira Branch & Gandian Minor RD 36500 in reaches | Mansehra Irrigation Division Mansehra | 0.55 | 0.4954 | 26.21 | 2080.06 | 12.1 | 3.7887 | 1218.14 | 59% | Work is in progress (Due to the thunderstorm and heavy rain falls De-siltation has not been executed at site today)
71 | Silt Clearance of Ichar Canal/ Kalghan Minor RD 0-tail in reaches | Mansehra Irrigation Division Mansehra | 0.25 | 0.2254 | 5.97 | 1197.78 | 5.66 | 0.8534 | 79.28 | 7% | Work is in progress (Due to the thunderstorm and heavy rain falls De-siltation has not been executed at site today)
72 | Silt Clearance of Upper Siran Canal from RD 0-30000 In reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2065 | 3.048 | 1.0515 | 374.96 | 18% | Work is in progress (Due to the thunderstorm and heavy rain falls De-siltation has not been executed at site today)
73 | Silt Clearance of Upper Siran Canal from RD 30000-61000 in reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2110 | 9.44 | 5 | 1576 | 75% | Work is in progress (Due to the thunderstorm and heavy rain falls De-siltation has not been executed at site today)
74 | Silt Clearance of Upper Siran Canal from RD 61000-tail in reaches | Mansehra Irrigation Division Mansehra | 0.18 | 0.1623 | 23.86 | 930 | 5.27 | 1.264 | 240.26 | 26% | Work is in progress (Due to the thunderstorm and heavy rain falls De-siltation has not been executed at site today)
75 | Silt Clearance of Dhodial Minor Upper Siran Canal in reaches | Mansehra Irrigation Division Mansehra | 0.22 | 0.1981 | 5.24 | 1135 | 5.24 | 2.7017 | 579.76 | 51% | Work is in progress (Due to the thunderstorm and heavy rain falls De-siltation has not been executed at site today)
76 | Jue Shiekh Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 16.29 | 13.03 | 53.35 | 132353 | 53.35 | 49.1 | 121809 | 92% | Work is in progress
77 | Jue Zardad Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 3.6 | 2.88 | 13.1 | 18500 | 13.1 | 13.1 | 18500 | 100% | Completed
78 | Kabul River Canal | Peshawar Canal Division, Peshawar (Kabaul River Canal Sub Division) | 27.855 | 22.284 | 60.35 | 1062085 | 60.35 | 39.1 | 688146 | 65% | Work is in progress
79 | Hazar Khwani Branch | Peshawar Canal Division, Peshawar (Kabul River Canal Sub Division) | 23.2 | 18.56 | 28.04 | 1016303 | 28.04 | 26.7 | 967735 | 95% | Work is in progress
80 | Potta Section (Disty No.11,12 & 13 i/c (Main Canal RD:49623-60500 m)
81 | Silt clearance of Sarai Saleh NPC Rd 0-10000 in reaches | Haripur Irrigation Division Haripur | 0.35 | 0.283 | 15.85 | 1271 | 3.04 | 3 | 1250 | 95% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
82 | Silt clearance of Sarai Saleh NPC Rd 10000-17000 i/c Minor No.1 in reaches | Haripur Irrigation Division Haripur | 0.3 | 0.24 | 15.85 | 1131.96 | 2.13 | 2.01 | 1095.23 | 95% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
83 | Silt clearance of Sarai Saleh NPC Rd 17000-30000 i/c Minor No.2 in reaches | Haripur Irrigation Division Haripur | 0.35 | 0.28 | 15.85 | 1347 | 3.96 | 2.05 | 750.32 | 50% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
84 | Clearance of Daur Main Canal Rd 0-tail | Haripur Irrigation Division Haripur | 0.15 | 0.1216 | 0.838 | 555.2 | 0.838 | 0.838 | 555.2 | 100% | Work completed
85 | Silt Clearance of Disty No.02 RD 0-20000 in reaches. | Haripur Irrigation Division Haripur | 0.25 | 0.2 | 6.62 | 1287.6 | 6.09 | 5.79 | 1210.58 | 95% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
86 | Silt Clearance of Main KRBC RD 11000-42000 in reaches | Haripur Irrigation Division Haripur | 0.25 | 0.225 | 12.8 | 1287.6 | 9.45 | 9.45 | 1287.6 | 100% | Work completed
87 | Silt Clearance Disty No.04 RD 0-24000 in reaches. | Haripur Irrigation Division Haripur | 0.3 | 0.24 | 7.31 | 1545.12 | 7.31 | 6.18 | 1382.99 | 85% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
88 | Silt Clearance of Disty No.03 i/c Ziarat Minor and Bandi Minor in reaches. | Haripur Irrigation Division Haripur | 0.3 | 0.24 | 10.67 | 1545.12 | 10.67 | 5.02 | 785.23 | 49% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
89 | Silt Clearance of Disty No.1 i/c Balartop & Kamalpur Minors in reaches. | haripur Irrigation Division Haripur | 0.3 | 0.24 | 10.36 | 1545.12 | 10.36 | 7.5 | 998.32 | 76% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
90 | Silt Clearance of KLBC Rd 0-26000 in reaches | haripur Irrigation Division Haripur | 0.3 | 0.24 | 7.92 | 1545.12 | 7.92 | 0 | 0 | 0 | not yet started due to decisiion made in meeting with XEN WAPDA, PMO and CDA Islambad authorities and work will be started from 15th February 2023
91 | Silt clearance of Sarai Saleh NPC Rd 30000-40000 i/c Minor No. 3 in reaches | HAripur Irrigation Division Haripur | 0.25 | 0.2 | 15.85 | 946 | 3.04 | 1.03 | 405.2 | 40% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
92 | Clearance of Main Rangila Irrigation system i/c Rangila Tank | Haripur Irrigation Division Haripur | 0.2 | 0.173 | 2.21 | 559 | 2.21 | 0.3 | 95.23 | 15% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
93 | Silt Clearance of Chak Muneem Minor. | Haripur Irrigation Division Haripur | 0.2 | 0.16 | 7.01 | 1030.8 | 7.01 | 1.25 | 110.3 | 15% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
94 | Silt clearance of Kharabara Dam Channel | Haripur Irrigation Division Haripur | 0.1 | 0.08 | 2.8 | 515.1 | 2.8 | 0.58 | 85.36 | 15% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
95 | Silt clearance/removal of heaps of Disty No. 9 RD; 41000 to 85500 | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 13.41 | 599.93 | 1 | 1 | 599.93 | 100% | Completed
96 | Silt clearance of Power House Minor RD 0 to tail | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 1.28 | 599.9 | 1.28 | 1.25 | 585.84 | 98% | In progress
97 | Silt clearance of conduit covering portion of 2/9 Hoti Minor RD 4200 to 5000, 5800 to 7000 & 7200 to 7500 | Mardan Irrigation Division Mardan | 0.7 | 0.4546 | 0.7 | 745.53 | 0.7 | 0.61 | 649.68 | 87% | In progress
98 | Silt clearance of 2/9 Hoti Minor RD 0 to 4200, 5000 to 5800 & 7500 to 19000 | Mardan Irrigation Division Mardan | 0.8 | 0.5195 | 5.94 | 921.08 | 2.43 | 1.96 | 742.93 | 81% | In progress
99 | Silt clearance /removal of heaps of kalpani disty RD 0-51000 in reaches and clearance of syphones RD 10500 and 15000 | Mardan Irrigation Division Mardan | 0.7 | 0.4544 | 15.6 | 4463.54 | 5.07 | 5.07 | 4463.54 | 100% | Completed
100 | Silt clearance /removal of heaps of 1/kalpani Kodinaka Minor RD 0-27000 in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 8.22 | 599.94 | 1.82 | 1.62 | 534.01 | 89% | In progress
101 | Silt clearance /removal of heaps of 2/kalpani Taus Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 6.4 | 2801.12 | 5.5 | 5.5 | 2801.12 | 100% | Completed
102 | Silt clearance of 3/9 Toru Minor RD 0 to 15800 | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 4.81 | 2801.12 | 4.81 | 4.81 | 2801.12 | 100% | Completed
103 | Silt clearance of branch 2/kalpani Muhib Banda Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.175 | 0.1308 | 2.89 | 1633.98 | 2 | 2 | 1633.98 | 100% | Completed
104 | Silt Clearance of Maho Dheri Minor RD: 4000 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.1493 | 4.57 | 1138.2 | 3.35 | 3.35 | 1138.2 | 100% | Completed
105 | Silt Clearance of Rashakai Minor from RD: 7000 to 31000 in reaches | Mardan Irrigation Division Mardan | 0.6 | 0.3894 | 9.45 | 2972.29 | 7.31 | 7.31 | 2972.29 | 100% | Completed
106 | Silt Clearance of Nowshera Minor RD:0 - tail in reachers | Mardan Irrigation Division Mardan | 0.35 | 0.2613 | 5.18 | 2059.85 | 3.2 | 3.2 | 2059.85 | 100% | Completed
107 | Silt Clearance of Turlandi Minor Head to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 5.27 | 2134.4 | 4.71 | 4.71 | 2134.4 | 100% | Completed
108 | Silt Clearance of Khan Mahi Branch from RD: 0 to 3000 and RD: 8000 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 13.41 | 2344.08 | 5.48 | 5.48 | 2344.08 | 100% | Completed
109 | Silt Clearance of Bara Banda Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 3.04 | 1703.02 | 3.04 | 3.04 | 1703.02 | 100% | Completed
110 | Removal of heaps of Disty No. 8 RD: 52000 to 68000 in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 9.45 | 1860.72 | 1.43 | 1.43 | 1860.72 | 100% | Completed
111 | Silt Clearance/removal of heaps of Disty No. 7 at RD: 4000 to 14000 in reaches | Mardan Irrigation Division Mardan | 0.15 | 0.1133 | 4.26 | 1400.56 | 3.04 | 3.04 | 1400.56 | 100% | Completed
112 | Silt Clearance/removal of heaps of Sheikh yousaf Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 5.48 | 239.97 | 2.13 | 2.13 | 239.97 | 100% | Completed
113 | Silt Clearance/removal of heaps of 1/9 Guide Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 7 | 479.94 | 2.74 | 2.74 | 479.94 | 100% | Completed
114 | Silt Clearance/removal of heaps of Koragh Branch RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 14.93 | 479.94 | 2.23 | 2.23 | 479.94 | 100% | Completed
115 | Removal of heaps of Disty No.8 RD: 0 to 38000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 11.58 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
116 | Removal of heaps of Disty No.9 RD: 0 to 41000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 12.5 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
S# | Name of Canal | Name of Division | Estimated Cost (RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Total Quantity of Silt to be removed (m3) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Total Quantity of Silt removed till date (m3) | Progress Till date in % | Remarks
| GOMAL ZAM IRRIGATION DIVISION DIKHAN | Gomal Zam Irrigation Division DIK
117 | Periodical Restoration / Extension of D/S earthen temporary bund at Kot Mutraza Barrage | Gomal Zam Irrigation Division DIK | 0.3 | 0.3
118 | AOM&R of Gate equipment i/c other Electrical Mechanical, solar parts accessories and Generator repair/purchasing of all unit of mechanical installed at Barrage Kot Murtaza District Tank | Gomal Zam Irrigation Division DIK | 0.8 | 0.8
119 | Restoration of Occasional Breaches / Over Topping & strengthing of banks of RB Disty RD.00-10395 (m) Tail in reaches, Disty Khanwand RD.00-5249 (m) Tail in reaches & Disty D1R1 RD.00-10438 (m) Tail in reaches covering Main canal RD: 2741-22141 m in reaches. | Gomal Zam Irrigation Division DIK | 0.25 | 0.25
120 | Repair/Restoration of PCC Lining/Canal section of Main Canal RD:2741-22141(M) in reaches and R.B Disty RD:00- tail in reaches | Gomal Zam Irrigation Division DIK | 0.8 | 0.8
121 | Repair to Damaged Lining Pannels/Canal Section of Main canal RD: 22141-25000 m in reaches.& Disty No.1 RD.00-7500 (m) Tail in reaches, Disty No.2 RD.00-16694 (m) Tail in reaches & Disty No.3 RD.00-23990 (m) Tail in reaches . | Gomal Zam Irrigation Division DIK | 0.4 | 0.4
122 | Restoration of Occasional Breaches/Over Topping & strengthing of banks of Disty No.1 RD.00-7500 (m) Tail in reaches, Disty No.2 RD.00-16694 (m) Tail in reaches i/c Main canal RD: 22141-25000(m) in reaches, Disty No.3 RD.00-23990 (m) Tail in reaches. | Gomal Zam Irrigation Division DIK | 0.4 | 0.4
123 | Repair to Damaged PCC lining / Masonry Structure / Outlets of Waran Canal RD: 00+00-18+00 in reaches i/c Sheikh Sultan Minor ( 00-8+300) & Dabara Minor RD: 00-9+612) Pathar Minor (RD: 00-4+429) | Gomal Zam Irrigation Division DIK | 0.9 | 0.9
124 | Repair to Damaged PCC lining / Masonry Structure / Outlets of Waran Canal RD: 18+000-36+469, Deyal Minor ( RD: 00-11+214) & Fareed Abad Minor RD: 00-13+691) Manjhi Minor (RD: 00-10+395) Ranwal Minor RD: 00-10+194) & Azami Minor RD: 00-6+567) | Gomal Zam Irrigation Division DIK | 0.4 | 0.4
125 | Restoration of damaged PCC lining and Raising of Fareed abad Minor RD: 0-13+691 in reaches i/c Waran Canal RD: 18+00-36+469 in reaches. | Gomal Zam Irrigation Division DIK | 0.8 | 0.8
126 | Restoration of occasional breaches/over toping & strengthing of banks in Disty No.4 RD:00 to10131m (tail)& Disty No.5 RD:00 to 12711m in reaches. | Gomal Zam Irrigation Division DIK | 0.3 | 0.3
127 | Restoration of occasional breaches/over toping & strengthing of banks in Main canal RD:25000-33063m in reaches. | Gomal Zam Irrigation Division DIK | 0.2 | 0.2
128 | Emergent repair/De-siltation/Jungle clearance/ Damaged PCC lining / tempered outlets & masonry structure of Disty 5 i/c minors, i/c Main canal in Rohri Section. | Gomal Zam Irrigation Division DIK | 0.3 | 0.3
129 | Periodical Silt/Mud Clearance of excessively choked up Disty No.6 RD:00-tail in reaches & its minors other then closure period due to heavy silt load. | Gomal Zam Irrigation Division DIK | 0.4 | 0.4
130 | Emergent repair/De-siltation/Jungle clearance/ Damaged PCC lining / tempered outlets & masonry structure of various Distys/Minors i/c Main canal in Kulachi Section | Gomal Zam Irrigation Division DIK | 0.4 | 0.4
131 | Periodical Silt/Mud Clearance of Disty No.8, RD.11000-15800 (m), & Disty No.9 RD.00-500 & RD.3200-5872 (m). | Gomal Zam Irrigation Division DIK | 0.4 | 0.4
132 | Repair to eroded weak canal banks / rain cuts in Disty No.8, RD:00 to 15781m Disty No.9 RD:00 to 5872 m & Disty No.10, RD:00 to 13230m in reaches, Main canal RD: 45433-49623 m in reaches. | Gomal Zam Irrigation Division DIK | 0.3 | 0.3
133 | Emergent repair/De-siltation/Jungle clearance/ Damaged PCC lining / tempered oulets & masonry structure of various Distys/Minors i/c Main canal in Attal Sharif Section | Gomal Zam Irrigation Division DIK | 0.3 | 0.3
134 | Emergent repair/De-siltation/Jungle clearance/ Damaged PCC lining / tempered outlets & masonry structure of various Distys/Minors i/c Main canal in Potta Section | Gomal Zam Irrigation Division DIK | 0.4 | 0.4
135
136 | Desiltation / berm cutting/Jungle clearance of Disty No.04, RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 10.11 | 5964.26 | 5.64 | 3.95 | 4174.98 | 70% | Work is in progress.
137 | Desiltation / berm cutting/Jungle clearance of Disty No.5 & its Minor and sub Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 26.31 | 7688.07 | 8.2 | 5.17 | 4843.48 | 63% | Work is in progress.
138 | Desiltation / berm cutting/Jungle clearance of Dera Disty RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 16.7 | 5812.06 | 6.55 | 5.17 | 4591.53 | 79% | Work is in progress.
139 | Silt clearance/ jungle clearance of Muryali Minor RD. 00-15000 in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.64 | 4021.01 | 5.33 | 0 | 0 | 0% | Work is in progress.
140 | Silt clearance/ jungle clearance including removal of debris of Lachra Minor/Makali Minor in reaches. | CRBC Irrigation Division DIKhan | 0.25 | 0.23 | 3.92 | 2402.7 | 11.3 | 0.57 | 120.14 | 5% | Work is in progress.
141 | Desiltation / berm cutting/Jungle clearance of Mehmood Disty. RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.05 | 5737.19 | 4.42 | 3.54 | 4589.75 | 80% | Work is in progress.
142 | Desiltation / berm cutting/Jungle clearance of Nawab Minor RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.3 | 0.27 | 7.62 | 2952 | 2.59 | 1.99 | 2273.04 | 77% | work in progress
143 | Desiltation / berm cutting/Jungle clearance of Disty No.7, i/c Minors of Disty No.7 RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 30.53 | 7801.33 | 15.37 | 8.61 | 4368.74 | 56% | work in progress
144 | Desiltation / berm cutting/Jungle clearance of Disty No. 8 & 8-A, RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.29 | 3999 | 3.95 | 3.75 | 3799.05 | 95% | work in progress
145 | Desiltation / berm cutting/Jungle clearance of Disty No.9 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.71 | 3560.86 | 2.9 | 0.72 | 890.22 | 25% | work in progress
146 | Desiltation / berm cutting/Jungle clearance of Disty No.10 & 10/A RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11 | 3950.22 | 3.19 | 0.64 | 790.04 | 20% | yet to be started
147 | Desiltation / berm cutting/Jungle clearance of Disty No. 11 & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 9.1 | 5670.47 | 10.66 | 7.36 | 3912.62 | 69% | work in progress
148 | Desiltation / berm cutting/Jungle clearance of Disty No. 11-A, & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 21.86 | 7695.14 | 5.93 | 2.25 | 2924.15 | 38% | work in progress
149 | Desiltation / berm cutting/Jungle clearance of Disty No. 12 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.23 | 5762.51 | 4.11 | 3.66 | 5128.63 | 89% | work in progress
150 | Desiltation /Jungle Clearance of Disty # 13 & its System RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.675 | 0.6075 | 21.655 | 4256.03 | 4.66 | 4.38 | 4001 | 94% | Work is in progress.
151 | Shingling of CPR & Jungle Clearance of Disty # 14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.725 | 0.6525 | 21.616 | 4176.75 | 4.58 | 4.35 | 3968 | 95% | Work is in progress.
152 | Shingling of CPR & Jungle Clearance of MD-14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.433 | 2145.01 | 2.43 | 2.18 | 1931 | 90% | Work is in progress.
153 | Shingling of CPR & Jungle Clearance of Disty # 15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.7 | 0.63 | 21.494 | 3752 | 3.65 | 2.55 | 2626 | 70% | Work is in progress.
154 | Shingling of CPR & Jungle Clearance of MD-15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.325 | 0.2925 | 5.8384 | 1862.55 | 2.28 | 0 |  | 0% | Work not yet started.
155 | Shingling of CPR & Jungle Clearance of Disty 16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 12.75 |  | 2.43 | 0 |  | 0% | Work not yet started.
156 | Shingling of CPR & Jungle Clearance of Minor of Disty-16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.8445 |  | 2.45 | 0 |  | 0% | Work not yet started.
157 | Desiltation / Jungle Clearance of Disty # 17 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 9.6951 |  | 2.13 | 0 |  | 0% | Work not yet started.
158 | Shingling of CPR & Jungle Clearance of Disty # 18 its Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 18.009 |  | 4.26 | 0 |  | 0% | Work not yet started.
159 | Shingling of CPR & Jungle Clearance of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.55 | 0.495 | 15.753 |  | 3.96 | 0 |  | 0% | Work not yet started.
160 | Desiltation / Jungle Clearance of M-1 & M-2 of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.829 |  | 4 | 0 |  | 0% | Work not yet started.
161 | Removal of Heaps / Clearance of Bari Band Disty RD: 39+500-88+600 in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.33775 | 14.96 | 1435.76 | 8.21 | 7.85 | 1390 | 95.62% | Work in Progress (Work Stop due to Rain)
162 | Removal of Heaps / Clearance of Hero Shah Minor RD: 0 -38+000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 11.58 | 2446.93 | 11.58 | 10.75 | 2250 | 92.83% | Work in Progress (Work Stop due to Rain)
163 | Removal of Heaps / Clearance of Kalu Shah Disty and Dundian Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.1 | 0.098 | 7.69 | 785.8 | 5 | 5 | 785.8 | 100% | Completed
164 | Removal of Heaps / Clearance of Sarwala Disty and Lund Khwar Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 18.29 | 3172.99 | 10.06 | 10.06 | 3172.99 | 100% | Completed
165 | Removal of Heaps / Clearance of Said Abad Disty and Pir Abad Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 20.42 | 3113.1 | 7.31 | 7.31 | 3113.1 | 100% | Completed
166 | Removal of Heaps / Clearance of Katlang Disty from RD: 0-40+000 in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 12.19 | 1910.43 | 7.61 | 7.61 | 1910.43 | 100% | Completed
167 | Removal of Heaps / Clearance of Shamozai Disty/ Syphon and Likpani Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.392 | 17.67 | 2730.62 | 13.01 | 13.01 | 2730.62 | 100% | Completed
168 | Removal of Heaps / Clearance of Dheri Minor and Tail Minor Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.15 | 0.147 | 7.01 | 1211.68 | 6 | 6 | 1211.68 | 100% | Completed
169 | Bazai Main Canal Head Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 21 | 21 | 1168.075 | 100% | Completed
170 | Wartair Disty | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 6 | 587.93 | 6 | 6 | 587.93 | 100% | Completed
171 | Kharki Disty No. 02 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 3.3 | 1272.34 | 3.3 | 3.3 | 1272.34 | 100% | Completed
172 | Additional Minor No. 03, 06 and Bazai Disty No. 01. | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | 16.8 | 1272.14 | 3 | 3 | 1272.14 | 100% | Completed
173 | Bazai Main Canal, Syphon No. 4431, 5851, 12530, 13590, 14842, 18400, 47527 & 58853 | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | [5 empty] | 70% | Work in Progress (Work Stop due to Rain)
174 | Bazai Disty No. 04, Bazai Minor No. 09, 11 and 12. | Malakand Irrigation Division Malakand | 0.27 | 0.26625 | 15.2 | 4070 | 9 | 9 | 4070 | 100% | Completed
175 | Clearance of Syphon 79205, 93480 and 97962. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | [5 empty] | 20% | Work in Progress (Work Stop due to Rain)
176 | Bazai Disty No. 03 and Bazai Minor No. 05. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | 20.5 | 1907.82 | 7 | 7 | 1907.82 | 100% | Completed
177 | Bazai Main Canal Tail Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 0 | 0 | 0 | 0% | Not Yet start
178 | KM-1 RD: 0-2976 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 143.26 | 0.9 | 0.9 | 143.26 | 100% | Completed
179 | KM-1 RD: 0-1500, 22000-29000 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 410.62 | 2.6 | 2.6 | 410.62 | 100% | Completed
180 | Bazai Main Canal RD: 79500 to RD: 84500 | Malakand Irrigation Division Malakand | 0.302 | 0.296 | 39 | 649.87 | 1.5 | 1.4 | 606.52 | 93.33% | Work in Progress (Work Stop due to Rain)
181 | Silt & Shingle Clearance of P.C Minor from RD 0+000 To Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.388 | 12.881 | 1851.77 | 7.62 | 3.1 | 753.3 | 40.68% | Work in Progress (Work Stop due to Rain)
182 | Clearance of Shingri Minor from RD 0-17250 in reaches. | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.309 | 530.92 | 2.347 | 2.04 | 461.42 | 86.91% | Work in Progress (Work Stop due to Rain)
183 | Clearance of Meherdi Minor from RD 0-31000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 9.451 | 2167.5 | 8.382 | 6.113 | 1580.75 | 72.93% | Work in Progress (Work Stop due to Rain)
184 | Clearance of Kalu Branch from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.33 | 0.3218 | 11.563 | 1318.25 | 5 | 3.05 | 804.13 | 61% | Work in Progress (Work Stop due to Rain)
185 | Clearance of Hathian Minor from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.05 | 0.04875 | 2.35 |  |  | 0 | 0 | 0% | Not yet started
186 | Clearance of Jalala Disty from RD: 29000 to Tail in reaches | Malakand Irrigation Division Malakand | 0.37 | 0.3607 | 14.024 | 1476.73 | 5900 | 5400 | 1351.5 | 91.52% | Work in Progress (Work Stop due to Rain)
187 | Clearance of Pirsaddo Disty, Ghano Minor and Qutab Gharh Minor from : H-Tail to Tail in reaches. | Malakand Irrigation Division Malakand | 0.35 | 0.341 | 1.88 |  |  | 0 | 0 | 0% | Not yet started
188 | Clearance of Shergarh Minor from Head to Rd:12+000 in reaches. | Malakand Irrigation Division Malakand | 0.15 | 0.146 | 7.752 |  |  | 0 | 0 | 0% | Not yet started
189 | Clearance of Shergarh Minor from Rd:12+000 tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 7.752 | 1195.13 | 6000 | 5500 | 956.83 | 91.66% | Work in Progress (Work Stop due to Rain)
190 | Clearance of Spokanda Disty from RD: 18000 to Tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 5.659 |  |  | 0 | 0 | 0% | Not yet started
191 | Silt & Shingle Clearance of Spokanda Disty from 0-18000 | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.488 | 771.85 | 2.743 | 1.1 | 308.74 | 40% | Work in Progress (Work Stop due to Rain)
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086

## 10-02-2023
S# | Name of Canal | Name of Division | Estimated Cost(RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Total Quantity of Silt to be removed (m3) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Total Quantity of Silt removed till date (m3) | Progress Till date in % | Remarks
1 | Barwai Irrigation Canal | Swat Irrigation Division-II Matta | 0.3 | 0.2805 | 11.22 | 1300 | 6.1 | 6.1 | 1300 | 100% | Completed
2 | Shamizai Irrigation Canal | Swat Irrigation Division-II Matta | 1 | 0.779 | 20.73 | 5150 | 19.5 | 19.5 | 5150 | 100% | Completed
3 | Silt clearance of Sarai Saleh NPC Rd 0-10000 in reaches | Haripur Irrigation Division Haripur | 0.35 | 0.283 | 15.85 | 1271 | 3.04 | 3 | 1250 | 95% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
4 | Silt clearance of Sarai Saleh NPC Rd 10000-17000 i/c Minor No.1 in reaches | Haripur Irrigation Division Haripur | 0.3 | 0.24 | 15.85 | 1131.96 | 2.13 | 2.01 | 1095.23 | 95% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
5 | Silt clearance of Sarai Saleh NPC Rd 17000-30000 i/c Minor No.2 in reaches | Haripur Irrigation Division Haripur | 0.35 | 0.28 | 15.85 | 1347 | 3.96 | 2.05 | 750.32 | 50% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
6 | Clearance of Daur Main Canal Rd 0-tail | Haripur Irrigation Division Haripur | 0.15 | 0.1216 | 0.838 | 555.2 | 0.838 | 0.838 | 555.2 | 100% | Work completed
7 | Silt Clearance of Disty No.02 RD 0-20000 in reaches. | Haripur Irrigation Division Haripur | 0.25 | 0.2 | 6.62 | 1287.6 | 6.09 | 5.79 | 1210.58 | 95% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
8 | Silt Clearance of Main KRBC RD 11000-42000 in reaches | Haripur Irrigation Division Haripur | 0.25 | 0.225 | 12.8 | 1287.6 | 9.45 | 9.45 | 1287.6 | 100% | Work completed
9 | Silt Clearance Disty No.04 RD 0-24000 in reaches. | Haripur Irrigation Division Haripur | 0.3 | 0.24 | 7.31 | 1545.12 | 7.31 | 6.18 | 1382.99 | 85% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
10 | Silt Clearance of Disty No.03 i/c Ziarat Minor and Bandi Minor in reaches. | Haripur Irrigation Division Haripur | 0.3 | 0.24 | 10.67 | 1545.12 | 10.67 | 5.02 | 785.23 | 49% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
11 | Silt Clearance of Disty No.1 i/c Balartop & Kamalpur Minors in reaches. | haripur Irrigation Division Haripur | 0.3 | 0.24 | 10.36 | 1545.12 | 10.36 | 7.5 | 998.32 | 76% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
12 | Silt Clearance of KLBC Rd 0-26000 in reaches | haripur Irrigation Division Haripur | 0.3 | 0.24 | 7.92 | 1545.12 | 7.92 | 0 | 0 | 0 | not yet started due to decisiion made in meeting with XEN WAPDA, PMO and CDA Islambad authorities and work will be started from 15th February 2023
13 | Silt clearance of Sarai Saleh NPC Rd 30000-40000 i/c Minor No. 3 in reaches | HAripur Irrigation Division Haripur | 0.25 | 0.2 | 15.85 | 946 | 3.04 | 1.03 | 405.2 | 40% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
14 | Clearance of Main Rangila Irrigation system i/c Rangila Tank | Haripur Irrigation Division Haripur | 0.2 | 0.173 | 2.21 | 559 | 2.21 | 0.3 | 95.23 | 15% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
15 | Silt Clearance of Chak Muneem Minor. | Haripur Irrigation Division Haripur | 0.2 | 0.16 | 7.01 | 1030.8 | 7.01 | 1.25 | 110.3 | 15% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
16 | Silt clearance of Kharabara Dam Channel | Haripur Irrigation Division Haripur | 0.1 | 0.08 | 2.8 | 515.1 | 2.8 | 0.58 | 85.36 | 15% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
SWABI IRRIGATION DIVN-1
17 | Clearance from the bed of Jamal Garhi Disty from 00-tail in reaches. | Swabi Irrigation Division-I Swabi | 0.3 | 0.11 | 16.81 | 1692.37 | 4.7 | 4.5 | 1607.75 | 95% | In-progress
18 | Silt Clearance from the bed of Buxali Disty & Kot Minor from 00-tail in reaches | Swabi Irrigation Division-I Swabi | 0.65 | 0.36 | 21.34 | 4715.26 | 9.42 | 7.5 | 4385.19 | 93% | In-progress
20 | Removal of debris and heaps from Machai Branch RD 105+000 to 142+000 in reaches | Swabi Irrigation Division-I Swabi | 0.35 | 0.13 | 247.58 | 4521.89 | 0.48 | 0.3 | 3843.61 | 85% | In-progress
21 | Removal of debris and heaps from Machai Branch RD 142+000 to 186+000 in reaches | Swabi Irrigation Division-I Swabi | 0.35 | 0.13 | 247.58 | 4513.02 | 0.35 | 0.3 | 4422.76 | 98% | In-progress
22 | Silt Clearance from the bed of Chura Minor , Sawal Dher Minor & Mala Minor from RD: 00-tail in reaches. | Swabi Irrigation Division-I Swabi | 0.3 | 0.11 | 14.38 | 1698.88 | 7 | 5.4 | 1613.94 | 95% | In-progress
23 | Silt clearance from the bed Shahbaz Garhi Disty and its sub System from RD:00-tail in reaches | Swabi Irrigation Division-I Swabi | 0.8 | 0.44 | 18.29 | 4522.69 | 14.85 | 12.5 | 4160.87 | 92% | In-progress
24 | Silt Clearance from the bed of Ismalia Disty and its sub system from 00-tail in reaches | Swabi Irrigation Division-I Swabi | 0.9 | 0.5 | 18.29 | 6469.09 | 13.26 | 11.7 | 6275.02 | 97% | In-progress
25 | Silt Clearance from the bed of Adina Minor and adina Minor Branch from Head to tail in reaches | Swabi Irrigation Division-I Swabi | 0.35 | 0.19 | 7.89 | 1980.17 | 5.59 | 4.7 | 1861.36 | 94% | In-progress
26 | Silt Clearance of Machai Branch at RD: 186000-252000 in reaches | Swabi Irr:Divn-1 Swabi | 1 | 0.45 | 24.764 | 9344.56 | 3.2 | 3.2 | 8121 | 87% | In progress
27 | Silt Clearance of Kalu Khan Disty and its sub system from RD: 00-tail in reaches | Swabi Irr:Divn-1 Swabi | 1 | 0.45 | 53.87 | 8707 | 27.54 | 20.25 | 6313.95 | 73% | In progress
28 | Silt Clearance of Nawan Killi Minor ,Sarbandi Minor, Shagai Minor RD:00- tail in reaches | Swabi Irr:Divn-1 Swabi | 0.3 | 0.155 | 4.69 2.92 5.18 12.79 | 2288.51 | 8.8 | 5 | 1517.79 | 66% | In progress
29 | Silt Clearance of , Naranji Disty & Naranji Minor No.1 & 2 RD: 00-tail in reaches | Swabi Irr:Divn-1 Swabi | 0.3 | 0.15 | 10.3963 3.04 1.58 15.01 | 2465 | 9.14 | 4 | 1812.7 | 74% | In progress
30 | Silt Clearance of Old Indus branch & Zaida Minor RD:0-Tail in reaches | Swabi Irr:Divn-1 Swabi | 0.4 | 0.2 | 9.84 2.97 12.81 | 4193 | 8.84 | 4.88 | 4089.51 | 98% | In progress
31 | Silt Clearance of Pehur branch and its sub system RD:0-Tail in reaches | Swabi Irr:Divn-1 Swabi | 1 | 0.55 | 30.69 | 8240 | 15.85 | 10.36 | 7060.6 | 86% | In progress
32
33 | Name of Canal | Name of Division | Estimated Cost (RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km)
34 | GOMAL ZAM IRRIGATION DIVISION DIKHAN | Gomal Zam Irrigation Division DIK
35 | Periodical Restoration / Extension of D/S earthen temporary bund at Kot Mutraza Barrage | Gomal Zam Irrigation Division DIK | 0.3 | 0.3 | 0
36 | AOM&R of Gate equipment i/c other Electrical Mechanical, solar parts accessories and Generator repair/purchasing of all unit of mechanical installed at Barrage Kot Murtaza District Tank | Gomal Zam Irrigation Division DIK | 0.8 | 0.8 | 0
37 | Restoration of Occasional Breaches / Over Topping & strengthing of banks of RB Disty RD.00-10395 (m) Tail in reaches, Disty Khanwand RD.00-5249 (m) Tail in reaches & Disty D1R1 RD.00-10438 (m) Tail in reaches covering Main canal RD: 2741-22141 m in reaches. | Gomal Zam Irrigation Division DIK | 0.25 | 0.25 | 26.23
38 | Repair/Restoration of PCC Lining/Canal section of Main Canal RD:2741-22141(M) in reaches and R.B Disty RD:00- tail in reaches | Gomal Zam Irrigation Division DIK | 0.8 | 0.8 | 10.32
39 | Repair to Damaged Lining Pannels/Canal Section of Main canal RD: 22141-25000 m in reaches.& Disty No.1 RD.00-7500 (m) Tail in reaches, Disty No.2 RD.00-16694 (m) Tail in reaches & Disty No.3 RD.00-23990 (m) Tail in reaches . | Gomal Zam Irrigation Division DIK | 0.4 | 0.4 | 48.18
40 | Restoration of Occasional Breaches/Over Topping & strengthing of banks of Disty No.1 RD.00-7500 (m) Tail in reaches, Disty No.2 RD.00-16694 (m) Tail in reaches i/c Main canal RD: 22141-25000(m) in reaches, Disty No.3 RD.00-23990 (m) Tail in reaches. | Gomal Zam Irrigation Division DIK | 0.4 | 0.4 | 48.18
41 | Repair to Damaged PCC lining / Masonry Structure / Outlets of Waran Canal RD: 00+00-18+00 in reaches i/c Sheikh Sultan Minor ( 00-8+300) & Dabara Minor RD: 00-9+612) Pathar Minor (RD: 00-4+429) | Gomal Zam Irrigation Division DIK | 0.9 | 0.9 | 24.97
42 | Repair to Damaged PCC lining / Masonry Structure / Outlets of Waran Canal RD: 18+000-36+469, Deyal Minor ( RD: 00-11+214) & Fareed Abad Minor RD: 00-13+691) Manjhi Minor (RD: 00-10+395) Ranwal Minor RD: 00-10+194) & Azami Minor RD: 00-6+567) | Gomal Zam Irrigation Division DIK | 0.4 | 0.4 | 52.09
43 | Restoration of damaged PCC lining and Raising of Fareed abad Minor RD: 0-13+691 in reaches i/c Waran Canal RD: 18+00-36+469 in reaches. | Gomal Zam Irrigation Division DIK | 0.8 | 0.8 | 13.69
44 | Restoration of occasional breaches/over toping & strengthing of banks in Disty No.4 RD:00 to10131m (tail)& Disty No.5 RD:00 to 12711m in reaches. | Gomal Zam Irrigation Division DIK | 0.3 | 0.3 | 22.81
45 | Restoration of occasional breaches/over toping & strengthing of banks in Main canal RD:25000-33063m in reaches. | Gomal Zam Irrigation Division DIK | 0.2 | 0.2 | 8
46 | Emergent repair/De-siltation/Jungle clearance/ Damaged PCC lining / tempered outlets & masonry structure of Disty 5 i/c minors, i/c Main canal in Rohri Section. | Gomal Zam Irrigation Division DIK | 0.3 | 0.3 | 12.71
47 | Periodical Silt/Mud Clearance of excessively choked up Disty No.6 RD:00-tail in reaches & its minors other then closure period due to heavy silt load. | Gomal Zam Irrigation Division DIK | 0.4 | 0.4 | 32
48 | Emergent repair/De-siltation/Jungle clearance/ Damaged PCC lining / tempered outlets & masonry structure of various Distys/Minors i/c Main canal in Kulachi Section | Gomal Zam Irrigation Division DIK | 0.4 | 0.4 | 44
49 | Periodical Silt/Mud Clearance of Disty No.8, RD.11000-15800 (m), & Disty No.9 RD.00-500 & RD.3200-5872 (m). | Gomal Zam Irrigation Division DIK | 0.4 | 0.4 | 20
50 | Repair to eroded weak canal banks / rain cuts in Disty No.8, RD:00 to 15781m Disty No.9 RD:00 to 5872 m & Disty No.10, RD:00 to 13230m in reaches, Main canal RD: 45433-49623 m in reaches. | Gomal Zam Irrigation Division DIK | 0.3 | 0.3 | 34.91
51 | Emergent repair/De-siltation/Jungle clearance/ Damaged PCC lining / tempered oulets & masonry structure of various Distys/Minors i/c Main canal in Attal Sharif Section | Gomal Zam Irrigation Division DIK | 0.3 | 0.3 | 34.91
52 | Emergent repair/De-siltation/Jungle clearance/ Damaged PCC lining / tempered outlets & masonry structure of various Distys/Minors i/c Main canal in Potta Section | Gomal Zam Irrigation Division DIK | 0.4 | 0.4 | 26.15
53 | Silt clearance/removal of heaps of Disty No. 9 RD; 41000 to 85500 | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 13.41 | 599.93 | 1 | 1 | 599.93 | 100% | Completed
54 | Silt clearance of Power House Minor RD 0 to tail | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 1.28 | 599.9 | 1.28 | 1.25 | 585.84 | 98% | In progress
55 | Silt clearance of conduit covering portion of 2/9 Hoti Minor RD 4200 to 5000, 5800 to 7000 & 7200 to 7500 | Mardan Irrigation Division Mardan | 0.7 | 0.4546 | 0.7 | 745.53 | 0.7 | 0.65 | 692.28 | 93% | In progress
56 | Silt clearance of 2/9 Hoti Minor RD 0 to 4200, 5000 to 5800 & 7500 to 19000 | Mardan Irrigation Division Mardan | 0.8 | 0.5195 | 5.94 | 921.08 | 2.43 | 2.1 | 796 | 86% | In progress
57 | Silt clearance /removal of heaps of kalpani disty RD 0-51000 in reaches and clearance of syphones RD 10500 and 15000 | Mardan Irrigation Division Mardan | 0.7 | 0.4544 | 15.6 | 4463.54 | 5.07 | 5.07 | 4463.54 | 100% | Completed
58 | Silt clearance /removal of heaps of 1/kalpani Kodinaka Minor RD 0-27000 in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 8.22 | 599.94 | 1.82 | 1.62 | 534.01 | 89% | In progress
59 | Silt clearance /removal of heaps of 2/kalpani Taus Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 6.4 | 2801.12 | 5.5 | 5.5 | 2801.12 | 100% | Completed
60 | Silt clearance of 3/9 Toru Minor RD 0 to 15800 | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 4.81 | 2801.12 | 4.81 | 4.81 | 2801.12 | 100% | Completed
61 | Silt clearance of branch 2/kalpani Muhib Banda Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.175 | 0.1308 | 2.89 | 1633.98 | 2 | 2 | 1633.98 | 100% | Completed
62 | Silt Clearance of Maho Dheri Minor RD: 4000 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.1493 | 4.57 | 1138.2 | 3.35 | 3.35 | 1138.2 | 100% | Completed
63 | Silt Clearance of Rashakai Minor from RD: 7000 to 31000 in reaches | Mardan Irrigation Division Mardan | 0.6 | 0.3894 | 9.45 | 2972.29 | 7.31 | 7.31 | 2972.29 | 100% | Completed
64 | Silt Clearance of Nowshera Minor RD:0 - tail in reachers | Mardan Irrigation Division Mardan | 0.35 | 0.2613 | 5.18 | 2059.85 | 3.2 | 3.2 | 2059.85 | 100% | Completed
65 | Silt Clearance of Turlandi Minor Head to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 5.27 | 2134.4 | 4.71 | 4.71 | 2134.4 | 100% | Completed
66 | Silt Clearance of Khan Mahi Branch from RD: 0 to 3000 and RD: 8000 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 13.41 | 2344.08 | 5.48 | 5.48 | 2344.08 | 100% | Completed
67 | Silt Clearance of Bara Banda Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 3.04 | 1703.02 | 3.04 | 3.04 | 1703.02 | 100% | Completed
68 | Removal of heaps of Disty No. 8 RD: 52000 to 68000 in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 9.45 | 1860.72 | 1.43 | 1.43 | 1860.72 | 100% | Completed
69 | Silt Clearance/removal of heaps of Disty No. 7 at RD: 4000 to 14000 in reaches | Mardan Irrigation Division Mardan | 0.15 | 0.1133 | 4.26 | 1400.56 | 3.04 | 3.04 | 1400.56 | 100% | Completed
70 | Silt Clearance/removal of heaps of Sheikh yousaf Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 5.48 | 239.97 | 2.13 | 2.13 | 239.97 | 100% | Completed
71 | Silt Clearance/removal of heaps of 1/9 Guide Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 7 | 479.94 | 2.74 | 2.74 | 479.94 | 100% | Completed
72 | Silt Clearance/removal of heaps of Koragh Branch RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 14.93 | 479.94 | 2.23 | 2.23 | 479.94 | 100% | Completed
73 | Removal of heaps of Disty No.8 RD: 0 to 38000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 11.58 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
74 | Removal of heaps of Disty No.9 RD: 0 to 41000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 12.5 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
75 | Silt Clearance of Disty No.6 from RD: 55+000 to 60+000 in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.183 | 0.155 | 22.25 |  | 0.61 | 0.61 |  | 100% | Completed
76 | Silt Clearance of Disty No.6 from RD: 60+000 to 65+000 in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.157 | 0.133 | 22.25 |  | 0.45 | 0.45 |  | 100% | Completed
77 | Silt Clearance of Disty No.6 from RD: 65+000 to 73+000 in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.2 | 0.169 | 22.25 |  | 0.61 | 0.61 |  | 100% | Completed
78 | Silt Clearance of Nisatta Branch from RD: 0+000 to Tail in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.336 | 0.284 | 11.88 |  | 1 | 0.85 |  | 85% | Work in progress
79 | Silt Clearance of Nisatta Minor from RD: 0+000 to Tail in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.218 | 0.184 | 3.35 |  | 2 | 1.8 |  | 90% | Work in progress
80 | Silt Clearance of Palosa Minor from RD: 0+000 to Tail in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.253 | 0.214 | 5.03 |  | 1.35 | 1.215 |  | 90% | Work in progress
81 | Silt Clearance of Zardad and Kheshki Branch in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.348 | 0.294 | 14.49 |  | 7 | 6.3 |  | 90% | Work in progress
82 | Nipki Khel Irrigation Scheme | Swat Irrigation Division -I | 2.2 | 1.76 | 38.87 | 10172.62 | 38.87 | 20.3354 | 5336 | 52.32% | Work is in progress
83 | Desiltation / berm cutting/Jungle clearance of Disty No.04, RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 10.11 | 5964.26 | 5.64 | 3.95 | 4174.98 | 70% | Work is in progress.
84 | Desiltation / berm cutting/Jungle clearance of Disty No.5 & its Minor and sub Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 26.31 | 7688.07 | 8.2 | 5.82 | 5458.53 | 71% | Work is in progress.
85 | Desiltation / berm cutting/Jungle clearance of Dera Disty RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 16.7 | 5812.06 | 6.55 | 5.17 | 4591.53 | 79% | Work is in progress.
86 | Silt clearance/ jungle clearance of Muryali Minor RD. 00-15000 in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.64 | 4021.01 | 5.33 | 0 | 0 | 0% | Work is in progress.
87 | Silt clearance/ jungle clearance including removal of debris of Lachra Minor/Makali Minor in reaches. | CRBC Irrigation Division DIKhan | 0.25 | 0.23 | 3.92 | 2402.7 | 11.3 | 0.57 | 120.14 | 5% | Work is in progress.
88 | Desiltation / berm cutting/Jungle clearance of Mehmood Disty. RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.05 | 5737.19 | 4.42 | 3.54 | 4589.75 | 80% | Work is in progress.
89 | Desiltation / berm cutting/Jungle clearance of Nawab Minor RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.3 | 0.27 | 7.62 | 2952 | 2.59 | 1.99 | 2273.04 | 77% | work in progress
90 | Desiltation / berm cutting/Jungle clearance of Disty No.7, i/c Minors of Disty No.7 RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 30.53 | 7801.33 | 15.37 | 8.61 | 4368.74 | 56% | work in progress
91 | Desiltation / berm cutting/Jungle clearance of Disty No. 8 & 8-A, RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.29 | 3999 | 3.95 | 3.75 | 3799.05 | 95% | work in progress
92 | Desiltation / berm cutting/Jungle clearance of Disty No.9 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.71 | 3560.86 | 2.9 | 0.72 | 890.22 | 25% | work in progress
93 | Desiltation / berm cutting/Jungle clearance of Disty No.10 & 10/A RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11 | 3950.22 | 3.19 | 0.96 | 1185.07 | 30% | yet to be started
94 | Desiltation / berm cutting/Jungle clearance of Disty No. 11 & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 9.1 | 5670.47 | 10.66 | 7.36 | 3912.62 | 69% | work in progress
95 | Desiltation / berm cutting/Jungle clearance of Disty No. 11-A, & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 21.86 | 7695.14 | 5.93 | 2.25 | 2924.15 | 38% | work in progress
96 | Desiltation / berm cutting/Jungle clearance of Disty No. 12 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.23 | 5762.51 | 4.11 | 3.66 | 5128.63 | 89% | work in progress
97 | Desiltation /Jungle Clearance of Disty # 13 & its System RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.675 | 0.6075 | 21.655 | 4256.03 | 4.66 | 4.38 | 4001 | 94% | Work is in progress.
98 | Shingling of CPR & Jungle Clearance of Disty # 14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.725 | 0.6525 | 21.616 | 4176.75 | 4.58 | 4.35 | 3968 | 95% | Work is in progress.
99 | Shingling of CPR & Jungle Clearance of MD-14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.433 | 2145.01 | 2.43 | 2.18 | 1931 | 90% | Work is in progress.
100 | Shingling of CPR & Jungle Clearance of Disty # 15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.7 | 0.63 | 21.494 | 3752 | 3.65 | 2.55 | 2626 | 70% | Work is in progress.
101 | Shingling of CPR & Jungle Clearance of MD-15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.325 | 0.2925 | 5.8384 | 1862.55 | 2.28 | 0 |  | 0% | Work not yet started.
102 | Shingling of CPR & Jungle Clearance of Disty 16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 12.75 |  | 2.43 | 0 |  | 0% | Work not yet started.
103 | Shingling of CPR & Jungle Clearance of Minor of Disty-16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.8445 |  | 2.45 | 0 |  | 0% | Work not yet started.
104 | Desiltation / Jungle Clearance of Disty # 17 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 9.6951 |  | 2.13 | 0 |  | 0% | Work not yet started.
105 | Shingling of CPR & Jungle Clearance of Disty # 18 its Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 18.009 |  | 4.26 | 0 |  | 0% | Work not yet started.
106 | Shingling of CPR & Jungle Clearance of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.55 | 0.495 | 15.753 |  | 3.96 | 0 |  | 0% | Work not yet started.
107 | Desiltation / Jungle Clearance of M-1 & M-2 of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.829 |  | 4 | 0 |  | 0% | Work not yet started.
108 | Silt Clearance of Lower Siran Canal RD 0-14000 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3110.16 | 3.04 | 1.402 | 1699.37 | 55% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
109 | Silt Clearance of Lower Siran Canal RD 14000-36500 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3142.51 | 4.26 | 1.8286 | 1430.82 | 46% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
110 | Silt Clearance of Lower Siran Canal Hathi Maira Branch & Gandian Minor RD 36500 in reaches | Mansehra Irrigation Division Mansehra | 0.55 | 0.4954 | 26.21 | 2080.06 | 12.1 | 3.7887 | 1218.14 | 59% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
111 | Silt Clearance of Ichar Canal/ Kalghan Minor RD 0-tail in reaches | Mansehra Irrigation Division Mansehra | 0.25 | 0.2254 | 5.97 | 1197.78 | 5.66 | 0.8534 | 79.28 | 7% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
112 | Silt Clearance of Upper Siran Canal from RD 0-30000 In reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2065 | 3.048 | 1.0515 | 374.96 | 18% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
113 | Silt Clearance of Upper Siran Canal from RD 30000-61000 in reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2110 | 9.44 | 5 | 1576 | 75% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
114 | Silt Clearance of Upper Siran Canal from RD 61000-tail in reaches | Mansehra Irrigation Division Mansehra | 0.18 | 0.1623 | 23.86 | 930 | 5.27 | 1.264 | 240.26 | 26% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
115 | Silt Clearance of Dhodial Minor Upper Siran Canal in reaches | Mansehra Irrigation Division Mansehra | 0.22 | 0.1981 | 5.24 | 1135 | 5.24 | 2.7017 | 579.76 | 51% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
116 | Removal of Heaps / Clearance of Bari Band Disty RD: 39+500-88+600 in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.33775 | 14.96 | 1435.76 | 8.21 | 7.85 | 1390 | 95.62% | Work in Progress (Work Stop due to Rain)
117 | Removal of Heaps / Clearance of Hero Shah Minor RD: 0 -38+000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 11.58 | 2446.93 | 11.58 | 10.75 | 2250 | 92.83% | Work in Progress (Work Stop due to Rain)
118 | Removal of Heaps / Clearance of Kalu Shah Disty and Dundian Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.1 | 0.098 | 7.69 | 785.8 | 5 | 5 | 785.8 | 100% | Completed
119 | Removal of Heaps / Clearance of Sarwala Disty and Lund Khwar Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 18.29 | 3172.99 | 10.06 | 10.06 | 3172.99 | 100% | Completed
120 | Removal of Heaps / Clearance of Said Abad Disty and Pir Abad Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 20.42 | 3113.1 | 7.31 | 7.31 | 3113.1 | 100% | Completed
121 | Removal of Heaps / Clearance of Katlang Disty from RD: 0-40+000 in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 12.19 | 1910.43 | 7.61 | 7.61 | 1910.43 | 100% | Completed
122 | Removal of Heaps / Clearance of Shamozai Disty/ Syphon and Likpani Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.392 | 17.67 | 2730.62 | 13.01 | 13.01 | 2730.62 | 100% | Completed
123 | Removal of Heaps / Clearance of Dheri Minor and Tail Minor Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.15 | 0.147 | 7.01 | 1211.68 | 6 | 6 | 1211.68 | 100% | Completed
124 | Bazai Main Canal Head Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 10.5 | 10.5 | 1168.075 | 100% | Completed
125 | Wartair Disty | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 6 | 587.93 | 6 | 6 | 587.93 | 100% | Completed
126 | Kharki Disty No. 02 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 3.3 | 1272.34 | 3.3 | 3.3 | 1272.34 | 100% | Completed
127 | Additional Minor No. 03, 06 and Bazai Disty No. 01. | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | 16.8 | 1272.14 | 3 | 3 | 1272.14 | 100% | Completed
128 | Bazai Main Canal, Syphon No. 4431, 5851, 12530, 13590, 14842, 18400, 47527 & 58853 | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | [5 empty] | 70% | Work in Progress (Work Stop due to Rain)
129 | Bazai Disty No. 04, Bazai Minor No. 09, 11 and 12. | Malakand Irrigation Division Malakand | 0.27 | 0.26625 | 15.2 | 4070 | 9 | 9 | 4070 | 100% | Completed
130 | Clearance of Syphon 79205, 93480 and 97962. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | [5 empty] | 20% | Work in Progress (Work Stop due to Rain)
131 | Bazai Disty No. 03 and Bazai Minor No. 05. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | 20.5 | 1907.82 | 7 | 7 | 1907.82 | 100% | Completed
132 | Bazai Main Canal Tail Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 4.78 | 0 | 0 | 0% | Not Yet start
133 | KM-1 RD: 0-2976 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 143.26 | 0.9 | 0.9 | 143.26 | 100% | Completed
134 | KM-1 RD: 0-1500, 22000-29000 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 410.62 | 2.6 | 2.6 | 410.62 | 100% | Completed
135 | Bazai Main Canal RD: 79500 to RD: 84500 | Malakand Irrigation Division Malakand | 0.302 | 0.296 | 39 | 649.87 | 1.5 | 1.4 | 606.52 | 93.33% | Work in Progress (Work Stop due to Rain)
136 | Silt & Shingle Clearance of P.C Minor from RD 0+000 To Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.388 | 12.881 | 1851.77 | 7.62 | 3.1 | 753.3 | 40.68% | Work in Progress (Work Stop due to Rain)
137 | Clearance of Shingri Minor from RD 0-17250 in reaches. | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.309 | 530.92 | 2.347 | 2.04 | 461.42 | 86.91% | Work in Progress (Work Stop due to Rain)
138 | Clearance of Meherdi Minor from RD 0-31000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 9.451 | 2167.5 | 8.382 | 6.113 | 1580.75 | 72.93% | Work in Progress (Work Stop due to Rain)
139 | Clearance of Kalu Branch from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.33 | 0.3218 | 11.563 | 1318.25 | 5 | 3.05 | 804.13 | 61% | Work in Progress (Work Stop due to Rain)
140 | Clearance of Hathian Minor from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.05 | 0.04875 | 2.35 |  |  | 0 | 0 | 0% | Not yet started
141 | Clearance of Jalala Disty from RD: 29000 to Tail in reaches | Malakand Irrigation Division Malakand | 0.37 | 0.3607 | 14.024 | 1476.73 | 5900 | 5400 | 1351.5 | 91.52% | Work in Progress (Work Stop due to Rain)
142 | Clearance of Pirsaddo Disty, Ghano Minor and Qutab Gharh Minor from : H-Tail to Tail in reaches. | Malakand Irrigation Division Malakand | 0.35 | 0.341 | 1.88 |  |  | 0 | 0 | 0% | Not yet started
143 | Clearance of Shergarh Minor from Head to Rd:12+000 in reaches. | Malakand Irrigation Division Malakand | 0.15 | 0.146 | 7.752 |  |  | 0 | 0 | 0% | Not yet started
144 | Clearance of Shergarh Minor from Rd:12+000 tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 7.752 | 1195.13 | 6000 | 5500 | 956.83 | 91.66% | Work in Progress (Work Stop due to Rain)
145 | Clearance of Spokanda Disty from RD: 18000 to Tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 5.659 |  |  | 0 | 0 | 0% | Not yet started
146 | Silt & Shingle Clearance of Spokanda Disty from 0-18000 | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.488 | 771.85 | 2.743 | 1.1 | 308.74 | 40% | Work in Progress (Work Stop due to Rain)
145 | Silt Clearance of Badwan Kharif Irrigation Scheme at RD 0+00 To Tail. | Chakdara Irrigation Sub Division ,Dir Division | 0.9 | 0.8957 | 22.18 | 4635.35 | 22.18 | 9.6 | 2689.19 | 58.01% | Work is in progress (Today Desiltation is Stope Due To Friday)
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086

## 11-02-2023
S# | Name of Canal | Name of Division | Estimated Cost(RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Total Quantity of Silt to be removed (m3) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Total Quantity of Silt removed till date (m3) | Progress Till date in % | Remarks
1 | Barwai Irrigation Canal | Swat Irrigation Division-II Matta | 0.3 | 0.2805 | 11.22 | 1300 | 6.1 | 6.1 | 1300 | 100% | Completed
2 | Shamizai Irrigation Canal | Swat Irrigation Division-II Matta | 1 | 0.779 | 20.73 | 5150 | 19.5 | 19.5 | 5150 | 100% | Completed
3 | Removal of Heaps / Clearance of Bari Band Disty RD: 39+500-88+600 in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.33775 | 14.96 | 1435.76 | 8.21 | 7.95 | 1400 | 96.83% | Work in Progress
4 | Removal of Heaps / Clearance of Hero Shah Minor RD: 0 -38+000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 11.58 | 2446.93 | 11.58 | 10.85 | 2300 | 93.7% | Work in Progress
5 | Removal of Heaps / Clearance of Kalu Shah Disty and Dundian Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.1 | 0.098 | 7.69 | 785.8 | 5 | 5 | 785.8 | 100% | Completed
6 | Removal of Heaps / Clearance of Sarwala Disty and Lund Khwar Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 18.29 | 3172.99 | 10.06 | 10.06 | 3172.99 | 100% | Completed
7 | Removal of Heaps / Clearance of Said Abad Disty and Pir Abad Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 20.42 | 3113.1 | 7.31 | 7.31 | 3113.1 | 100% | Completed
8 | Removal of Heaps / Clearance of Katlang Disty from RD: 0-40+000 in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 12.19 | 1910.43 | 7.61 | 7.61 | 1910.43 | 100% | Completed
9 | Removal of Heaps / Clearance of Shamozai Disty/ Syphon and Likpani Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.392 | 17.67 | 2730.62 | 13.01 | 13.01 | 2730.62 | 100% | Completed
10 | Removal of Heaps / Clearance of Dheri Minor and Tail Minor Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.15 | 0.147 | 7.01 | 1211.68 | 6 | 6 | 1211.68 | 100% | Completed
11 | Bazai Main Canal Head Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 10.5 | 10.5 | 1168.075 | 100% | Completed
12 | Wartair Disty | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 6 | 587.93 | 6 | 6 | 587.93 | 100% | Completed
13 | Kharki Disty No. 02 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 3.3 | 1272.34 | 3.3 | 3.3 | 1272.34 | 100% | Completed
14 | Additional Minor No. 03, 06 and Bazai Disty No. 01. | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | 16.8 | 1272.14 | 3 | 3 | 1272.14 | 100% | Completed
15 | Bazai Main Canal, Syphon No. 4431, 5851, 12530, 13590, 14842, 18400, 47527 & 58853 | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | [5 empty] | 70% | Work in Progress
16 | Bazai Disty No. 04, Bazai Minor No. 09, 11 and 12. | Malakand Irrigation Division Malakand | 0.27 | 0.26625 | 15.2 | 4070 | 9 | 9 | 4070 | 100% | Completed
17 | Clearance of Syphon 79205, 93480 and 97962. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | [5 empty] | 20% | Work in Progress
18 | Bazai Disty No. 03 and Bazai Minor No. 05. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | 20.5 | 1907.82 | 7 | 7 | 1907.82 | 100% | Completed
19 | Bazai Main Canal Tail Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 4.78 | 0 | 0 | 0% | Not Yet start
20 | KM-1 RD: 0-2976 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 143.26 | 0.9 | 0.9 | 143.26 | 100% | Completed
21 | KM-1 RD: 0-1500, 22000-29000 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 410.62 | 2.6 | 2.6 | 410.62 | 100% | Completed
22 | Bazai Main Canal RD: 79500 to RD: 84500 | Malakand Irrigation Division Malakand | 0.302 | 0.296 | 39 | 649.87 | 1.5 | 1.4 | 606.52 | 93.33% | Work in Progress
23 | Silt & Shingle Clearance of P.C Minor from RD 0+000 To Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.388 | 12.881 | 1851.77 | 7.62 | 4.1 | 996.25 | 53.8% | Work in Progress
24 | Clearance of Shingri Minor from RD 0-17250 in reaches. | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.309 | 530.92 | 2.347 | 2.12 | 479.52 | 90.32% | Work in Progress
25 | Clearance of Meherdi Minor from RD 0-31000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 9.451 | 2167.5 | 8.382 | 6.21 | 1605.68 | 74.08% | Work in Progress
26 | Clearance of Kalu Branch from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.33 | 0.3218 | 11.563 | 1318.25 | 5 | 4.6 | 1212.79 | 92% | Work in Progress
27 | Clearance of Hathian Minor from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.05 | 0.04875 | 2.35 |  |  | 0 | 0 | 0% | Not yet started
28 | Clearance of Jalala Disty from RD: 29000 to Tail in reaches | Malakand Irrigation Division Malakand | 0.37 | 0.3607 | 14.024 | 1476.73 | 5900 | 5400 | 1351.5 | 91.52% | Work in Progress
29 | Clearance of Pirsaddo Disty, Ghano Minor and Qutab Gharh Minor from : H-Tail to Tail in reaches. | Malakand Irrigation Division Malakand | 0.35 | 0.341 | 1.88 |  |  | 0 | 0 | 0% | Not yet started
30 | Clearance of Shergarh Minor from Head to Rd:12+000 in reaches. | Malakand Irrigation Division Malakand | 0.15 | 0.146 | 7.752 |  |  | 0 | 0 | 0% | Not yet started
31 | Clearance of Shergarh Minor from Rd:12+000 tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 7.752 | 1195.13 | 6000 | 5500 | 956.83 | 91.66% | Work in Progress
32 | Clearance of Spokanda Disty from RD: 18000 to Tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 5.659 |  |  | 0 | 0 | 0% | Not yet started
33 | Silt & Shingle Clearance of Spokanda Disty from 0-18000 | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.488 | 771.85 | 2.743 | 1.34 | 378.2 | 48.85% | Work in Progress
34 | Silt clearance/removal of heaps of Disty No. 9 RD; 41000 to 85500 | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 13.41 | 599.93 | 1 | 1 | 599.93 | 100% | Completed
35 | Silt clearance of Power House Minor RD 0 to tail | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 1.28 | 599.9 | 1.28 | 1.25 | 585.84 | 98% | In progress
36 | Silt clearance of conduit covering portion of 2/9 Hoti Minor RD 4200 to 5000, 5800 to 7000 & 7200 to 7500 | Mardan Irrigation Division Mardan | 0.7 | 0.4546 | 0.7 | 745.53 | 0.7 | 0.67 | 713.58 | 96% | In progress
37 | Silt clearance of 2/9 Hoti Minor RD 0 to 4200, 5000 to 5800 & 7500 to 19000 | Mardan Irrigation Division Mardan | 0.8 | 0.5195 | 5.94 | 921.08 | 2.43 | 2.25 | 852.85 | 93% | In progress
38 | Silt clearance /removal of heaps of kalpani disty RD 0-51000 in reaches and clearance of syphones RD 10500 and 15000 | Mardan Irrigation Division Mardan | 0.7 | 0.4544 | 15.6 | 4463.54 | 5.07 | 5.07 | 4463.54 | 100% | Completed
39 | Silt clearance /removal of heaps of 1/kalpani Kodinaka Minor RD 0-27000 in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 8.22 | 599.94 | 1.82 | 1.62 | 534.01 | 89% | In progress
40 | Silt clearance /removal of heaps of 2/kalpani Taus Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 6.4 | 2801.12 | 5.5 | 5.5 | 2801.12 | 100% | Completed
41 | Silt clearance of 3/9 Toru Minor RD 0 to 15800 | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 4.81 | 2801.12 | 4.81 | 4.81 | 2801.12 | 100% | Completed
42 | Silt clearance of branch 2/kalpani Muhib Banda Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.175 | 0.1308 | 2.89 | 1633.98 | 2 | 2 | 1633.98 | 100% | Completed
43 | Silt Clearance of Maho Dheri Minor RD: 4000 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.1493 | 4.57 | 1138.2 | 3.35 | 3.35 | 1138.2 | 100% | Completed
44 | Silt Clearance of Rashakai Minor from RD: 7000 to 31000 in reaches | Mardan Irrigation Division Mardan | 0.6 | 0.3894 | 9.45 | 2972.29 | 7.31 | 7.31 | 2972.29 | 100% | Completed
45 | Silt Clearance of Nowshera Minor RD:0 - tail in reachers | Mardan Irrigation Division Mardan | 0.35 | 0.2613 | 5.18 | 2059.85 | 3.2 | 3.2 | 2059.85 | 100% | Completed
46 | Silt Clearance of Turlandi Minor Head to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 5.27 | 2134.4 | 4.71 | 4.71 | 2134.4 | 100% | Completed
47 | Silt Clearance of Khan Mahi Branch from RD: 0 to 3000 and RD: 8000 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 13.41 | 2344.08 | 5.48 | 5.48 | 2344.08 | 100% | Completed
48 | Silt Clearance of Bara Banda Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 3.04 | 1703.02 | 3.04 | 3.04 | 1703.02 | 100% | Completed
49 | Removal of heaps of Disty No. 8 RD: 52000 to 68000 in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 9.45 | 1860.72 | 1.43 | 1.43 | 1860.72 | 100% | Completed
50 | Silt Clearance/removal of heaps of Disty No. 7 at RD: 4000 to 14000 in reaches | Mardan Irrigation Division Mardan | 0.15 | 0.1133 | 4.26 | 1400.56 | 3.04 | 3.04 | 1400.56 | 100% | Completed
51 | Silt Clearance/removal of heaps of Sheikh yousaf Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 5.48 | 239.97 | 2.13 | 2.13 | 239.97 | 100% | Completed
52 | Silt Clearance/removal of heaps of 1/9 Guide Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 7 | 479.94 | 2.74 | 2.74 | 479.94 | 100% | Completed
53 | Silt Clearance/removal of heaps of Koragh Branch RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 14.93 | 479.94 | 2.23 | 2.23 | 479.94 | 100% | Completed
54 | Removal of heaps of Disty No.8 RD: 0 to 38000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 11.58 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
55 | Removal of heaps of Disty No.9 RD: 0 to 41000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 12.5 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
56 | Silt Clearance of Lower Siran Canal RD 0-14000 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3110.16 | 3.04 | 1.8592 | 1869.27 | 60% | In progress
57 | Silt Clearance of Lower Siran Canal RD 14000-36500 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3142.51 | 4.26 | 2.3772 | 1572.405 | 50% | In progress
58 | Silt Clearance of Lower Siran Canal Hathi Maira Branch & Gandian Minor RD 36500 in reaches | Mansehra Irrigation Division Mansehra | 0.55 | 0.4954 | 26.21 | 2080.06 | 12.1 | 7.9035 | 1331.408 | 64% | In progress
59 | Silt Clearance of Ichar Canal/ Kalghan Minor RD 0-tail in reaches | Mansehra Irrigation Division Mansehra | 0.25 | 0.2254 | 5.97 | 1197.78 | 5.66 | 2.0726 | 362.45 | 30% | In progress
60 | Silt Clearance of Upper Siran Canal from RD 0-30000 In reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2065 | 3.048 | 1.5087 | 828.032 | 40% | In progress
61 | Silt Clearance of Upper Siran Canal from RD 30000-61000 in reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2110 | 9.44 | 6.8288 | 1745.902 | 83% | In progress
62 | Silt Clearance of Upper Siran Canal from RD 61000-tail in reaches | Mansehra Irrigation Division Mansehra | 0.18 | 0.1623 | 23.86 | 930 | 5.27 | 2.1784 | 410.162 | 44% | In progress
63 | Silt Clearance of Dhodial Minor Upper Siran Canal in reaches | Mansehra Irrigation Division Mansehra | 0.22 | 0.1981 | 5.24 | 1135 | 5.24 | 3.4637 | 650.5525 | 57% | In progress
64 | Jue Shiekh Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 16.29 | 13.03 | 53.35 | 132353 | 53.35 | 53.35 | 132353 | 100% | Completed
65 | Jue Zardad Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 3.6 | 2.88 | 13.1 | 18500 | 13.1 | 13.1 | 18500 | 100% | Completed
66 | Kabul River Canal | Peshawar Canal Division, Peshawar (Kabaul River Canal Sub Division) | 27.855 | 22.284 | 60.35 | 1062085 | 60.35 | 43.2 | 760304 | 72% | Work is in progress
67 | Hazar Khwani Branch | Peshawar Canal Division, Peshawar (Kabul River Canal Sub Division) | 23.2 | 18.56 | 28.04 | 1016303 | 28.04 | 27.7 | 1003980 | 99% | Work is in progress
68 | Nipki Khel Irrigation Scheme | Swat Irrigation Division -I | 2.2 | 1.76 | 38.87 | 10172.62 | 38.87 | 21.7378 | 5704 | 55.92% | Work is in progress
17 | Silt Clearance of Badwan Kharif Irrigation Scheme at RD 0+00 To Tail. | Chakdara Irrigation Sub Division ,Dir Division | 0.9 | 0.8957 | 22.18 | 4635.35 | 22.18 | 9.6 | 2689.19 | 58.01% | Work is in progress (Today Desiltation is Stope Due To Rain)
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086

## 12-02-2023
S# | Name of Canal | Name of Division | Estimated Cost(RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Total Quantity of Silt to be removed (m3) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Total Quantity of Silt removed till date (m3) | Progress Till date in % | Remarks
1 | Shamizai Irrigation Canal | Swat Irrigation Division-II Matta | 1 | 0.779 | 20.73 | 5150 | 19.5 | 19.5 | 5150 | 100% | Completed
2 | Barwai Irrigation Canal | Swat Irrigation Division-II Matta | 0.3 | 0.2805 | 11.22 | 1300 | 6.1 | 6.1 | 1300 | 100% | Completed
3 | Silt clearance of Sarai Saleh NPC Rd 0-10000 in reaches | Haripur Irrigation Division Haripur | 0.35 | 0.283 | 15.85 | 1271 | 3.04 | 3 | 1250 | 95% | Work is in progress
4 | Silt clearance of Sarai Saleh NPC Rd 10000-17000 i/c Minor No.1 in reaches | Haripur Irrigation Division Haripur | 0.3 | 0.24 | 15.85 | 1131.96 | 2.13 | 2.01 | 1095.23 | 95% | Work is in progress
5 | Silt clearance of Sarai Saleh NPC Rd 17000-30000 i/c Minor No.2 in reaches | Haripur Irrigation Division Haripur | 0.35 | 0.28 | 15.85 | 1347 | 3.96 | 3.56 | 1298.99 | 95% | Work is in progress
6 | Clearance of Daur Main Canal Rd 0-tail | Haripur Irrigation Division Haripur | 0.15 | 0.1216 | 0.838 | 555.2 | 0.838 | 0.838 | 555.2 | 100% | Work completed
7 | Silt Clearance of Disty No.02 RD 0-20000 in reaches. | Haripur Irrigation Division Haripur | 0.25 | 0.2 | 6.62 | 1287.6 | 6.09 | 5.79 | 1210.58 | 95% | Work is in progress
8 | Silt Clearance of Main KRBC RD 11000-42000 in reaches | Haripur Irrigation Division Haripur | 0.25 | 0.225 | 12.8 | 1287.6 | 9.45 | 9.45 | 1287.6 | 100% | Work completed
9 | Silt Clearance Disty No.04 RD 0-24000 in reaches. | Haripur Irrigation Division Haripur | 0.3 | 0.24 | 7.31 | 1545.12 | 7.31 | 6.18 | 1382.99 | 85% | Work is in progress
10 | Silt Clearance of Disty No.03 i/c Ziarat Minor and Bandi Minor in reaches. | Haripur Irrigation Division Haripur | 0.3 | 0.24 | 10.67 | 1545.12 | 10.67 | 5.02 | 785.23 | 49% | Work is in progress
11 | Silt Clearance of Disty No.1 i/c Balartop & Kamalpur Minors in reaches. | haripur Irrigation Division Haripur | 0.3 | 0.24 | 10.36 | 1545.12 | 10.36 | 7.5 | 998.32 | 76% | Work is in progress
12 | Silt Clearance of KLBC Rd 0-26000 in reaches | haripur Irrigation Division Haripur | 0.3 | 0.24 | 7.92 | 1545.12 | 7.92 | 0 | 0 | 0 | not yet started due to decisiion made in meeting with XEN WAPDA, PMO and CDA Islambad authorities and work will be started from 15th February 2023
13 | Silt clearance of Sarai Saleh NPC Rd 30000-40000 i/c Minor No. 3 in reaches | HAripur Irrigation Division Haripur | 0.25 | 0.2 | 15.85 | 946 | 3.04 | 1.9 | 523.54 | 60% | Work is in progress
14 | Clearance of Main Rangila Irrigation system i/c Rangila Tank | Haripur Irrigation Division Haripur | 0.2 | 0.173 | 2.21 | 559 | 2.21 | 1.07 | 222.65 | 40% | Work is in progress
15 | Silt Clearance of Chak Muneem Minor. | Haripur Irrigation Division Haripur | 0.2 | 0.16 | 7.01 | 1030.8 | 7.01 | 2.04 | 375.58 | 35% | Work is in progress
16 | Silt clearance of Kharabara Dam Channel | Haripur Irrigation Division Haripur | 0.1 | 0.08 | 2.8 | 515.1 | 2.8 | 2.05 | 376.56 | 70% | Work is in progress
17 | Silt Clearance of Badwan Kharif Irrigation Scheme at RD 0+00 To Tail. | Chakdara Irrigation Sub Division ,Dir Division | 0.9 | 0.8957 | 22.18 | 4635.35 | 22.18 | 10.05 | 2780.01 | 59.97% | Work is in progress (Today Desiltation is Stope Due To Rain)
18 | Silt clearance/removal of heaps of Disty No. 9 RD; 41000 to 85500 | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 13.41 | 599.93 | 1 | 1 | 599.93 | 100% | Completed
19 | Silt clearance of Power House Minor RD 0 to tail | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 1.28 | 599.9 | 1.28 | 1.25 | 585.84 | 98% | In progress
20 | Silt clearance of conduit covering portion of 2/9 Hoti Minor RD 4200 to 5000, 5800 to 7000 & 7200 to 7500 | Mardan Irrigation Division Mardan | 0.7 | 0.4546 | 0.7 | 745.53 | 0.7 | 0.67 | 713.58 | 96% | In progress
21 | Silt clearance of 2/9 Hoti Minor RD 0 to 4200, 5000 to 5800 & 7500 to 19000 | Mardan Irrigation Division Mardan | 0.8 | 0.5195 | 5.94 | 921.08 | 2.43 | 2.35 | 890.76 | 97% | In progress
22 | Silt clearance /removal of heaps of kalpani disty RD 0-51000 in reaches and clearance of syphones RD 10500 and 15000 | Mardan Irrigation Division Mardan | 0.7 | 0.4544 | 15.6 | 4463.54 | 5.07 | 5.07 | 4463.54 | 100% | Completed
23 | Silt clearance /removal of heaps of 1/kalpani Kodinaka Minor RD 0-27000 in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 8.22 | 599.94 | 1.82 | 1.62 | 534.01 | 89% | In progress
24 | Silt clearance /removal of heaps of 2/kalpani Taus Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 6.4 | 2801.12 | 5.5 | 5.5 | 2801.12 | 100% | Completed
25 | Silt clearance of 3/9 Toru Minor RD 0 to 15800 | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 4.81 | 2801.12 | 4.81 | 4.81 | 2801.12 | 100% | Completed
26 | Silt clearance of branch 2/kalpani Muhib Banda Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.175 | 0.1308 | 2.89 | 1633.98 | 2 | 2 | 1633.98 | 100% | Completed
27 | Silt Clearance of Maho Dheri Minor RD: 4000 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.1493 | 4.57 | 1138.2 | 3.35 | 3.35 | 1138.2 | 100% | Completed
28 | Silt Clearance of Rashakai Minor from RD: 7000 to 31000 in reaches | Mardan Irrigation Division Mardan | 0.6 | 0.3894 | 9.45 | 2972.29 | 7.31 | 7.31 | 2972.29 | 100% | Completed
29 | Silt Clearance of Nowshera Minor RD:0 - tail in reachers | Mardan Irrigation Division Mardan | 0.35 | 0.2613 | 5.18 | 2059.85 | 3.2 | 3.2 | 2059.85 | 100% | Completed
30 | Silt Clearance of Turlandi Minor Head to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 5.27 | 2134.4 | 4.71 | 4.71 | 2134.4 | 100% | Completed
31 | Silt Clearance of Khan Mahi Branch from RD: 0 to 3000 and RD: 8000 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 13.41 | 2344.08 | 5.48 | 5.48 | 2344.08 | 100% | Completed
32 | Silt Clearance of Bara Banda Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 3.04 | 1703.02 | 3.04 | 3.04 | 1703.02 | 100% | Completed
33 | Removal of heaps of Disty No. 8 RD: 52000 to 68000 in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 9.45 | 1860.72 | 1.43 | 1.43 | 1860.72 | 100% | Completed
34 | Silt Clearance/removal of heaps of Disty No. 7 at RD: 4000 to 14000 in reaches | Mardan Irrigation Division Mardan | 0.15 | 0.1133 | 4.26 | 1400.56 | 3.04 | 3.04 | 1400.56 | 100% | Completed
35 | Silt Clearance/removal of heaps of Sheikh yousaf Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 5.48 | 239.97 | 2.13 | 2.13 | 239.97 | 100% | Completed
36 | Silt Clearance/removal of heaps of 1/9 Guide Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 7 | 479.94 | 2.74 | 2.74 | 479.94 | 100% | Completed
37 | Silt Clearance/removal of heaps of Koragh Branch RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 14.93 | 479.94 | 2.23 | 2.23 | 479.94 | 100% | Completed
38 | Removal of heaps of Disty No.8 RD: 0 to 38000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 11.58 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
39 | Removal of heaps of Disty No.9 RD: 0 to 41000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 12.5 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
40 | Removal of Heaps / Clearance of Bari Band Disty RD: 39+500-88+600 in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.33775 | 14.96 | 1435.76 | 8.21 | 8 | 1410 | 97.44% | Work in Progress
41 | Removal of Heaps / Clearance of Hero Shah Minor RD: 0 -38+000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 11.58 | 2446.93 | 11.58 | 10.9 | 2330 | 94.13% | Work in Progress
42 | Removal of Heaps / Clearance of Kalu Shah Disty and Dundian Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.1 | 0.098 | 7.69 | 785.8 | 5 | 5 | 785.8 | 100% | Completed
43 | Removal of Heaps / Clearance of Sarwala Disty and Lund Khwar Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 18.29 | 3172.99 | 10.06 | 10.06 | 3172.99 | 100% | Completed
44 | Removal of Heaps / Clearance of Said Abad Disty and Pir Abad Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 20.42 | 3113.1 | 7.31 | 7.31 | 3113.1 | 100% | Completed
45 | Removal of Heaps / Clearance of Katlang Disty from RD: 0-40+000 in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 12.19 | 1910.43 | 7.61 | 7.61 | 1910.43 | 100% | Completed
46 | Removal of Heaps / Clearance of Shamozai Disty/ Syphon and Likpani Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.392 | 17.67 | 2730.62 | 13.01 | 13.01 | 2730.62 | 100% | Completed
47 | Removal of Heaps / Clearance of Dheri Minor and Tail Minor Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.15 | 0.147 | 7.01 | 1211.68 | 6 | 6 | 1211.68 | 100% | Completed
48 | Bazai Main Canal Head Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 10.5 | 10.5 | 1168.075 | 100% | Completed
49 | Wartair Disty | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 6 | 587.93 | 6 | 6 | 587.93 | 100% | Completed
50 | Kharki Disty No. 02 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 3.3 | 1272.34 | 3.3 | 3.3 | 1272.34 | 100% | Completed
51 | Additional Minor No. 03, 06 and Bazai Disty No. 01. | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | 16.8 | 1272.14 | 3 | 3 | 1272.14 | 100% | Completed
52 | Bazai Main Canal, Syphon No. 4431, 5851, 12530, 13590, 14842, 18400, 47527 & 58853 | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | [5 empty] | 70% | Work in Progress
53 | Bazai Disty No. 04, Bazai Minor No. 09, 11 and 12. | Malakand Irrigation Division Malakand | 0.27 | 0.26625 | 15.2 | 4070 | 9 | 9 | 4070 | 100% | Completed
54 | Clearance of Syphon 79205, 93480 and 97962. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | [5 empty] | 20% | Work in Progress
55 | Bazai Disty No. 03 and Bazai Minor No. 05. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | 20.5 | 1907.82 | 7 | 7 | 1907.82 | 100% | Completed
56 | Bazai Main Canal Tail Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 4.78 | 4.78 | 1168.075 | 100% | Completed
57 | KM-1 RD: 0-2976 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 143.26 | 0.9 | 0.9 | 143.26 | 100% | Completed
58 | KM-1 RD: 0-1500, 22000-29000 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 410.62 | 2.6 | 2.6 | 410.62 | 100% | Completed
59 | Bazai Main Canal RD: 79500 to RD: 84500 | Malakand Irrigation Division Malakand | 0.302 | 0.296 | 39 | 649.87 | 1.5 | 1.4 | 606.52 | 93.33% | Work in Progress
60 | Silt & Shingle Clearance of P.C Minor from RD 0+000 To Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.388 | 12.881 | 1851.77 | 7.62 | 4.1 | 996.25 | 53.8% | Work in Progress
61 | Clearance of Shingri Minor from RD 0-17250 in reaches. | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.309 | 530.92 | 2.347 | 2.12 | 479.52 | 90.32% | Work in Progress
62 | Clearance of Meherdi Minor from RD 0-31000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 9.451 | 2167.5 | 8.382 | 6.21 | 1605.68 | 74.08% | Work in Progress
63 | Clearance of Kalu Branch from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.33 | 0.3218 | 11.563 | 1318.25 | 5 | 4.6 | 1212.79 | 92% | Work in Progress
64 | Clearance of Hathian Minor from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.05 | 0.04875 | 2.35 |  |  | 0 | 0 | 0% | Not yet started
65 | Clearance of Jalala Disty from RD: 29000 to Tail in reaches | Malakand Irrigation Division Malakand | 0.37 | 0.3607 | 14.024 | 1476.73 | 5900 | 5400 | 1351.5 | 91.52% | Work in Progress
66 | Clearance of Pirsaddo Disty, Ghano Minor and Qutab Gharh Minor from : H-Tail to Tail in reaches. | Malakand Irrigation Division Malakand | 0.35 | 0.341 | 1.88 |  |  | 0 | 0 | 0% | Not yet started
67 | Clearance of Shergarh Minor from Head to Rd:12+000 in reaches. | Malakand Irrigation Division Malakand | 0.15 | 0.146 | 7.752 |  |  | 0 | 0 | 0% | Not yet started
68 | Clearance of Shergarh Minor from Rd:12+000 tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 7.752 | 1195.13 | 6000 | 5500 | 956.83 | 91.66% | Work in Progress
69 | Clearance of Spokanda Disty from RD: 18000 to Tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 5.659 | 1215.5 | 4.97 | 0.92 | 230.94 | 18.51% | Work in Progress
70 | Silt & Shingle Clearance of Spokanda Disty from 0-18000 | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.488 | 771.85 | 2.743 | 1.34 | 378.2 | 48.85% | Work in Progress
71 | Silt Clearance of Lower Siran Canal RD 0-14000 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3110.16 | 3.04 | 2.32 | 2039.17 | 66% | In progress
72 | Silt Clearance of Lower Siran Canal RD 14000-36500 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3142.51 | 4.26 | 2.93 | 1713.99 | 55% | In progress
73 | Silt Clearance of Lower Siran Canal Hathi Maira Branch & Gandian Minor RD 36500 in reaches | Mansehra Irrigation Division Mansehra | 0.55 | 0.4954 | 26.21 | 2080.06 | 12.1 | 8.82 | 1444.676 | 69% | In progress
74 | Silt Clearance of Ichar Canal/ Kalghan Minor RD 0-tail in reaches | Mansehra Irrigation Division Mansehra | 0.25 | 0.2254 | 5.97 | 1197.78 | 5.66 | 2.377 | 419.084 | 35% | In progress
75 | Silt Clearance of Upper Siran Canal from RD 0-30000 In reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2065 | 3.048 | 1.965 | 941.3 | 46% | In progress
76 | Silt Clearance of Upper Siran Canal from RD 30000-61000 in reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2110 | 9.44 | 7.742 | 1830.853 | 87% | In progress
77 | Silt Clearance of Upper Siran Canal from RD 61000-tail in reaches | Mansehra Irrigation Division Mansehra | 0.18 | 0.1623 | 23.86 | 930 | 5.27 | 2.6352 | 466.796 | 50% | In progress
78 | Silt Clearance of Dhodial Minor Upper Siran Canal in reaches | Mansehra Irrigation Division Mansehra | 0.22 | 0.1981 | 5.24 | 1135 | 5.24 | 3.7648 | 707.1865 | 62% | In progress
79 | Nipki Khel Irrigation Scheme | Swat Irrigation Division -I | 2.2 | 1.76 | 38.87 | 10172.62 | 38.87 | 22.2561 | 5840 | 57.26% | Work is in progress
80 | Jue Shiekh Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 16.29 | 13.03 | 53.35 | 132353 | 53.35 | 53.35 | 132353 | 100% | Completed
81 | Jue Zardad Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 3.6 | 2.88 | 13.1 | 18500 | 13.1 | 13.1 | 18500 | 100% | Completed
82 | Kabul River Canal | Peshawar Canal Division, Peshawar (Kabaul River Canal Sub Division) | 27.855 | 22.284 | 60.35 | 1062085 | 60.35 | 46.2 | 813103 | 77% | Work is in progress
83 | Hazar Khwani Branch | Peshawar Canal Division, Peshawar (Kabul River Canal Sub Division) | 23.2 | 18.56 | 28.04 | 1016303 | 28.04 | 28.04 | 1016303 | 100% | Completed
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086

## 13-02-2023
S# | Name of Canal | Name of Division | Estimated Cost(RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Total Quantity of Silt to be removed (m3) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Total Quantity of Silt removed till date (m3) | Progress Till date in % | Remarks
1 | Swabi Irrigation Division-I Swabi
2 | Shahbaz Garhi Sub Division
3 | Clearance from the bed of Jamal Garhi Disty from 00-tail in reaches. | Swabi Irrigation Division-I Swabi | 0.3 | 0.11 | 16.81 | 1692.37 | 4.7 | 4.6 | 1641.6 | 97% | In-Progress
4 | Silt Clearance from the bed of Buxali Disty & Kot Minor from 00-tail in reaches | Swabi Irrigation Division-I Swabi | 0.65 | 0.36 | 21.34 | 4715.26 | 9.42 | 7.5 | 4479.5 | 95% | In-Progress
5 | Removal of debris and heaps from Machai Branch RD 105+000 to 142+000 in reaches | Swabi Irrigation Division-I Swabi | 0.35 | 0.13 | 247.58 | 4521.89 | 0.48 | 0.3 | 4069.7 | 90% | In-Progress
6 | Removal of debris and heaps from Machai Branch RD 142+000 to 186+000 in reaches | Swabi Irrigation Division-I Swabi | 0.35 | 0.13 | 247.58 | 4513.02 | 0.35 | 0.3 | 4467.89 | 99% | In-Progress
7 | Silt Clearance from the bed of Chura Minor , Sawal Dher Minor & Mala Minor from RD: 00-tail in reaches. | Swabi Irrigation Division-I Swabi | 0.3 | 0.11 | 14.38 | 1698.88 | 7 | 5.4 | 1664.9 | 98% | In-Progress
8 | Silt clearance from the bed Shahbaz Garhi Disty and its sub System from RD:00-tail in reaches | Swabi Irrigation Division-I Swabi | 0.8 | 0.44 | 18.29 | 4522.69 | 14.85 | 12.5 | 4296.56 | 95% | In-Progress
9 | Silt Clearance from the bed of Ismalia Disty and its sub system from 00-tail in reaches | Swabi Irrigation Division-I Swabi | 0.9 | 0.5 | 18.29 | 6469.09 | 13.26 | 11.7 | 6339.71 | 98% | In-Progress
10 | Silt Clearance from the bed of Adina Minor and adina Minor Branch from Head to tail in reaches | Swabi Irrigation Division-I Swabi | 0.35 | 0.19 | 7.89 | 1980.17 | 5.59 | 4.7 | 1900.96 | 96% | In-Progress
11 | Shamizai Irrigation Canal | Swat Irrigation Division-II Matta | 1 | 0.779 | 20.73 | 5150 | 19.5 | 19.5 | 5150 | 100% | Completed
12 | Barwai Irrigation Canal | Swat Irrigation Division-II Matta | 0.3 | 0.2805 | 11.22 | 1300 | 6.1 | 6.1 | 1300 | 100% | Completed
13 | Silt clearance/removal of heaps of Disty No. 9 RD; 41000 to 85500 | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 13.41 | 599.93 | 1 | 1 | 599.93 | 100% | Completed
14 | Silt clearance of Power House Minor RD 0 to tail | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 1.28 | 599.9 | 1.28 | 1.25 | 585.84 | 98% | In progress
15 | Silt clearance of conduit covering portion of 2/9 Hoti Minor RD 4200 to 5000, 5800 to 7000 & 7200 to 7500 | Mardan Irrigation Division Mardan | 0.7 | 0.4546 | 0.7 | 745.53 | 0.7 | 0.7 | 745.53 | 100% | In progress
16 | Silt clearance of 2/9 Hoti Minor RD 0 to 4200, 5000 to 5800 & 7500 to 19000 | Mardan Irrigation Division Mardan | 0.8 | 0.5195 | 5.94 | 921.08 | 2.43 | 2.35 | 890.76 | 97% | In progress
17 | Silt clearance /removal of heaps of kalpani disty RD 0-51000 in reaches and clearance of syphones RD 10500 and 15000 | Mardan Irrigation Division Mardan | 0.7 | 0.4544 | 15.6 | 4463.54 | 5.07 | 5.07 | 4463.54 | 100% | Completed
18 | Silt clearance /removal of heaps of 1/kalpani Kodinaka Minor RD 0-27000 in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 8.22 | 599.94 | 1.82 | 1.62 | 534.01 | 89% | In progress
19 | Silt clearance /removal of heaps of 2/kalpani Taus Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 6.4 | 2801.12 | 5.5 | 5.5 | 2801.12 | 100% | Completed
20 | Silt clearance of 3/9 Toru Minor RD 0 to 15800 | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 4.81 | 2801.12 | 4.81 | 4.81 | 2801.12 | 100% | Completed
21 | Silt clearance of branch 2/kalpani Muhib Banda Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.175 | 0.1308 | 2.89 | 1633.98 | 2 | 2 | 1633.98 | 100% | Completed
22 | Silt Clearance of Maho Dheri Minor RD: 4000 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.1493 | 4.57 | 1138.2 | 3.35 | 3.35 | 1138.2 | 100% | Completed
23 | Silt Clearance of Rashakai Minor from RD: 7000 to 31000 in reaches | Mardan Irrigation Division Mardan | 0.6 | 0.3894 | 9.45 | 2972.29 | 7.31 | 7.31 | 2972.29 | 100% | Completed
24 | Silt Clearance of Nowshera Minor RD:0 - tail in reachers | Mardan Irrigation Division Mardan | 0.35 | 0.2613 | 5.18 | 2059.85 | 3.2 | 3.2 | 2059.85 | 100% | Completed
25 | Silt Clearance of Turlandi Minor Head to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 5.27 | 2134.4 | 4.71 | 4.71 | 2134.4 | 100% | Completed
26 | Silt Clearance of Khan Mahi Branch from RD: 0 to 3000 and RD: 8000 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 13.41 | 2344.08 | 5.48 | 5.48 | 2344.08 | 100% | Completed
27 | Silt Clearance of Bara Banda Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 3.04 | 1703.02 | 3.04 | 3.04 | 1703.02 | 100% | Completed
28 | Removal of heaps of Disty No. 8 RD: 52000 to 68000 in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 9.45 | 1860.72 | 1.43 | 1.43 | 1860.72 | 100% | Completed
29 | Silt Clearance/removal of heaps of Disty No. 7 at RD: 4000 to 14000 in reaches | Mardan Irrigation Division Mardan | 0.15 | 0.1133 | 4.26 | 1400.56 | 3.04 | 3.04 | 1400.56 | 100% | Completed
30 | Silt Clearance/removal of heaps of Sheikh yousaf Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 5.48 | 239.97 | 2.13 | 2.13 | 239.97 | 100% | Completed
31 | Silt Clearance/removal of heaps of 1/9 Guide Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 7 | 479.94 | 2.74 | 2.74 | 479.94 | 100% | Completed
32 | Silt Clearance/removal of heaps of Koragh Branch RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 14.93 | 479.94 | 2.23 | 2.23 | 479.94 | 100% | Completed
33 | Removal of heaps of Disty No.8 RD: 0 to 38000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 11.58 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
34 | Removal of heaps of Disty No.9 RD: 0 to 41000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 12.5 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
35 | Swabi Irrigation Division-II Swabi
36 | Clearance of Topi Lift Irrigation Channels RD;00-Tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 4.88 | 1161.77 | 2.84 | 2.77 | 1139.39 | 98% | Work in progress
37 | Clearance of Topi & Zarobi Minors from RD;00 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | Topi =4.24 Zarobi =4.27 | 1159.72 | 3.05 | 2.74 | 1095.85 | 90% | Work in progress
38 | Clearance/Repair of Badri Lift Irrigation Scheme | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 0.34 | 607.12 | 0.33 | 0.33 | 607.12 | 100% | Competed
39 | Clearance of Kotha Disty; from RD;00 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.24 | 0.24 | 17.53 | 1389.07 | 1.89 | 1.89 | 1389.07 | 100% | Competed
40 | Clearance of Pehur main Canal from RD;46000 to RD;54000 | Swabi Irrigation Division-II Swabi | 0.18 | 0.18 | 51.4 | 1042.24 | 0.53 | 0.53 | 1042.24 | 100% | Competed
41 | Clearance of Pehur Main Canal from RD;54500 to RD;66000 | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 51.4 | 1130.88 | 0.55 | 0.49 | 967.65 | 89% | Work in progress
42 | Clearance of Pehur Main Canal from RD;66000 to RD;85000 | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.92 | 0.7 | 0.67 | 1333.14 | 96% | Work in progress
43 | Clearance of Pehur Main Canal RD;85000 to RD;93000 | Swabi Irrigation Division-II Swabi | 0.16 | 0.16 | 51.4 | 976.63 | 0.63 | 0.63 | 976.63 | 100% | Competed
44 | Clearance of Pehur Main Canal from RD;93500 to RD;98000 | Swabi Irrigation Division-II Swabi | 0.17 | 0.17 | 51.4 | 1033.5 | 0.32 | 0.21 | 795 | 67% | Work in progress
45 | Clearance of Pehur Main Canal from RD;98500 to RD;113000 | Swabi Irrigation Division-II Swabi | 0.18 | 0.18 | 51.4 | 1094.71 | 0.61 | 0.55 | 956.47 | 90% | Work in progress
46 | Clearance of Kaddi, Zaida, Zakarriya & Sheikhdheri Minors from RD;00 to Tail | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | Kaddi= 5.79 Zaida= 3.81 Zakary=3.43 S/Dher=2.95 | 1292.45 | 0.39 | 0.3 | 906 | 77% | Work in progress
47 | Clearance of Pehur Main Canal System from RD;113000 to RD;117000 | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 51.4 | 883 | 0.4 | 0.4 | 883 | 100% | Competed
48 | Clearance of Pehur Main Canal System from RD;117000 to RD;122000 | Swabi Irrigation Division-II Swabi | 0.12 | 0.12 | 51.4 | 729.53 | 0.22 | 0.22 | 729.53 | 100% | Competed
49 | Clearance of Pehur main Canal System from RD;122000 to RD;133000 | Swabi Irrigation Division-II Swabi | 0.13 | 0.13 | 51.4 | 790.91 | 0.4 | 0.37 | 697.59 | 92% | Work in progress
50 | Clearance of PMC System from RD;133000 to 140000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 51.4 | 1738.06 | 0.85 | 0.85 | 1738.06 | 100% | Competed
51 | Clearance of PMC Systems from RD;145000 to RD;150000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.23 | 0.23 | 51.4 | 1332.82 | 0.41 | 0.34 | 1211.65 | 83% | Work in progress
52 | Clearance of PMC System from RD;150500 to RD;162000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.81 | 0.44 | 0.34 | 1297.59 | 77% | Work in progress
53 | Clearance of PMC System from RD;162100 to Tail & other allied Branches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.85 | 3.23 | 3.08 | 1406.71 | 95% | Work in progress
54 | Clearance of Thanodher Disty: & Bazar Minor from RD;00 to Tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | Thano=6.00 Bazar=7.47 | 1157.95 | 0.35 | 0.27 | 1000.58 | 77% | Work in progress
55 | Clearance of flood deposition and silt clearance of ¦Indus Branch RD:74500 Tail in reaches. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 18.54 | 4478 | 11.89 | 11.43 | 3617.16 | 96% | Work in progress
56 | Silt Clearance of Dagi Minor from RD:0- 37000 in reaches i/c repair to out lets & other allied structures. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 11.28 | 4482 | 9.15 | 9.15 | 4482 | 100% | Competed
57 | Silt Clearance of Dandoka Minor from RD:0-Tail in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.03 | 2246.38 | 4.27 | 2.74 | 1396.88 |  | Work in progress
58 | Silt Clearance of Sudher Minor RD:0 - tail in reaches & other allied structures | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 2.29 | 1684.86 | 1.83 | 0 | 0 |  | contractor deployed
59 | Silt Clearance of Yar Hussain Minor RD;0-tail | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 6.8 | 2803.37 | 5.79 | 1.22 | 622.97 | 21% | Work in progress
60 | Silt Clearance of Ghazi Kot Minor from RD: 0-tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.95 | 2244.11 | 4.57 | 0 | 0 |  | contractor deployed
61 | Silt Clearance Daulat Minor and Gidar Minor RD; 0-tail in reaches & other allied structures | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 16.84 | 4482 | 13.11 | 13.11 | 4482 | 100% | Competed
62 | Silt Clearance of Pirsabaq Disty and pirsabaq Minor from Rd:0-tail in reaches. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 11.75 | 4946.41 | 14.21 | 10.67 | 3984.01 | 75% | Work in progress
63 | Silt Clearance of Chowky Disty, Chowki Minor 1 and 2 from RD: 00 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 8.23 | 3710.22 | 11.1 | 6.16 | 2766.7 | 55% | Work in progress
64 | Silt Clearance of Gumbat Minor No.1 & Gumbat Branch from RD:0+0 to tail in reaches., | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 5.18 | 3096.09 | 6.46 | 4.57 | 2731.49 | 71% | Work in progress
65 | Silt Clearance of Misri Banda from RD;0 to tal in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.73 | 2472.77 | 5.4 | 3.96 | 2063.58 | 73% | Work in progress
66 | Silt Clearance of Ambar Branch from RD;0+0 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.35 | 0.35 | 7.88 | 3923.31 | 3.9 | 0.3 | 283.17 | 8% | Work in progress
67 | Silt Clearance of Jehangira Minor & Nandrak Minor from RD;0-tail in reaches and repair to allied structures | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 11.52 | 0 | 0 | 0 | 0 |  | contractor deployed
68 | Silt Clearance of Thanodher Minor & Manki Minor from RD;0-tail in reaches | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 12.42 | 1090.2 | 5.18 | 5.18 | 1090.15 | 100% | Competed
69 | Silt Clearance of Yaqubi Minor, Sard China Minor and Naik Nam Minor from RD; 0-tail | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 10.46 | 1684.86 | 7.44 | 7.44 | 1684.84 | 100% | Competed
70 | Silt Clearance of Dagi Disty & repair to allied structures Rd 0 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 3.23 | 1158.16 | 2.16 | 0 | 0 |  | contractor deployed
71 | Silt Clerance of Gumbat Minor No 2 | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 4.57 | 1855.74 | 4.12 | 2.13 | 953.14 | 52% | Work in progress
72 | Silt Clearance and repair of Link Channel, Lahor Minor ,Zakaria Minor Sheik Dheri from RD; 0- to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 8.19 | 948.62 | 1.52 | 1.52 | 948.62 | 100% | Competed
73 | Silt Clearance of Lower Siran Canal RD 0-14000 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3110.16 | 3.04 | 2.61 | 2463.93 | 79% | In progress
74 | Silt Clearance of Lower Siran Canal RD 14000-36500 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3142.51 | 4.26 | 3.22 | 1855.575 | 59% | In progress
75 | Silt Clearance of Lower Siran Canal Hathi Maira Branch & Gandian Minor RD 36500 in reaches | Mansehra Irrigation Division Mansehra | 0.55 | 0.4954 | 26.21 | 2080.06 | 12.1 | 9.72 | 1557.944 | 75% | In progress
76 | Silt Clearance of Ichar Canal/ Kalghan Minor RD 0-tail in reaches | Mansehra Irrigation Division Mansehra | 0.25 | 0.2254 | 5.97 | 1197.78 | 5.66 | 2.675 | 475.718 | 40% | In progress
77 | Silt Clearance of Upper Siran Canal from RD 0-30000 In reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2065 | 3.048 | 2.27 | 1054.568 | 51% | In progress
78 | Silt Clearance of Upper Siran Canal from RD 30000-61000 in reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2110 | 9.44 | 8.809 | 1915.804 | 91% | In progress
79 | Silt Clearance of Upper Siran Canal from RD 61000-tail in reaches | Mansehra Irrigation Division Mansehra | 0.18 | 0.1623 | 23.86 | 930 | 5.27 | 3.1482 | 560.2421 | 60% | In progress
80 | Silt Clearance of Dhodial Minor Upper Siran Canal in reaches | Mansehra Irrigation Division Mansehra | 0.22 | 0.1981 | 5.24 | 1135 | 5.24 | 4.0688 | 763.8205 | 67% | In progress
81 | Nipki Khel Irrigation Scheme | Swat Irrigation Division -I | 2.2 | 1.76 | 38.87 | 10172.62 | 38.87 | 25.9146 | 6800 | 66.67% | Work is in progress
82 | Desiltation / berm cutting/Jungle clearance of Disty No.04, RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 10.11 | 5964.26 | 5.64 | 4.29 | 4532.84 | 76% | Work is in progress.
83 | Desiltation / berm cutting/Jungle clearance of Disty No.5 & its Minor and sub Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 26.31 | 7688.07 | 8.2 | 5.82 | 5458.53 | 71% | Work is in progress.
84 | Desiltation / berm cutting/Jungle clearance of Dera Disty RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 16.7 | 5812.06 | 6.55 | 5.5 | 4882.13 | 84% | Work is in progress.
85 | Silt clearance/ jungle clearance of Muryali Minor RD. 00-15000 in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.64 | 4021.01 | 5.33 | 0 | 0 | 0% | Work is in progress.
86 | Silt clearance/ jungle clearance including removal of debris of Lachra Minor/Makali Minor in reaches. | CRBC Irrigation Division DIKhan | 0.25 | 0.23 | 3.92 | 2402.7 | 11.3 | 2.26 | 480.54 | 20% | Work is in progress.
87 | Desiltation / berm cutting/Jungle clearance of Mehmood Disty. RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.05 | 5737.19 | 4.42 | 3.89 | 5048.73 | 88% | Work is in progress.
88 | Desiltation / berm cutting/Jungle clearance of Nawab Minor RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.3 | 0.27 | 7.62 | 2952 | 2.59 | 2.2 | 2509.2 | 85% | Work is in progress.
89 | Desiltation / berm cutting/Jungle clearance of Disty No.7, i/c Minors of Disty No.7 RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 30.53 | 7801.33 | 15.37 | 9.38 | 4758.81 | 61% | Work is in progress.
90 | Desiltation / berm cutting/Jungle clearance of Disty No. 8 & 8-A, RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.29 | 3999 | 3.95 | 3.75 | 3799.05 | 95% | Work is in progress.
91 | Desiltation / berm cutting/Jungle clearance of Disty No.9 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.71 | 3560.86 | 2.9 | 1.01 | 1246.3 | 35% | Work is in progress.
92 | Desiltation / berm cutting/Jungle clearance of Disty No.10 & 10/A RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11 | 3950.22 | 3.19 | 0.96 | 1185.07 | 30% | Work is in progress.
93 | Desiltation / berm cutting/Jungle clearance of Disty No. 11 & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 9.1 | 5670.47 | 10.66 | 8.1 | 4309.56 | 76% | Work is in progress.
94 | Desiltation / berm cutting/Jungle clearance of Disty No. 11-A, & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 21.86 | 7695.14 | 5.93 | 2.73 | 3539.76 | 46% | Work is in progress.
95 | Desiltation / berm cutting/Jungle clearance of Disty No. 12 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.23 | 5762.51 | 4.11 | 3.86 | 5416..76 | 94% | Work is in progress.
96 | Desiltation /Jungle Clearance of Disty # 13 & its System RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.675 | 0.6075 | 21.655 | 4256.03 | 4.66 | 4.36 | 4170.9 | 98% | Work is in progress.
97 | Shingling of CPR & Jungle Clearance of Disty # 14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.725 | 0.6525 | 21.616 | 4176.75 | 4.58 | 4.53 | 4134.98 | 99% | Work is in progress.
98 | Shingling of CPR & Jungle Clearance of MD-14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.433 | 2145.01 | 2.43 | 2.33 | 2059.2 | 96% | Work is in progress.
99 | Shingling of CPR & Jungle Clearance of Disty # 15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.7 | 0.63 | 21.494 | 3752 | 3.65 | 3.1 | 3189.2 | 85% | Work is in progress.
100 | Shingling of CPR & Jungle Clearance of MD-15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.325 | 0.2925 | 5.8384 | 1862.55 | 2.28 | 0.34 | 279.38 | 15% | Work is in progress.
101 | Shingling of CPR & Jungle Clearance of Disty 16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 12.75 | 3018 | 2.5 | 0.62 | 755 | 25% | Work is in progress.
102 | Shingling of CPR & Jungle Clearance of Minor of Disty-16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.8445 |  | 2.45 | 0 |  | 0% | Work not yet started.
103 | Desiltation / Jungle Clearance of Disty # 17 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 9.6951 |  | 2.13 | 0 |  | 0% | Work not yet started.
104 | Shingling of CPR & Jungle Clearance of Disty # 18 its Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 18.009 |  | 4.26 | 0 |  | 0% | Work not yet started.
105 | Shingling of CPR & Jungle Clearance of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.55 | 0.495 | 15.753 |  | 3.96 | 0 |  | 0% | Work not yet started.
106 | Desiltation / Jungle Clearance of M-1 & M-2 of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.829 |  | 4 | 0 |  | 0% | Work not yet started.
107 | Silt Clearance of Disty No.6 from RD: 55+000 to 60+000 in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.183 | 0.155 | 22.25 | 538.02 | 0.61 | 0.61 | 538.02 | 100% | Completed
108 | Silt Clearance of Disty No.6 from RD: 60+000 to 65+000 in reaches. | -do- | 0.157 | 0.133 | 22.25 | 460.15 | 0.45 | 0.45 | 460.15 | 100% | Completed
109 | Silt Clearance of Disty No.6 from RD: 65+000 to 73+000 in reaches. | -do- | 0.2 | 0.169 | 22.25 | 587.58 | 0.61 | 0.61 | 587.58 | 100% | Completed
110 | Silt Clearance of Nisatta Branch from RD: 0+000 to Tail in reaches. | -do- | 0.336 | 0.284 | 11.88 | 991.1 | 1 | 0.85 | 842.435 | 85% | Work in progress
111 | Silt Clearance of Nisatta Minor from RD: 0+000 to Tail in reaches. | -do- | 0.218 | 0.184 | 3.35 | 877.83 | 2 | 1.8 | 790.047 | 90% | Work in progress
112 | Silt Clearance of Palosa Minor from RD: 0+000 to Tail in reaches. | -do- | 0.253 | 0.214 | 5.03 | 748.98 | 1.35 | 1.215 | 674.082 | 90% | Work in progress
113 | Silt Clearance of Zardad and Kheshki Branch in reaches. | -do- | 0.348 | 0.294 | 14.49 | 1880.25 | 7 | 7 | 1880.25 | 100% | Completed
114 | Silt Clearance of Badwan Kharif Irrigation Scheme at RD 0+00 To Tail. | Chakdara Irrigation Sub Division ,Dir Division | 0.9 | 0.8957 | 22.18 | 4635.35 | 22.18 | 10.97 | 2830.01 | 61.05% | Work is in progress (Today Desiltation is Stope Due To Rain)
115 | Jue Shiekh Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 16.29 | 13.03 | 53.35 | 132353 | 53.35 | 53.35 | 132353 | 100% | Completed
116 | Jue Zardad Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 3.6 | 2.88 | 13.1 | 18500 | 13.1 | 13.1 | 18500 | 100% | Completed
117 | Kabul River Canal | Peshawar Canal Division, Peshawar (Kabaul River Canal Sub Division) | 27.855 | 22.284 | 60.35 | 1062085 | 60.35 | 49.3 | 867662 | 82% | Work is in progress
118 | Hazar Khwani Branch | Peshawar Canal Division, Peshawar (Kabul River Canal Sub Division) | 23.2 | 18.56 | 28.04 | 1016303 | 28.04 | 28.04 | 1016303 | 100% | Completed
119 | Removal of Heaps / Clearance of Bari Band Disty RD: 39+500-88+600 in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.33775 | 14.96 | 1435.76 | 8.21 | 8.05 | 1410 | 98.05% | Work in Progress
120 | Removal of Heaps / Clearance of Hero Shah Minor RD: 0 -38+000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 11.58 | 2446.93 | 11.58 | 11.12 | 2330 | 96.03% | Work in Progress
121 | Removal of Heaps / Clearance of Kalu Shah Disty and Dundian Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.1 | 0.098 | 7.69 | 785.8 | 5 | 5 | 785.8 | 100% | Completed
122 | Removal of Heaps / Clearance of Sarwala Disty and Lund Khwar Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 18.29 | 3172.99 | 10.06 | 10.06 | 3172.99 | 100% | Completed
123 | Removal of Heaps / Clearance of Said Abad Disty and Pir Abad Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 20.42 | 3113.1 | 7.31 | 7.31 | 3113.1 | 100% | Completed
124 | Removal of Heaps / Clearance of Katlang Disty from RD: 0-40+000 in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 12.19 | 1910.43 | 7.61 | 7.61 | 1910.43 | 100% | Completed
125 | Removal of Heaps / Clearance of Shamozai Disty/ Syphon and Likpani Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.392 | 17.67 | 2730.62 | 13.01 | 13.01 | 2730.62 | 100% | Completed
126 | Removal of Heaps / Clearance of Dheri Minor and Tail Minor Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.15 | 0.147 | 7.01 | 1211.68 | 6 | 6 | 1211.68 | 100% | Completed
127 | Bazai Main Canal Head Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 10.5 | 10.5 | 1168.075 | 100% | Completed
128 | Wartair Disty | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 6 | 587.93 | 6 | 6 | 587.93 | 100% | Completed
129 | Kharki Disty No. 02 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 3.3 | 1272.34 | 3.3 | 3.3 | 1272.34 | 100% | Completed
130 | Additional Minor No. 03, 06 and Bazai Disty No. 01. | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | 16.8 | 1272.14 | 3 | 3 | 1272.14 | 100% | Completed
131 | Bazai Main Canal, Syphon No. 4431, 5851, 12530, 13590, 14842, 18400, 47527 & 58853 | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | [5 empty] | 70% | Work in Progress
132 | Bazai Disty No. 04, Bazai Minor No. 09, 11 and 12. | Malakand Irrigation Division Malakand | 0.27 | 0.26625 | 15.2 | 4070 | 9 | 9 | 4070 | 100% | Completed
133 | Clearance of Syphon 79205, 93480 and 97962. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | [5 empty] | 20% | Work in Progress
134 | Bazai Disty No. 03 and Bazai Minor No. 05. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | 20.5 | 1907.82 | 7 | 7 | 1907.82 | 100% | Completed
135 | Bazai Main Canal Tail Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 4.78 | 4.78 | 1168.075 | 100% | Completed
136 | KM-1 RD: 0-2976 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 143.26 | 0.9 | 0.9 | 143.26 | 100% | Completed
137 | KM-1 RD: 0-1500, 22000-29000 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 410.62 | 2.6 | 2.6 | 410.62 | 100% | Completed
138 | Bazai Main Canal RD: 79500 to RD: 84500 | Malakand Irrigation Division Malakand | 0.302 | 0.296 | 39 | 649.87 | 1.5 | 1.4 | 606.52 | 93.33% | Work in Progress
139 | Silt & Shingle Clearance of P.C Minor from RD 0+000 To Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.388 | 12.881 | 1851.77 | 7.62 | 4.1 | 996.25 | 53.8% | Work in Progress
140 | Clearance of Shingri Minor from RD 0-17250 in reaches. | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.309 | 530.92 | 2.347 | 2.12 | 479.52 | 90.32% | Work in Progress
141 | Clearance of Meherdi Minor from RD 0-31000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 9.451 | 2167.5 | 8.382 | 6.21 | 1605.68 | 74.08% | Work in Progress
142 | Clearance of Kalu Branch from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.33 | 0.3218 | 11.563 | 1318.25 | 5 | 4.6 | 1212.79 | 92% | Work in Progress
143 | Clearance of Hathian Minor from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.05 | 0.04875 | 2.35 |  |  | 0 | 0 | 0% | Not yet started
144 | Clearance of Jalala Disty from RD: 29000 to Tail in reaches | Malakand Irrigation Division Malakand | 0.37 | 0.3607 | 14.024 | 1476.73 | 5900 | 5400 | 1351.5 | 91.52% | Work in Progress
145 | Clearance of Pirsaddo Disty, Ghano Minor and Qutab Gharh Minor from : H-Tail to Tail in reaches. | Malakand Irrigation Division Malakand | 0.35 | 0.341 | 1.88 |  |  | 0 | 0 | 0% | Not yet started
146 | Clearance of Shergarh Minor from Head to Rd:12+000 in reaches. | Malakand Irrigation Division Malakand | 0.15 | 0.146 | 7.752 |  |  | 0 | 0 | 0% | Not yet started
147 | Clearance of Shergarh Minor from Rd:12+000 tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 7.752 | 1195.13 | 6000 | 5500 | 956.83 | 91.66% | Work in Progress
148 | Clearance of Spokanda Disty from RD: 18000 to Tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 5.659 | 1215.5 | 4.97 | 1.52 | 493.17 | 30.58% | Work in Progress
149 | Silt & Shingle Clearance of Spokanda Disty from 0-18000 | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.488 | 771.85 | 2.743 | 1.34 | 378.2 | 48.85% | Work in Progress
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086

## 14-02-2023
S# | Name of Canal | Name of Division | Estimated Cost(RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Total Quantity of Silt to be removed (m3) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Total Quantity of Silt removed till date (m3) | Progress Till date in % | Remarks
1 | Shamizai Irrigation Canal | Swat Irrigation Division-II Matta | 1 | 0.779 | 20.73 | 5150 | 19.5 | 19.5 | 5150 | 100% | Completed
2 | Barwai Irrigation Canal | Swat Irrigation Division-II Matta | 0.3 | 0.2805 | 11.22 | 1300 | 6.1 | 6.1 | 1300 | 100% | Completed
3 | Silt Clearance of Badwan Kharif Irrigation Scheme at RD 0+00 To Tail. | Chakdara Irrigation Sub Division ,Dir Division | 0.9 | 0.8957 | 22.18 | 4635.35 | 22.18 | 11.25 | 2880.15 | 62.13% | Work is in progress (Today Desiltation is Stope Due To Rain)
4 | Silt clearance/removal of heaps of Disty No. 9 RD; 41000 to 85500 | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 13.41 | 599.93 | 1 | 1 | 599.93 | 100% | Completed
5 | Silt clearance of Power House Minor RD 0 to tail | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 1.28 | 599.9 | 1.28 | 1.25 | 585.84 | 98% | In progress
6 | Silt clearance of conduit covering portion of 2/9 Hoti Minor RD 4200 to 5000, 5800 to 7000 & 7200 to 7500 | Mardan Irrigation Division Mardan | 0.7 | 0.4546 | 0.7 | 745.53 | 0.7 | 0.68 | 724.23 | 97% | In progress
7 | Silt clearance of 2/9 Hoti Minor RD 0 to 4200, 5000 to 5800 & 7500 to 19000 | Mardan Irrigation Division Mardan | 0.8 | 0.5195 | 5.94 | 921.08 | 2.43 | 2.43 | 921.08 | 100% | Completed
8 | Silt clearance /removal of heaps of kalpani disty RD 0-51000 in reaches and clearance of syphones RD 10500 and 15000 | Mardan Irrigation Division Mardan | 0.7 | 0.4544 | 15.6 | 4463.54 | 5.07 | 5.07 | 4463.54 | 100% | Completed
9 | Silt clearance /removal of heaps of 1/kalpani Kodinaka Minor RD 0-27000 in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 8.22 | 599.94 | 1.82 | 1.62 | 534.01 | 89% | In progress
10 | Silt clearance /removal of heaps of 2/kalpani Taus Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 6.4 | 2801.12 | 5.5 | 5.5 | 2801.12 | 100% | Completed
11 | Silt clearance of 3/9 Toru Minor RD 0 to 15800 | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 4.81 | 2801.12 | 4.81 | 4.81 | 2801.12 | 100% | Completed
12 | Silt clearance of branch 2/kalpani Muhib Banda Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.175 | 0.1308 | 2.89 | 1633.98 | 2 | 2 | 1633.98 | 100% | Completed
13 | Silt Clearance of Maho Dheri Minor RD: 4000 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.1493 | 4.57 | 1138.2 | 3.35 | 3.35 | 1138.2 | 100% | Completed
14 | Silt Clearance of Rashakai Minor from RD: 7000 to 31000 in reaches | Mardan Irrigation Division Mardan | 0.6 | 0.3894 | 9.45 | 2972.29 | 7.31 | 7.31 | 2972.29 | 100% | Completed
15 | Silt Clearance of Nowshera Minor RD:0 - tail in reachers | Mardan Irrigation Division Mardan | 0.35 | 0.2613 | 5.18 | 2059.85 | 3.2 | 3.2 | 2059.85 | 100% | Completed
16 | Silt Clearance of Turlandi Minor Head to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 5.27 | 2134.4 | 4.71 | 4.71 | 2134.4 | 100% | Completed
17 | Silt Clearance of Khan Mahi Branch from RD: 0 to 3000 and RD: 8000 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 13.41 | 2344.08 | 5.48 | 5.48 | 2344.08 | 100% | Completed
18 | Silt Clearance of Bara Banda Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 3.04 | 1703.02 | 3.04 | 3.04 | 1703.02 | 100% | Completed
19 | Removal of heaps of Disty No. 8 RD: 52000 to 68000 in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 9.45 | 1860.72 | 1.43 | 1.43 | 1860.72 | 100% | Completed
20 | Silt Clearance/removal of heaps of Disty No. 7 at RD: 4000 to 14000 in reaches | Mardan Irrigation Division Mardan | 0.15 | 0.1133 | 4.26 | 1400.56 | 3.04 | 3.04 | 1400.56 | 100% | Completed
21 | Silt Clearance/removal of heaps of Sheikh yousaf Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 5.48 | 239.97 | 2.13 | 2.13 | 239.97 | 100% | Completed
22 | Silt Clearance/removal of heaps of 1/9 Guide Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 7 | 479.94 | 2.74 | 2.74 | 479.94 | 100% | Completed
23 | Silt Clearance/removal of heaps of Koragh Branch RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 14.93 | 479.94 | 2.23 | 2.23 | 479.94 | 100% | Completed
24 | Removal of heaps of Disty No.8 RD: 0 to 38000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 11.58 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
25 | Removal of heaps of Disty No.9 RD: 0 to 41000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 12.5 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
26 | Swabi Irrigation Division-II Swabi
27 | Clearance of Topi Lift Irrigation Channels RD;00-Tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 4.88 | 1161.77 | 2.84 | 2.77 | 1139.39 | 98% | Work in progress
28 | Clearance of Topi & Zarobi Minors from RD;00 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | Topi =4.24 Zarobi =4.27 | 1159.72 | 3.05 | 2.74 | 1095.85 | 90% | Work in progress
29 | Clearance/Repair of Badri Lift Irrigation Scheme | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 0.34 | 607.12 | 0.33 | 0.33 | 607.12 | 100% | Competed
30 | Clearance of Kotha Disty; from RD;00 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.24 | 0.24 | 17.53 | 1389.07 | 1.89 | 1.89 | 1389.07 | 100% | Competed
31 | Clearance of Pehur main Canal from RD;46000 to RD;54000 | Swabi Irrigation Division-II Swabi | 0.18 | 0.18 | 51.4 | 1042.24 | 0.53 | 0.53 | 1042.24 | 100% | Competed
32 | Clearance of Pehur Main Canal from RD;54500 to RD;66000 | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 51.4 | 1130.88 | 0.55 | 0.49 | 967.65 | 89% | Work in progress
33 | Clearance of Pehur Main Canal from RD;66000 to RD;85000 | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.92 | 0.7 | 0.67 | 1333.14 | 96% | Work in progress
34 | Clearance of Pehur Main Canal RD;85000 to RD;93000 | Swabi Irrigation Division-II Swabi | 0.16 | 0.16 | 51.4 | 976.63 | 0.63 | 0.63 | 976.63 | 100% | Competed
35 | Clearance of Pehur Main Canal from RD;93500 to RD;98000 | Swabi Irrigation Division-II Swabi | 0.17 | 0.17 | 51.4 | 1033.5 | 0.32 | 0.29 | 795 | 91% | Work in progress
36 | Clearance of Pehur Main Canal from RD;98500 to RD;113000 | Swabi Irrigation Division-II Swabi | 0.18 | 0.18 | 51.4 | 1094.71 | 0.61 | 0.57 | 985.07 | 94% | Work in progress
37 | Clearance of Kaddi, Zaida, Zakarriya & Sheikhdheri Minors from RD;00 to Tail | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | Kaddi= 5.79 Zaida= 3.81 Zakary=3.43 S/Dher=2.95 | 1292.45 | 0.39 | 0.36 | 948.47 | 91% | Work in progress
38 | Clearance of Pehur Main Canal System from RD;113000 to RD;117000 | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 51.4 | 883 | 0.4 | 0.4 | 883 | 100% | Competed
39 | Clearance of Pehur Main Canal System from RD;117000 to RD;122000 | Swabi Irrigation Division-II Swabi | 0.12 | 0.12 | 51.4 | 729.53 | 0.22 | 0.22 | 729.53 | 100% | Competed
40 | Clearance of Pehur main Canal System from RD;122000 to RD;133000 | Swabi Irrigation Division-II Swabi | 0.13 | 0.13 | 51.4 | 790.91 | 0.4 | 0.38 | 697.59 | 95% | Work in progress
41 | Clearance of PMC System from RD;133000 to 140000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 51.4 | 1738.06 | 0.85 | 0.85 | 1738.06 | 100% | Competed
42 | Clearance of PMC Systems from RD;145000 to RD;150000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.23 | 0.23 | 51.4 | 1332.82 | 0.41 | 0.37 | 1211.65 | 91% | Work in progress
43 | Clearance of PMC System from RD;150500 to RD;162000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.81 | 0.44 | 0.4 | 1297.59 | 91% | Work in progress
44 | Clearance of PMC System from RD;162100 to Tail & other allied Branches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.85 | 3.23 | 3.11 | 1406.71 | 96% | Work in progress
45 | Clearance of Thanodher Disty: & Bazar Minor from RD;00 to Tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | Thano=6.00 Bazar=7.47 | 1157.95 | 0.35 | 0.27 | 1000.58 | 77% | Work in progress
46 | Clearance of flood deposition and silt clearance of ¦Indus Branch RD:74500 Tail in reaches. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 18.54 | 4478 | 11.89 | 11.89 | 4478 | 100% | Competed
47 | Silt Clearance of Dagi Minor from RD:0- 37000 in reaches i/c repair to out lets & other allied structures. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 11.28 | 4482 | 9.15 | 9.15 | 4482 | 100% | Competed
48 | Silt Clearance of Dandoka Minor from RD:0-Tail in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.03 | 2246.38 | 4.27 | 4.27 | 2246.38 | 100% | Competed
49 | Silt Clearance of Sudher Minor RD:0 - tail in reaches & other allied structures | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 2.29 | 1684.86 | 1.83 | 1.83 | 1684.86 | 100% | Competed
50 | Silt Clearance of Yar Hussain Minor RD;0-tail | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 6.8 | 2803.37 | 5.79 | 2.13 | 891.98 | 37% | Work in progress
51 | Silt Clearance of Ghazi Kot Minor from RD: 0-tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.95 | 2244.11 | 4.57 | 4.57 | 2244.11 | 100% | Competed
52 | Silt Clearance Daulat Minor and Gidar Minor RD; 0-tail in reaches & other allied structures | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 16.84 | 4482 | 13.11 | 13.11 | 4482 | 100% | Competed
53 | Silt Clearance of Pirsabaq Disty and pirsabaq Minor from Rd:0-tail in reaches. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 11.75 | 4946.41 | 14.21 | 10.67 | 3984.01 | 75% | Work in progress
54 | Silt Clearance of Chowky Disty, Chowki Minor 1 and 2 from RD: 00 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 8.23 | 3710.22 | 11.1 | 6.16 | 2766.7 | 55% | Work in progress
55 | Silt Clearance of Gumbat Minor No.1 & Gumbat Branch from RD:0+0 to tail in reaches., | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 5.18 | 3096.09 | 6.46 | 4.57 | 2731.49 | 71% | Work in progress
56 | Silt Clearance of Misri Banda from RD;0 to tal in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.73 | 2472.77 | 5.4 | 3.96 | 2063.58 | 73% | Work in progress
57 | Silt Clearance of Ambar Branch from RD;0+0 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.35 | 0.35 | 7.88 | 3923.31 | 3.9 | 1.22 | 764.57 | 31% | Work in progress
58 | Silt Clearance of Jehangira Minor & Nandrak Minor from RD;0-tail in reaches and repair to allied structures | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 11.52 | 2293.66 | 7.01 | 2.74 | 1132.69 | 39% | Work in progress
59 | Silt Clearance of Thanodher Minor & Manki Minor from RD;0-tail in reaches | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 12.42 | 1090.2 | 5.18 | 5.18 | 1090.15 | 100% | Competed
60 | Silt Clearance of Yaqubi Minor, Sard China Minor and Naik Nam Minor from RD; 0-tail | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 10.46 | 1684.86 | 7.44 | 7.44 | 1684.84 | 100% | Competed
61 | Silt Clearance of Dagi Disty & repair to allied structures Rd 0 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 3.23 | 1158.16 | 2.16 | 1.37 | 693.76 | 63% | Work in progress
62 | Silt Clerance of Gumbat Minor No 2 | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 4.57 | 1855.74 | 4.12 | 2.13 | 953.14 | 52% | Work in progress
63 | Silt Clearance and repair of Link Channel, Lahor Minor ,Zakaria Minor Sheik Dheri from RD; 0- to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 8.19 | 948.62 | 1.52 | 1.52 | 948.62 | 100% | Competed
46 | Jue Shiekh Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 16.29 | 13.03 | 53.35 | 132353 | 53.35 | 53.35 | 132353 | 100% | Completed
47 | Jue Zardad Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 3.6 | 2.88 | 13.1 | 18500 | 13.1 | 13.1 | 18500 | 100% | Completed
48 | Kabul River Canal | Peshawar Canal Division, Peshawar (Kabaul River Canal Sub Division) | 27.855 | 22.284 | 60.35 | 1062085 | 60.35 | 50.3 | 885261 | 83% | Work is in progress
49 | Hazar Khwani Branch | Peshawar Canal Division, Peshawar (Kabul River Canal Sub Division) | 23.2 | 18.56 | 28.04 | 1016303 | 28.04 | 25.3 | 916992 | 90% | Work is in progress
50 | Silt Clearance of Lower Siran Canal RD 0-14000 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3110.16 | 3.04 | 2.86 | 2647.99 | 85% | In progress
51 | Silt Clearance of Lower Siran Canal RD 14000-36500 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3142.51 | 4.26 | 3.62 | 2195.38 | 70% | In progress
52 | Silt Clearance of Lower Siran Canal Hathi Maira Branch & Gandian Minor RD 36500 in reaches | Mansehra Irrigation Division Mansehra | 0.55 | 0.4954 | 26.21 | 2080.06 | 12.1 | 10.64 | 1770.32 | 85% | In progress
53 | Silt Clearance of Ichar Canal/ Kalghan Minor RD 0-tail in reaches | Mansehra Irrigation Division Mansehra | 0.25 | 0.2254 | 5.97 | 1197.78 | 5.66 | 2.77 | 716.41 | 60% | In progress
54 | Silt Clearance of Upper Siran Canal from RD 0-30000 In reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2065 | 3.048 | 2.76 | 1238.63 | 60% | In progress
55 | Silt Clearance of Upper Siran Canal from RD 30000-61000 in reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2110 | 9.44 | 9.44 | 2110 | 100% | In progress
56 | Silt Clearance of Upper Siran Canal from RD 61000-tail in reaches | Mansehra Irrigation Division Mansehra | 0.18 | 0.1623 | 23.86 | 930 | 5.27 | 4.05 | 744.3 | 80% | In progress
57 | Silt Clearance of Dhodial Minor Upper Siran Canal in reaches | Mansehra Irrigation Division Mansehra | 0.22 | 0.1981 | 5.24 | 1135 | 5.24 | 4.68 | 1018.67 | 90% | In progress
58 | Nipki Khel Irrigation Scheme | Swat Irrigation Division -I | 2.2 | 1.76 | 38.87 | 10172.62 | 38.87 | 26.8293 | 7040 | 69.02% | Work is in progress
59 | Desiltation / berm cutting/Jungle clearance of Disty No.04, RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 10.11 | 5964.26 | 5.64 | 4.51 | 4771.41 | 80% | Work is in progress.
60 | Desiltation / berm cutting/Jungle clearance of Disty No.5 & its Minor and sub Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 26.31 | 7688.07 | 8.2 | 6.15 | 5766.05 | 75% | Work is in progress.
61 | Desiltation / berm cutting/Jungle clearance of Dera Disty RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 16.7 | 5812.06 | 6.55 | 5.9 | 5230.85 | 90% | Work is in progress.
62 | Silt clearance/ jungle clearance of Muryali Minor RD. 00-15000 in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.64 | 4021.01 | 5.33 | 0 | 0 | 0% | Work is in progress.
63 | Silt clearance/ jungle clearance including removal of debris of Lachra Minor/Makali Minor in reaches. | CRBC Irrigation Division DIKhan | 0.25 | 0.23 | 3.92 | 2402.7 | 11.3 | 2.83 | 600.68 | 25% | Work is in progress.
64 | Desiltation / berm cutting/Jungle clearance of Mehmood Disty. RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.05 | 5737.19 | 4.42 | 4.07 | 5278.21 | 92% | Work is in progress.
65 | Desiltation / berm cutting/Jungle clearance of Nawab Minor RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.3 | 0.27 | 7.62 | 2952 | 2.59 | 2.31 | 2627.28 | 89% | work in progress
66 | Desiltation / berm cutting/Jungle clearance of Disty No.7, i/c Minors of Disty No.7 RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 30.53 | 7801.33 | 15.37 | 10.14 | 5148.88 | 66% | work in progress
67 | Desiltation / berm cutting/Jungle clearance of Disty No. 8 & 8-A, RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.29 | 3999 | 3.95 | 3.75 | 3799.05 | 95% | work in progress
68 | Desiltation / berm cutting/Jungle clearance of Disty No.9 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.71 | 3560.86 | 2.9 | 1.16 | 1424.34 | 40% | work in progress
69 | Desiltation / berm cutting/Jungle clearance of Disty No.10 & 10/A RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11 | 3950.22 | 3.19 | 1.21 | 1501.08 | 38% | yet to be started
70 | Desiltation / berm cutting/Jungle clearance of Disty No. 11 & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 9.1 | 5670.47 | 10.66 | 8.53 | 4536.38 | 80% | work in progress
71 | Desiltation / berm cutting/Jungle clearance of Disty No. 11-A, & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 21.86 | 7695.14 | 5.93 | 3.08 | 4001.47 | 52% | work in progress
72 | Desiltation / berm cutting/Jungle clearance of Disty No. 12 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.23 | 5762.51 | 4.11 | 3.9 | 5474.38 | 95% | work in progress
73 | Desiltation /Jungle Clearance of Disty # 13 & its System RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.675 | 0.6075 | 21.655 | 4256.03 | 4.66 | 4.36 | 4170.9 | 98% | Work is in progress.
74 | Shingling of CPR & Jungle Clearance of Disty # 14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.725 | 0.6525 | 21.616 | 4176.75 | 4.58 | 4.53 | 4134.98 | 99% | Work is in progress.
75 | Shingling of CPR & Jungle Clearance of MD-14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.433 | 2145.01 | 2.43 | 2.38 | 2102 | 98% | Work is in progress.
76 | Shingling of CPR & Jungle Clearance of Disty # 15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.7 | 0.63 | 21.494 | 3752 | 3.65 | 3.28 | 3377 | 90% | Work is in progress.
77 | Shingling of CPR & Jungle Clearance of MD-15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.325 | 0.2925 | 5.8384 | 1862.55 | 2.28 | 0.57 | 466 | 25% | Work is in progress.
78 | Shingling of CPR & Jungle Clearance of Disty 16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 12.75 | 3018 | 2.5 | 0.87 | 1056 | 35% | Work is in progress.
79 | Shingling of CPR & Jungle Clearance of Minor of Disty-16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.8445 |  | 2.45 | 0 |  | 0% | Work not yet started.
80 | Desiltation / Jungle Clearance of Disty # 17 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 9.6951 |  | 2.13 | 0 |  | 0% | Work not yet started.
81 | Shingling of CPR & Jungle Clearance of Disty # 18 its Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 18.009 |  | 4.26 | 0 |  | 0% | Work not yet started.
82 | Shingling of CPR & Jungle Clearance of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.55 | 0.495 | 15.753 |  | 3.96 | 0 |  | 0% | Work not yet started.
83 | Desiltation / Jungle Clearance of M-1 & M-2 of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.829 |  | 4 | 0 |  | 0% | Work not yet started.
84 | Removal of Heaps / Clearance of Bari Band Disty RD: 39+500-88+600 in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.33775 | 14.96 | 1435.76 | 8.21 | 8.09 | 1415 | 98.54% | Work in Progress
85 | Removal of Heaps / Clearance of Hero Shah Minor RD: 0 -38+000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 11.58 | 2446.93 | 11.58 | 11.15 | 2350 | 96.29% | Work in Progress
86 | Removal of Heaps / Clearance of Kalu Shah Disty and Dundian Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.1 | 0.098 | 7.69 | 785.8 | 5 | 5 | 785.8 | 100% | Completed
87 | Removal of Heaps / Clearance of Sarwala Disty and Lund Khwar Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 18.29 | 3172.99 | 10.06 | 10.06 | 3172.99 | 100% | Completed
88 | Removal of Heaps / Clearance of Said Abad Disty and Pir Abad Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 20.42 | 3113.1 | 7.31 | 7.31 | 3113.1 | 100% | Completed
89 | Removal of Heaps / Clearance of Katlang Disty from RD: 0-40+000 in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 12.19 | 1910.43 | 7.61 | 7.61 | 1910.43 | 100% | Completed
90 | Removal of Heaps / Clearance of Shamozai Disty/ Syphon and Likpani Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.392 | 17.67 | 2730.62 | 13.01 | 13.01 | 2730.62 | 100% | Completed
91 | Removal of Heaps / Clearance of Dheri Minor and Tail Minor Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.15 | 0.147 | 7.01 | 1211.68 | 6 | 6 | 1211.68 | 100% | Completed
92 | Bazai Main Canal Head Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 10.5 | 10.5 | 1168.075 | 100% | Completed
93 | Wartair Disty | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 6 | 587.93 | 6 | 6 | 587.93 | 100% | Completed
94 | Kharki Disty No. 02 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 3.3 | 1272.34 | 3.3 | 3.3 | 1272.34 | 100% | Completed
95 | Additional Minor No. 03, 06 and Bazai Disty No. 01. | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | 16.8 | 1272.14 | 3 | 3 | 1272.14 | 100% | Completed
96 | Bazai Main Canal, Syphon No. 4431, 5851, 12530, 13590, 14842, 18400, 47527 & 58853 | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | [5 empty] | 70% | Work in Progress
97 | Bazai Disty No. 04, Bazai Minor No. 09, 11 and 12. | Malakand Irrigation Division Malakand | 0.27 | 0.26625 | 15.2 | 4070 | 9 | 9 | 4070 | 100% | Completed
98 | Clearance of Syphon 79205, 93480 and 97962. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | [5 empty] | 20% | Work in Progress
99 | Bazai Disty No. 03 and Bazai Minor No. 05. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | 20.5 | 1907.82 | 7 | 7 | 1907.82 | 100% | Completed
100 | Bazai Main Canal Tail Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 4.78 | 4.78 | 1168.075 | 100% | Completed
101 | KM-1 RD: 0-2976 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 143.26 | 0.9 | 0.9 | 143.26 | 100% | Completed
102 | KM-1 RD: 0-1500, 22000-29000 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 410.62 | 2.6 | 2.6 | 410.62 | 100% | Completed
103 | Bazai Main Canal RD: 79500 to RD: 84500 | Malakand Irrigation Division Malakand | 0.302 | 0.296 | 39 | 649.87 | 1.5 | 1.4 | 606.52 | 93.33% | Work in Progress
104 | Silt & Shingle Clearance of P.C Minor from RD 0+000 To Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.388 | 12.881 | 1851.77 | 7.62 | 6.1 | 1681.41 | 80% | Work in Progress
105 | Clearance of Shingri Minor from RD 0-17250 in reaches. | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.309 | 530.92 | 2.347 | 2.31 | 479.52 | 98.42% | Work in Progress
106 | Clearance of Meherdi Minor from RD 0-31000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 9.451 | 2167.5 | 8.382 | 6.21 | 1605.68 | 74.08% | Work in Progress
107 | Clearance of Kalu Branch from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.33 | 0.3218 | 11.563 | 1318.25 | 5 | 4.6 | 1212.79 | 92% | Work in Progress
108 | Clearance of Hathian Minor from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.05 | 0.04875 | 2.35 |  |  | 0 | 0 | 0% | Not yet started
109 | Clearance of Jalala Disty from RD: 29000 to Tail in reaches | Malakand Irrigation Division Malakand | 0.37 | 0.3607 | 14.024 | 1476.73 | 5900 | 5400 | 1351.5 | 91.52% | Work in Progress
110 | Clearance of Pirsaddo Disty, Ghano Minor and Qutab Gharh Minor from : H-Tail to Tail in reaches. | Malakand Irrigation Division Malakand | 0.35 | 0.341 | 1.88 |  |  | 0 | 0 | 0% | Not yet started
111 | Clearance of Shergarh Minor from Head to Rd:12+000 in reaches. | Malakand Irrigation Division Malakand | 0.15 | 0.146 | 7.752 |  |  | 0 | 0 | 0% | Not yet started
112 | Clearance of Shergarh Minor from Rd:12+000 tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 7.752 | 1195.13 | 6000 | 5500 | 956.83 | 91.66% | Work in Progress
113 | Clearance of Spokanda Disty from RD: 18000 to Tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 5.659 | 1215.5 | 4.97 | 1.52 | 493.17 | 30.58% | Work in Progress
114 | Silt & Shingle Clearance of Spokanda Disty from 0-18000 | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.488 | 771.85 | 2.743 | 1.34 | 378.2 | 48.85% | Work in Progress
115 | Silt clearance from RD:0+00 to RD:8+000 in reaches of Ghazai Khani Flow Irrigation Scheme | Swat Irrigation Division -I | 0.24 | 0.213 | 2.438 | 1339.39 | 2.44 | 2.25 | 750 | 56% | Work in Progress
116 | "Silt clearance from RD:0+00 to RD:12+000 in reaches of Karshalizara Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.1199 | 3.657 | 613 | 3.66 | 2.6 | 500 | 81.57% | Work in Progress
117 | "Silt clearance from RD:0+00 to RD:20+000 in reaches of Charorai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.15 | 0.135 | 6.096 | 766.25 | 6.1 | 4.8 | 698 | 91.09% | Work in Progress
118 | "Silt clearance from RD:0+00 to RD:12+000 in reaches of Kuriya Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.25 | 0.225 | 3.657 | 1397.44 | 3.66 | 2.9 | 780 | 55.82% | Work in Progress
119 | "Silt clearance from RD:0+00 to RD:9+000 in reaches of Elai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 2.743 | 613 | 2.74 | 2.4 | 370 | 60.36% | Work in Progress
120 | "Silt clearance from RD:0+00 to RD:60+000 in reaches of Budal Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 18.287 | 672.53 | 9.14 | 6.2 | 360 | 53.53% | Work in Progress
121 | "Silt clearance from RD:0+00 to RD:16+000 in reaches of Singarai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 4.267 | 669.7 | 4.27 | 3 | 370 | 55.25% | Work in Progress
122 | "Silt clearance from RD:0+00 to RD:26+000 in reaches of Bajkata Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.24 | 0.216 | 7.924 | 408.66 | 7.92 | 4.8 | 300 | 73.41% | Work in Progress
123 | Silt clearance from RD:0+00 to RD:34+000 in reaches of Gagra Flow Irrigation Scheme | Swat Irrigation Division -I | 0.5 | 0.4 | 10.363 | 2797 | 9.75 | 5.4 | 1820 | 65.07% | Work in Progress
125 | De-siltation / Berm Cutting of Additional Disty RD.00-Tail in reaches i/c Link channel of Additional Disty RD.00-Tail in reaches | Paharpur Irrigation Division DIKhan | 0.3 | 0.3 | 30 | 3421 | 3 | 2.25 | 2565.75 | 75% | Work is in progress
126 | De-siltation of Chashma Minor, Bilot Disty # 2 & 3, RD 00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.35 | 0.35 | 18.27 | 3182.64 | 8.5 | 6.63 | 2482.46 | 78% | Work is in progress
127 | De-siltation/Berm cutting of Takarwah Disty RD.00-36000 in reaches | Paharpur Irrigation Division DIKhan | 0.4 | 0.4 | 10.98 | 4562 | 1.8 | 1.62 | 4105.8 | 90% | Work is in progress
128 | De-siltation of Bilot Minor & Umray Wali Minor RD.0-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.3 | 0.3 | 11.55 | 3016.72 | 4.5 | 3.6 | 2413.38 | 80% | Work is in progress
129 | De-siltation of Kot Hafiz Disty RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.4 | 0.4 | 28.35 | 3954.92 | 4.5 | 3.38 | 2966.19 | 75% | Work is in progress
130 | De-siltation of Puran Minor i/c its Minors RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.3 | 0.3 | 13.6 | 3272 | 4 | 2.4 | 1963.2 | 60% | Work is in progress
131 | De-siltation of Segra Minor RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.2 | 0.2 | 12.25 | 2280.66 | 2.5 | 1.45 | 1322.78 | 58% | Work is in progress
132 | De-siltation of Takarwah Disty RD 36000-86000 in reaches. | Paharpur Irrigation Division DIKhan | 0.3 | 0.3 | 15.24 | 3420.98 | 3 | 2.55 | 2907.83 | 85% | Work is in progress
133 | De-siltation of Mala Minor RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.25 | 0.25 | 7.62 | 2850.82 | 2.5 | 1.25 | 1425.41 | 50% | Work is in progress
134 | De-siltation/ Jungle Clearance of Bigwani Minor RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.4 | 0.4 | 11.54 | 4561.31 | 3.5 | 2.63 | 3420.98 | 75% | Work is in progress
135 | De-siltation of Kat Garh Minor RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.25 | 0.25 | 6.39 | 2850.82 | 3 | 2.1 | 1995.57 | 70% | Work is in progress
136 | De-siltation of Kotla Minor & Disty # 1 RD.00-Tail in reaches i/c Jungle Clearance in reaches. | Paharpur Irrigation Division DIKhan | 0.4 | 0.4 | 7.72 | 3719.23 | 4 | 3 | 2789.42 | 75% | Work is in progress
137 | De-siltation of Upstream Dicth Channels RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.25 | 0.25 | 2 | 5678 | 2 | 1.52 | 4315.28 | 76% | Work is in progress
138 | De-siltation of Downstream Ditch Channels RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.25 | 0.25 | 4 | 1841 | 2 | 1.54 | 1417.57 | 77% | Work is in progress
139 | De-siltation of Disty No.2 & Disty # 3 RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.4 | 0.4 | 8.27 | 4561.31 | 2 | 1.5 | 3420.98 | 75% | Work is in progress
140 | De-siltation of Shah Kot Minor RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.2 | 0.2 | 8.32 | 2280.66 | 3 | 1.68 | 1277.17 | 56% | Work is in progress
141 | De-siltation of Shah Kot Feeder RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.35 | 0.35 | 1.5 | 3991.15 | 1.5 | 0.92 | 2434.6 | 61% | Work is in progress
142 | De-siltation of Bund Korai Minor RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.3 | 0.3 | 4.5 | 2814.59 | 3 | 1.65 | 1548.02 | 55% | Work is in progress
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086

## 15-02-2023
S# | Name of Canal | Name of Division | Estimated Cost(RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Total Quantity of Silt to be removed (m3) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Total Quantity of Silt removed till date (m3) | Progress Till date in % | Remarks
1 | Shamizai Irrigation Canal | Swat Irrigation Division-II Matta | 1 | 0.779 | 20.73 | 5150 | 19.5 | 19.5 | 5150 | 100% | Completed
2 | Barwai Irrigation Canal | Swat Irrigation Division-II Matta | 0.3 | 0.2805 | 11.22 | 1300 | 6.1 | 6.1 | 1300 | 100% | Completed
3 | Silt clearance from RD:0+00 to RD:8+000 in reaches of Ghazai Khani Flow Irrigation Scheme | Swat Irrigation Division -I | 0.24 | 0.213 | 2.438 | 1339.39 | 2.44 | 2.3 | 800 | 59.73% | Work in Progress
4 | "Silt clearance from RD:0+00 to RD:12+000 in reaches of Karshalizara Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.1199 | 3.657 | 613 | 3.66 | 2.8 | 530 | 86.46% | Work in Progress
5 | "Silt clearance from RD:0+00 to RD:20+000 in reaches of Charorai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.15 | 0.135 | 6.096 | 766.25 | 6.1 | 4.9 | 710 | 92.66% | Work in Progress
6 | "Silt clearance from RD:0+00 to RD:12+000 in reaches of Kuriya Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.25 | 0.225 | 3.657 | 1397.44 | 3.66 | 3 | 810 | 57.96% | Work in Progress
8 | "Silt clearance from RD:0+00 to RD:9+000 in reaches of Elai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 2.743 | 613 | 2.74 | 2.45 | 380 | 61.99% | Work in Progress
9 | "Silt clearance from RD:0+00 to RD:60+000 in reaches of Budal Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 18.287 | 672.53 | 9.14 | 6.5 | 410 | 60.96% | Work in Progress
10 | "Silt clearance from RD:0+00 to RD:16+000 in reaches of Singarai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 4.267 | 669.7 | 4.27 | 3.23 | 420 | 62.71% | Work in Progress
11 | "Silt clearance from RD:0+00 to RD:26+000 in reaches of Bajkata Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.24 | 0.216 | 7.924 | 408.66 | 7.92 | 5.2 | 350 | 85.65% | Work in Progress
12 | Silt clearance from RD:0+00 to RD:34+000 in reaches of Gagra Flow Irrigation Scheme | Swat Irrigation Division -I | 0.5 | 0.4 | 10.363 | 2797 | 9.75 | 6.5 | 1850 | 66.14% | Work in Progress
10 | De-siltation / Berm Cutting of Additional Disty RD.00-Tail in reaches i/c Link channel of Additional Disty RD.00-Tail in reaches | Paharpur Irrigation Division DIKhan | 0.3 | 0.3 | 30 | 3421 | 3 | 2.25 | 2565.75 | 75% | Work is in progress
11 | De-siltation of Chashma Minor, Bilot Disty # 2 & 3, RD 00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.35 | 0.35 | 18.27 | 3182.64 | 8.5 | 6.63 | 2482.46 | 78% | Work is in progress
12 | De-siltation/Berm cutting of Takarwah Disty RD.00-36000 in reaches | Paharpur Irrigation Division DIKhan | 0.4 | 0.4 | 10.98 | 4562 | 1.8 | 1.62 | 4105.8 | 90% | Work is in progress
13 | De-siltation of Bilot Minor & Umray Wali Minor RD.0-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.3 | 0.3 | 11.55 | 3016.72 | 4.5 | 3.6 | 2413.38 | 80% | Work is in progress
14 | De-siltation of Kot Hafiz Disty RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.4 | 0.4 | 28.35 | 3954.92 | 4.5 | 3.38 | 2966.19 | 75% | Work is in progress
15 | De-siltation of Puran Minor i/c its Minors RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.3 | 0.3 | 13.6 | 3272 | 4 | 2.4 | 1963.2 | 60% | Work is in progress
16 | De-siltation of Segra Minor RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.2 | 0.2 | 12.25 | 2280.66 | 2.5 | 1.45 | 1322.78 | 58% | Work is in progress
17 | De-siltation of Takarwah Disty RD 36000-86000 in reaches. | Paharpur Irrigation Division DIKhan | 0.3 | 0.3 | 15.24 | 3420.98 | 3 | 2.55 | 2907.83 | 85% | Work is in progress
18 | De-siltation of Mala Minor RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.25 | 0.25 | 7.62 | 2850.82 | 2.5 | 1.25 | 1425.41 | 50% | Work is in progress
19 | De-siltation/ Jungle Clearance of Bigwani Minor RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.4 | 0.4 | 11.54 | 4561.31 | 3.5 | 2.63 | 3420.98 | 75% | Work is in progress
20 | De-siltation of Kat Garh Minor RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.25 | 0.25 | 6.39 | 2850.82 | 3 | 2.1 | 1995.57 | 70% | Work is in progress
21 | De-siltation of Kotla Minor & Disty # 1 RD.00-Tail in reaches i/c Jungle Clearance in reaches. | Paharpur Irrigation Division DIKhan | 0.4 | 0.4 | 7.72 | 3719.23 | 4 | 3 | 2789.42 | 75% | Work is in progress
22 | De-siltation of Upstream Dicth Channels RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.25 | 0.25 | 2 | 5678 | 2 | 1.52 | 4315.28 | 76% | Work is in progress
23 | De-siltation of Downstream Ditch Channels RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.25 | 0.25 | 4 | 1841 | 2 | 1.54 | 1417.57 | 77% | Work is in progress
24 | De-siltation of Disty No.2 & Disty # 3 RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.4 | 0.4 | 8.27 | 4561.31 | 2 | 1.5 | 3420.98 | 75% | Work is in progress
25 | De-siltation of Shah Kot Minor RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.2 | 0.2 | 8.32 | 2280.66 | 3 | 1.68 | 1277.17 | 56% | Work is in progress
26 | De-siltation of Shah Kot Feeder RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.35 | 0.35 | 1.5 | 3991.15 | 1.5 | 0.92 | 2434.6 | 61% | Work is in progress
27 | De-siltation of Bund Korai Minor RD.00-Tail in reaches. | Paharpur Irrigation Division DIKhan | 0.3 | 0.3 | 4.5 | 2814.59 | 3 | 1.65 | 1548.02 | 55% | Work is in progress
28 | Jue Shiekh Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 16.29 | 13.03 | 53.35 | 132353 | 53.35 | 53.35 | 132353 | 100% | Completed
29 | Jue Zardad Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 3.6 | 2.88 | 13.1 | 18500 | 13.1 | 13.1 | 18500 | 100% | Completed
30 | Kabul River Canal | Peshawar Canal Division, Peshawar (Kabaul River Canal Sub Division) | 27.855 | 22.284 | 60.35 | 1062085 | 60.35 | 51 | 897581 | 85% | Work is in progress
31 | Hazar Khwani Branch | Peshawar Canal Division, Peshawar (Kabul River Canal Sub Division) | 23.2 | 18.56 | 28.04 | 1016303 | 28.04 | 25.3 | 916992 | 90% | Work is in progress
32 | Silt clearance/removal of heaps of Disty No. 9 RD; 41000 to 85500 | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 13.41 | 599.93 | 1 | 1 | 599.93 | 100% | Completed
33 | Silt clearance of Power House Minor RD 0 to tail | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 1.28 | 599.9 | 1.28 | 1.28 | 599.9 | 100% | Completed
34 | Silt clearance of conduit covering portion of 2/9 Hoti Minor RD 4200 to 5000, 5800 to 7000 & 7200 to 7500 | Mardan Irrigation Division Mardan | 0.7 | 0.4546 | 0.7 | 745.53 | 0.7 | 0.7 | 745.53 | 100% | Completed
35 | Silt clearance of 2/9 Hoti Minor RD 0 to 4200, 5000 to 5800 & 7500 to 19000 | Mardan Irrigation Division Mardan | 0.8 | 0.5195 | 5.94 | 921.08 | 2.43 | 2.37 | 898.34 | 98% | In progress
36 | Silt clearance /removal of heaps of kalpani disty RD 0-51000 in reaches and clearance of syphones RD 10500 and 15000 | Mardan Irrigation Division Mardan | 0.7 | 0.4544 | 15.6 | 4463.54 | 5.07 | 5.07 | 4463.54 | 100% | Completed
37 | Silt clearance /removal of heaps of 1/kalpani Kodinaka Minor RD 0-27000 in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 8.22 | 599.94 | 1.82 | 1.71 | 563.68 | 94% | In progress
38 | Silt clearance /removal of heaps of 2/kalpani Taus Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 6.4 | 2801.12 | 5.5 | 5.5 | 2801.12 | 100% | Completed
39 | Silt clearance of 3/9 Toru Minor RD 0 to 15800 | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 4.81 | 2801.12 | 4.81 | 4.81 | 2801.12 | 100% | Completed
40 | Silt clearance of branch 2/kalpani Muhib Banda Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.175 | 0.1308 | 2.89 | 1633.98 | 2 | 2 | 1633.98 | 100% | Completed
41 | Silt Clearance of Maho Dheri Minor RD: 4000 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.1493 | 4.57 | 1138.2 | 3.35 | 3.35 | 1138.2 | 100% | Completed
42 | Silt Clearance of Rashakai Minor from RD: 7000 to 31000 in reaches | Mardan Irrigation Division Mardan | 0.6 | 0.3894 | 9.45 | 2972.29 | 7.31 | 7.31 | 2972.29 | 100% | Completed
43 | Silt Clearance of Nowshera Minor RD:0 - tail in reachers | Mardan Irrigation Division Mardan | 0.35 | 0.2613 | 5.18 | 2059.85 | 3.2 | 3.2 | 2059.85 | 100% | Completed
44 | Silt Clearance of Turlandi Minor Head to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 5.27 | 2134.4 | 4.71 | 4.71 | 2134.4 | 100% | Completed
45 | Silt Clearance of Khan Mahi Branch from RD: 0 to 3000 and RD: 8000 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 13.41 | 2344.08 | 5.48 | 5.48 | 2344.08 | 100% | Completed
46 | Silt Clearance of Bara Banda Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 3.04 | 1703.02 | 3.04 | 3.04 | 1703.02 | 100% | Completed
47 | Removal of heaps of Disty No. 8 RD: 52000 to 68000 in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 9.45 | 1860.72 | 1.43 | 1.43 | 1860.72 | 100% | Completed
48 | Silt Clearance/removal of heaps of Disty No. 7 at RD: 4000 to 14000 in reaches | Mardan Irrigation Division Mardan | 0.15 | 0.1133 | 4.26 | 1400.56 | 3.04 | 3.04 | 1400.56 | 100% | Completed
49 | Silt Clearance/removal of heaps of Sheikh yousaf Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 5.48 | 239.97 | 2.13 | 2.13 | 239.97 | 100% | Completed
50 | Silt Clearance/removal of heaps of 1/9 Guide Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 7 | 479.94 | 2.74 | 2.74 | 479.94 | 100% | Completed
51 | Silt Clearance/removal of heaps of Koragh Branch RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 14.93 | 479.94 | 2.23 | 2.23 | 479.94 | 100% | Completed
52 | Removal of heaps of Disty No.8 RD: 0 to 38000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 11.58 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
53 | Removal of heaps of Disty No.9 RD: 0 to 41000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 12.5 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
54 | Swabi Irrigation Division-I Swabi
55 | Shahbaz Garhi Sub Division
56 | Clearance from the bed of Jamal Garhi Disty from 00-tail in reaches. | Swabi Irrigation Division-I Swabi | 0.3 | 0.11 | 16.81 | 1692.37 | 4.7 | 4.6 | 1658.52 | 98% | In-Progress
57 | Silt Clearance from the bed of Buxali Disty & Kot Minor from 00-tail in reaches | Swabi Irrigation Division-I Swabi | 0.65 | 0.36 | 21.34 | 4715.26 | 9.42 | 7.5 | 4526.65 | 96% | In-Progress
58 | Removal of debris and heaps from Machai Branch RD 105+000 to 142+000 in reaches | Swabi Irrigation Division-I Swabi | 0.35 | 0.13 | 247.58 | 4521.89 | 0.48 | 0.3 | 4160.14 | 92% | In-Progress
59 | Removal of debris and heaps from Machai Branch RD 142+000 to 186+000 in reaches | Swabi Irrigation Division-I Swabi | 0.35 | 0.13 | 247.58 | 4513.02 | 0.35 | 0.3 | 4490.45 | 99.5% | In-Progress
60 | Silt Clearance from the bed of Chura Minor , Sawal Dher Minor & Mala Minor from RD: 00-tail in reaches. | Swabi Irrigation Division-I Swabi | 0.3 | 0.11 | 14.38 | 1698.88 | 7 | 5.4 | 1681.89 | 99% | In-Progress
61 | Silt clearance from the bed Shahbaz Garhi Disty and its sub System from RD:00-tail in reaches | Swabi Irrigation Division-I Swabi | 0.8 | 0.44 | 18.29 | 4522.69 | 14.85 | 12.5 | 4341.78 | 96% | In-Progress
62 | Silt Clearance from the bed of Ismalia Disty and its sub system from 00-tail in reaches | Swabi Irrigation Division-I Swabi | 0.9 | 0.5 | 18.29 | 6469.09 | 13.26 | 11.7 | 6404.4 | 99% | In-Progress
63 | Silt Clearance from the bed of Adina Minor and adina Minor Branch from Head to tail in reaches | Swabi Irrigation Division-I Swabi | 0.35 | 0.19 | 7.89 | 1980.17 | 5.59 | 4.7 | 1920.76 | 97% | In-Progress
Gohati Sub Division
64 | Silt Clearance of Machai Branch at RD: 186000-252000 in reaches | Swabi Irr:Divn-1 Swabi | 1 | 0.45 | 24.764 | 9344.56 | 3.2 | 2.9 | 8600 | 92% | In progress
65 | Silt Clearance of Kalu Khan Disty and its sub system from RD: 00-tail in reaches | Swabi Irr:Divn-1 Swabi | 1 | 0.45 | 53.87 | 8707 | 27.54 | 23.5 | 7100 | 82% | In progress
66 | Silt Clearance of Nawan Killi Minor ,Sarbandi Minor, Shagai Minor RD:00- tail in reaches | Swabi Irr:Divn-1 Swabi | 0.3 | 0.155 | 4.69 2.92 5.18 12.79 | 2288.51 | 8.8 | 7.15 | 2050.12 | 90% | In progress
67 | Silt Clearance of , Naranji Disty & Naranji Minor No.1 & 2 RD: 00-tail in reaches | Swabi Irr:Divn-1 Swabi | 0.3 | 0.15 | 10.3963 3.04 1.58 15.01 | 2465 | 9.14 | 6.3 | 2300 | 93% | In progress
68 | Silt Clearance of Old Indus branch & Zaida Minor RD:0-Tail in reaches | Swabi Irr:Divn-1 Swabi | 0.4 | 0.2 | 9.84 2.97 12.81 | 4193 | 8.84 | 8.84 | 4093 | 98% | In progress
69 | Silt Clearance of Pehur branch and its sub system RD:0-Tail in reaches | Swabi Irr:Divn-1 Swabi | 1 | 0.55 | 30.69 | 8240 | 15.85 | 13.45 | 7300 | 89% | In progress
70 | Silt Clearance of Disty No.6 from RD: 55+000 to 60+000 in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.18292 | 0.15468 | 22.25 | 538.02 | 0.61 | 0.61 | 538.02 | 1 | Completed
71 | Silt Clearance of Disty No.6 from RD: 60+000 to 65+000 in reaches. | -do- | 0.15681 | 0.13259 | 22.25 | 460.15 | 0.45 | 0.45 | 460.15 | 1 | Completed
72 | Silt Clearance of Disty No.6 from RD: 65+000 to 73+000 in reaches. | -do- | 0.19992 | 0.16905 | 22.25 | 587.58 | 0.61 | 0.61 | 587.58 | 1 | Completed
73 | Silt Clearance of Nisatta Branch from RD: 0+000 to Tail in reaches. | -do- | 0.33551 | 0.2837 | 11.88 | 991.1 | 1 | 0.9 | 891.99 | 0.9 | Work in progress
74 | Silt Clearance of Nisatta Minor from RD: 0+000 to Tail in reaches. | -do- | 0.2176 | 0.184 | 3.35 | 877.83 | 2 | 1.9 | 833.9385 | 0.95 | Work in progress
75 | Silt Clearance of Palosa Minor from RD: 0+000 to Tail in reaches. | -do- | 0.25255 | 0.21355 | 5.03 | 748.98 | 1.35 | 1.2825 | 711.531 | 0.95 | Work in progress
76 | Silt Clearance of Zardad and Kheshki Branch in reaches. | -do- | 0.34775 | 0.29406 | 14.49 | 1880.25 | 7 | 7 | 1880.25 | 1 | Completed
Swabi Irrigation Division-II Swabi
77 | Clearance of Topi Lift Irrigation Channels RD;00-Tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 4.88 | 1161.77 | 2.84 | 2.77 | 1139.39 | 98% | Work in progress
78 | Clearance of Topi & Zarobi Minors from RD;00 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | Topi =4.24 Zarobi =4.27 | 1159.72 | 3.05 | 2.74 | 1095.85 | 90% | Work in progress
79 | Clearance/Repair of Badri Lift Irrigation Scheme | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 0.34 | 607.12 | 0.33 | 0.33 | 607.12 | 100% | Competed
80 | Clearance of Kotha Disty; from RD;00 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.24 | 0.24 | 17.53 | 1389.07 | 1.89 | 1.89 | 1389.07 | 100% | Competed
81 | Clearance of Pehur main Canal from RD;46000 to RD;54000 | Swabi Irrigation Division-II Swabi | 0.18 | 0.18 | 51.4 | 1042.24 | 0.53 | 0.53 | 1042.24 | 100% | Competed
82 | Clearance of Pehur Main Canal from RD;54500 to RD;66000 | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 51.4 | 1130.88 | 0.55 | 0.49 | 967.65 | 89% | Work in progress
83 | Clearance of Pehur Main Canal from RD;66000 to RD;85000 | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.92 | 0.7 | 0.67 | 1333.14 | 96% | Work in progress
84 | Clearance of Pehur Main Canal RD;85000 to RD;93000 | Swabi Irrigation Division-II Swabi | 0.16 | 0.16 | 51.4 | 976.63 | 0.63 | 0.63 | 976.63 | 100% | Competed
85 | Clearance of Pehur Main Canal from RD;93500 to RD;98000 | Swabi Irrigation Division-II Swabi | 0.17 | 0.17 | 51.4 | 1033.5 | 0.32 | 0.29 | 795 | 91% | Work in progress
86 | Clearance of Pehur Main Canal from RD;98500 to RD;113000 | Swabi Irrigation Division-II Swabi | 0.18 | 0.18 | 51.4 | 1094.71 | 0.61 | 0.57 | 985.07 | 94% | Work in progress
87 | Clearance of Kaddi, Zaida, Zakarriya & Sheikhdheri Minors from RD;00 to Tail | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | Kaddi= 5.79 Zaida= 3.81 Zakary=3.43 S/Dher=2.95 | 1292.45 | 0.39 | 0.36 | 948.47 | 91% | Work in progress
88 | Clearance of Pehur Main Canal System from RD;113000 to RD;117000 | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 51.4 | 883 | 0.4 | 0.4 | 883 | 100% | Competed
89 | Clearance of Pehur Main Canal System from RD;117000 to RD;122000 | Swabi Irrigation Division-II Swabi | 0.12 | 0.12 | 51.4 | 729.53 | 0.22 | 0.22 | 729.53 | 100% | Competed
90 | Clearance of Pehur main Canal System from RD;122000 to RD;133000 | Swabi Irrigation Division-II Swabi | 0.13 | 0.13 | 51.4 | 790.91 | 0.4 | 0.38 | 697.59 | 95% | Work in progress
91 | Clearance of PMC System from RD;133000 to 140000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 51.4 | 1738.06 | 0.85 | 0.85 | 1738.06 | 100% | Competed
92 | Clearance of PMC Systems from RD;145000 to RD;150000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.23 | 0.23 | 51.4 | 1332.82 | 0.41 | 0.37 | 1211.65 | 91% | Work in progress
93 | Clearance of PMC System from RD;150500 to RD;162000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.81 | 0.44 | 0.4 | 1297.59 | 91% | Work in progress
94 | Clearance of PMC System from RD;162100 to Tail & other allied Branches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.85 | 3.23 | 3.11 | 1406.71 | 96% | Work in progress
95 | Clearance of Thanodher Disty: & Bazar Minor from RD;00 to Tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | Thano=6.00 Bazar=7.47 | 1157.95 | 0.35 | 0.35 | 1000.58 | 100% | Competed
96 | Clearance of flood deposition and silt clearance of ¦Indus Branch RD:74500 Tail in reaches. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 18.54 | 4478 | 11.89 | 11.89 | 4478 | 100% | Competed
97 | Silt Clearance of Dagi Minor from RD:0- 37000 in reaches i/c repair to out lets & other allied structures. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 11.28 | 4482 | 9.15 | 9.15 | 4482 | 100% | Competed
98 | Silt Clearance of Dandoka Minor from RD:0-Tail in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.03 | 2246.38 | 4.27 | 4.27 | 2246.38 | 100% | Competed
99 | Silt Clearance of Sudher Minor RD:0 - tail in reaches & other allied structures | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 2.29 | 1684.86 | 1.83 | 1.83 | 1684.86 | 100% | Competed
100 | Silt Clearance of Yar Hussain Minor RD;0-tail | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 6.8 | 2803.37 | 5.79 | 4.88 | 2503.15 | 84% | Work in progress
101 | Silt Clearance of Ghazi Kot Minor from RD: 0-tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.95 | 2244.11 | 4.57 | 4.57 | 2244.11 | 100% | Competed
102 | Silt Clearance Daulat Minor and Gidar Minor RD; 0-tail in reaches & other allied structures | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 16.84 | 4482 | 13.11 | 13.11 | 4482 | 100% | Competed
103 | Silt Clearance of Pirsabaq Disty and pirsabaq Minor from Rd:0-tail in reaches. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 11.75 | 4946.41 | 14.21 | 14.21 | 4946.41 | 100% | Competed
104 | Silt Clearance of Chowky Disty, Chowki Minor 1 and 2 from RD: 00 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 8.23 | 3710.22 | 11.1 | 11.1 | 3710.22 | 100% | Competed
105 | Silt Clearance of Gumbat Minor No.1 & Gumbat Branch from RD:0+0 to tail in reaches., | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 5.18 | 3096.09 | 6.46 | 6.46 | 3096.09 | 100% | Competed
106 | Silt Clearance of Misri Banda from RD;0 to tal in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.73 | 2472.77 | 5.4 | 5.4 | 2472.77 | 100% | Competed
107 | Silt Clearance of Ambar Branch from RD;0+0 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.35 | 0.35 | 7.88 | 3923.31 | 3.9 | 2.13 | 2164.57 | 55% | Work in progress
108 | Silt Clearance of Jehangira Minor & Nandrak Minor from RD;0-tail in reaches and repair to allied structures | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 11.52 | 2293.66 | 7.01 | 7.01 | 2293.66 | 100% | Competed
109 | Silt Clearance of Thanodher Minor & Manki Minor from RD;0-tail in reaches | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 12.42 | 1090.2 | 5.18 | 5.18 | 1090.15 | 100% | Competed
110 |  | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 10.46 | 1684.86 | 7.44 | 7.44 | 1684.84 | 100% | Competed
111 | Silt Clearance of Dagi Disty & repair to allied structures Rd 0 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 3.23 | 1158.16 | 2.16 | 2.16 | 1158.16 | 100% | Competed
112 | Silt Clerance of Gumbat Minor No 2 | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 4.57 | 1855.74 | 4.12 | 4.12 | 1855.74 | 100% | Competed
113 | Silt Clearance and repair of Link Channel, Lahor Minor ,Zakaria Minor Sheik Dheri from RD; 0- to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 8.19 | 948.62 | 1.52 | 1.52 | 948.62 | 100% | Competed
114 | Silt Clerance of Toru Minor | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 4.57 | 1855 | 3.81 | 3.81 | 1855 | 100% | Competed
115 | Repair clearance of Sypon Rd 6200 & 8000 Pir Sabaq Disty | Swabi Irrigation Division-II Swabi | 0.1 | 0.1 | 0.06 | 60 | 0.06 | 0.06 | 60 | 100% | Competed
116 | Repair clearance of Sypon Rd 200 Gidar Minor | Swabi Irrigation Division-II Swabi | 0.05 | 0.05 | 0.05 | 37 | 0.04 | 0.04 | 37 | 100% | Competed
106 | CRBC Irrigation Division DIKhan
107 | Desiltation / berm cutting/Jungle clearance of Disty No.04, RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 10.11 | 5964.26 | 5.64 | 4.85 | 5129.26 | 86% | Work is in progress.
108 | Desiltation / berm cutting/Jungle clearance of Disty No.5 & its Minor and sub Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 26.31 | 7688.07 | 8.2 | 6.56 | 6150.46 | 80% | Work is in progress.
109 | Desiltation / berm cutting/Jungle clearance of Dera Disty RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 16.7 | 5812.06 | 6.55 | 6.22 | 5521.46 | 95% | Work is in progress.
110 | Silt clearance/ jungle clearance of Muryali Minor RD. 00-15000 in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.64 | 4021.01 | 5.33 | 0 | 0 | 0% | Work is in progress.
111 | Silt clearance/ jungle clearance including removal of debris of Lachra Minor/Makali Minor in reaches. | CRBC Irrigation Division DIKhan | 0.25 | 0.23 | 3.92 | 2402.7 | 11.3 | 3.96 | 840.95 | 35% | Work is in progress.
112 | Desiltation / berm cutting/Jungle clearance of Mehmood Disty. RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.05 | 5737.19 | 4.42 | 4.07 | 5278.21 | 92% | Work is in progress.
113 | Desiltation / berm cutting/Jungle clearance of Nawab Minor RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.3 | 0.27 | 7.62 | 2952 | 2.59 | 2.31 | 2627.28 | 89% | work in progress
114 | Desiltation / berm cutting/Jungle clearance of Disty No.7, i/c Minors of Disty No.7 RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 30.53 | 7801.33 | 15.37 | 10.76 | 5460.9 | 70% | work in progress
115 | Desiltation / berm cutting/Jungle clearance of Disty No. 8 & 8-A, RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.29 | 3999 | 3.95 | 3.75 | 3799.05 | 95% | work in progress
116 | Desiltation / berm cutting/Jungle clearance of Disty No.9 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.71 | 3560.86 | 2.9 | 1.36 | 1673.6 | 47% | work in progress
117 | Desiltation / berm cutting/Jungle clearance of Disty No.10 & 10/A RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11 | 3950.22 | 3.19 | 1.4 | 1738.1 | 44% | yet to be started
118 | Desiltation / berm cutting/Jungle clearance of Disty No. 11 & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 9.1 | 5670.47 | 10.66 | 9.06 | 4819.9 | 85% | work in progress
119 | Desiltation / berm cutting/Jungle clearance of Disty No. 11-A, & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 21.86 | 7695.14 | 5.93 | 3.56 | 4617.08 | 60% | work in progress
120 | Desiltation / berm cutting/Jungle clearance of Disty No. 12 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.23 | 5762.51 | 4.11 | 3.9 | 5474.38 | 95% | work in progress
121 | Desiltation /Jungle Clearance of Disty # 13 & its System RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.675 | 0.6075 | 21.655 | 4256.03 | 4.66 | 4.36 | 4170.9 | 98% | Work is in progress.
122 | Shingling of CPR & Jungle Clearance of Disty # 14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.725 | 0.6525 | 21.616 | 4176.75 | 4.58 | 4.53 | 4134.98 | 99% | Work is in progress.
123 | Shingling of CPR & Jungle Clearance of MD-14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.433 | 2145.01 | 2.43 | 2.38 | 2102 | 98% | Work is in progress.
124 | Shingling of CPR & Jungle Clearance of Disty # 15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.7 | 0.63 | 21.494 | 3752 | 3.65 | 3.28 | 3377 | 90% | Work is in progress.
125 | Shingling of CPR & Jungle Clearance of MD-15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.325 | 0.2925 | 5.8384 | 1862.55 | 2.28 | 0.57 | 466 | 35% | Work is in progress.
126 | Shingling of CPR & Jungle Clearance of Disty 16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 12.75 | 3018 | 2.5 | 0.87 | 1056 | 37% | Work is in progress.
127 | Shingling of CPR & Jungle Clearance of Minor of Disty-16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.8445 |  | 2.45 | 0 |  | 0% | Work not yet started.
128 | Desiltation / Jungle Clearance of Disty # 17 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 9.6951 |  | 2.13 | 0 |  | 0% | Work not yet started.
129 | Shingling of CPR & Jungle Clearance of Disty # 18 its Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 18.009 |  | 4.26 | 0 |  | 0% | Work not yet started.
130 | Shingling of CPR & Jungle Clearance of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.55 | 0.495 | 15.753 |  | 3.96 | 0 |  | 0% | Work not yet started.
131 | Desiltation / Jungle Clearance of M-1 & M-2 of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.829 |  | 4 | 0 |  | 0% | Work not yet started.
132 | Removal of Heaps / Clearance of Bari Band Disty RD: 39+500-88+600 in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.33775 | 14.96 | 1435.76 | 8.21 | 8.11 | 1415 | 98.78% | Work in Progress
133 | Removal of Heaps / Clearance of Hero Shah Minor RD: 0 -38+000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 11.58 | 2446.93 | 11.58 | 11.2 | 2350 | 96.72% | Work in Progress
134 | Removal of Heaps / Clearance of Kalu Shah Disty and Dundian Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.1 | 0.098 | 7.69 | 785.8 | 5 | 5 | 785.8 | 100% | Completed
135 | Removal of Heaps / Clearance of Sarwala Disty and Lund Khwar Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 18.29 | 3172.99 | 10.06 | 10.06 | 3172.99 | 100% | Completed
136 | Removal of Heaps / Clearance of Said Abad Disty and Pir Abad Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 20.42 | 3113.1 | 7.31 | 7.31 | 3113.1 | 100% | Completed
137 | Removal of Heaps / Clearance of Katlang Disty from RD: 0-40+000 in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 12.19 | 1910.43 | 7.61 | 7.61 | 1910.43 | 100% | Completed
138 | Removal of Heaps / Clearance of Shamozai Disty/ Syphon and Likpani Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.392 | 17.67 | 2730.62 | 13.01 | 13.01 | 2730.62 | 100% | Completed
139 | Removal of Heaps / Clearance of Dheri Minor and Tail Minor Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.15 | 0.147 | 7.01 | 1211.68 | 6 | 6 | 1211.68 | 100% | Completed
140 | Bazai Main Canal Head Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 10.5 | 10.5 | 1168.075 | 100% | Completed
141 | Wartair Disty | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 6 | 587.93 | 6 | 6 | 587.93 | 100% | Completed
142 | Kharki Disty No. 02 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 3.3 | 1272.34 | 3.3 | 3.3 | 1272.34 | 100% | Completed
143 | Additional Minor No. 03, 06 and Bazai Disty No. 01. | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | 16.8 | 1272.14 | 3 | 3 | 1272.14 | 100% | Completed
144 | Bazai Main Canal, Syphon No. 4431, 5851, 12530, 13590, 14842, 18400, 47527 & 58853 | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | [5 empty] | 70% | Work in Progress
145 | Bazai Disty No. 04, Bazai Minor No. 09, 11 and 12. | Malakand Irrigation Division Malakand | 0.27 | 0.26625 | 15.2 | 4070 | 9 | 9 | 4070 | 100% | Completed
146 | Clearance of Syphon 79205, 93480 and 97962. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | [5 empty] | 20% | Work in Progress
147 | Bazai Disty No. 03 and Bazai Minor No. 05. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | 20.5 | 1907.82 | 7 | 7 | 1907.82 | 100% | Completed
148 | Bazai Main Canal Tail Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 4.78 | 4.78 | 1168.075 | 100% | Completed
149 | KM-1 RD: 0-2976 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 143.26 | 0.9 | 0.9 | 143.26 | 100% | Completed
150 | KM-1 RD: 0-1500, 22000-29000 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 410.62 | 2.6 | 2.6 | 410.62 | 100% | Completed
151 | Bazai Main Canal RD: 79500 to RD: 84500 | Malakand Irrigation Division Malakand | 0.302 | 0.296 | 39 | 649.87 | 1.5 | 1.4 | 606.52 | 93.33% | Work in Progress
152 | Silt & Shingle Clearance of P.C Minor from RD 0+000 To Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.388 | 12.881 | 1851.77 | 7.62 | 6.1 | 1681.41 | 80% | Work in Progress
153 | Clearance of Shingri Minor from RD 0-17250 in reaches. | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.309 | 530.92 | 2.347 | 2.31 | 479.52 | 98.42% | Work in Progress
154 | Clearance of Meherdi Minor from RD 0-31000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 9.451 | 2167.5 | 8.382 | 6.21 | 1605.68 | 74.08% | Work in Progress
155 | Clearance of Kalu Branch from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.33 | 0.3218 | 11.563 | 1318.25 | 5 | 4.6 | 1212.79 | 92% | Work in Progress
156 | Clearance of Hathian Minor from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.05 | 0.04875 | 2.1 | 265.88 | 1.73 | 0.96 | 146.23 | 55.49% | Work in Progress
157 | Clearance of Jalala Disty from RD: 29000 to Tail in reaches | Malakand Irrigation Division Malakand | 0.37 | 0.3607 | 14.024 | 1476.73 | 5900 | 5400 | 1351.5 | 91.52% | Work in Progress
158 | Clearance of Pirsaddo Disty, Ghano Minor and Qutab Gharh Minor from : H-Tail to Tail in reaches. | Malakand Irrigation Division Malakand | 0.35 | 0.341 | 1.88 |  |  | 0 | 0 | 0% | Not yet started
159 | Clearance of Shergarh Minor from Head to Rd:12+000 in reaches. | Malakand Irrigation Division Malakand | 0.15 | 0.146 | 7.752 |  |  | 0 | 0 | 0% | Not yet started
160 | Clearance of Shergarh Minor from Rd:12+000 tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 7.752 | 1195.13 | 6000 | 5500 | 956.83 | 91.66% | Work in Progress
161 | Clearance of Spokanda Disty from RD: 18000 to Tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 5.659 | 1215.5 | 4.97 | 1.52 | 493.17 | 30.58% | Work in Progress
162 | Silt & Shingle Clearance of Spokanda Disty from 0-18000 | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.488 | 771.85 | 2.743 | 1.34 | 378.2 | 48.85% | Work in Progress
163 | Silt Clearance of Badwan Kharif Irrigation Scheme at RD 0+00 To Tail. | Chakdara Irrigation Sub Division ,Dir Division | 0.9 | 0.8957 | 22.18 | 4635.35 | 22.18 | 13.1 | 3009.6 | 64.92% | Work in progress
164 | Silt Clearance of Lower Siran Canal RD 0-14000 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3110.16 | 3.04 | 2.9 | 2931.15 | 94% | In progress
165 | Silt Clearance of Lower Siran Canal RD 14000-36500 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3142.51 | 4.26 | 3.83 | 2903.3 | 92% | In progress
166 | Silt Clearance of Lower Siran Canal Hathi Maira Branch & Gandian Minor RD 36500 in reaches | Mansehra Irrigation Division Mansehra | 0.55 | 0.4954 | 26.21 | 2080.06 | 12.1 | 11.09 | 1954.38 | 94% | In progress
167 | Silt Clearance of Ichar Canal/ Kalghan Minor RD 0-tail in reaches | Mansehra Irrigation Division Mansehra | 0.25 | 0.2254 | 5.97 | 1197.78 | 5.66 | 3.52 | 886.31 | 74% | In progress
168 | Silt Clearance of Upper Siran Canal from RD 0-30000 In reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2065 | 3.048 | 2.8 | 1351.89 | 65% | In progress
169 | Silt Clearance of Upper Siran Canal from RD 30000-61000 in reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2110 | 9.44 | 9.44 | 2110 | 100% | In progress
170 | Silt Clearance of Upper Siran Canal from RD 61000-tail in reaches | Mansehra Irrigation Division Mansehra | 0.18 | 0.1623 | 23.86 | 930 | 5.27 | 4.66 | 800.93 | 86% | In progress
171 | Silt Clearance of Dhodial Minor Upper Siran Canal in reaches | Mansehra Irrigation Division Mansehra | 0.22 | 0.1981 | 5.24 | 1135 | 5.24 | 4.79 | 1075.3 | 95% | In progress
172 | Silt clearance of Sarai Saleh NPC Rd 0-10000 in reaches | Haripur Irrigation Division Haripur | 0.35 | 0.283 | 15.85 | 1271 | 3.04 | 3 | 1250 | 95% | Work is in progress
173 | Silt clearance of Sarai Saleh NPC Rd 10000-17000 i/c Minor No.1 in reaches | Haripur Irrigation Division Haripur | 0.3 | 0.24 | 15.85 | 1131.96 | 2.13 | 2.01 | 1095.23 | 95% | Work is in progress
174 | Silt clearance of Sarai Saleh NPC Rd 17000-30000 i/c Minor No.2 in reaches | Haripur Irrigation Division Haripur | 0.35 | 0.28 | 15.85 | 1347 | 3.96 | 3.56 | 1298.99 | 95% | Work is in progress
175 | Clearance of Daur Main Canal Rd 0-tail | Haripur Irrigation Division Haripur | 0.15 | 0.1216 | 0.838 | 555.2 | 0.838 | 0.838 | 555.2 | 100% | Work completed
176 | Silt Clearance of Disty No.02 RD 0-20000 in reaches. | Haripur Irrigation Division Haripur | 0.25 | 0.2 | 6.62 | 1287.6 | 6.09 | 5.79 | 1210.58 | 95% | Work is in progress
177 | Silt Clearance of Main KRBC RD 11000-42000 in reaches | Haripur Irrigation Division Haripur | 0.25 | 0.225 | 12.8 | 1287.6 | 9.45 | 9.45 | 1287.6 | 100% | Work completed
178 | Silt Clearance Disty No.04 RD 0-24000 in reaches. | Haripur Irrigation Division Haripur | 0.3 | 0.24 | 7.31 | 1545.12 | 7.31 | 7.87 | 1467.89 | 90% | Work is in progress
179 | Silt Clearance of Disty No.03 i/c Ziarat Minor and Bandi Minor in reaches. | Haripur Irrigation Division Haripur | 0.3 | 0.24 | 10.67 | 1545.12 | 10.67 | 6.56 | 989.76 | 60% | Work is in progress
180 | Silt Clearance of Disty No.1 i/c Balartop & Kamalpur Minors in reaches. | haripur Irrigation Division Haripur | 0.3 | 0.24 | 10.36 | 1545.12 | 10.36 | 8.76 | 1245.67 | 85% | Work is in progress
181 | Silt Clearance of KLBC Rd 0-26000 in reaches | haripur Irrigation Division Haripur | 0.3 | 0.24 | 7.92 | 1545.12 | 7.92 | 154.3 | 0.59 | 105 | work in progress
182 | Silt clearance of Sarai Saleh NPC Rd 30000-40000 i/c Minor No. 3 in reaches | HAripur Irrigation Division Haripur | 0.25 | 0.2 | 15.85 | 946 | 3.04 | 2.56 | 723.87 | 75% | Work is in progress
183 | Clearance of Main Rangila Irrigation system i/c Rangila Tank | Haripur Irrigation Division Haripur | 0.2 | 0.173 | 2.21 | 559 | 2.21 | 1.89 | 310 | 65% | Work is in progress
184 | Silt Clearance of Chak Muneem Minor. | Haripur Irrigation Division Haripur | 0.2 | 0.16 | 7.01 | 1030.8 | 7.01 | 5.02 | 745 | 65% | Work is in progress
185 | Silt clearance of Kharabara Dam Channel | Haripur Irrigation Division Haripur | 0.1 | 0.08 | 2.8 | 515.1 | 2.8 | 2.5 | 4.65 | 85% | Work is in progress
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086

## 16-02-2023
S# | Name of Canal | Name of Division | Estimated Cost(RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Total Quantity of Silt to be removed (m3) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Total Quantity of Silt removed till date (m3) | Progress Till date in % | Remarks
1 | Shamizai Irrigation Canal | Swat Irrigation Division-II Matta | 1 | 0.779 | 20.73 | 5150 | 19.5 | 19.5 | 5150 | 100% | Completed
2 | Barwai Irrigation Canal | Swat Irrigation Division-II Matta | 0.3 | 0.2805 | 11.22 | 1300 | 6.1 | 6.1 | 1300 | 100% | Completed
3 | Jue Shiekh Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 16.29 | 13.03 | 53.35 | 132353 | 53.35 | 53.35 | 132353 | 100% | Completed
4 | Jue Zardad Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 3.6 | 2.88 | 13.1 | 18500 | 13.1 | 13.1 | 18500 | 100% | Completed
5 | Kabul River Canal | Peshawar Canal Division, Peshawar (Kabaul River Canal Sub Division) | 27.855 | 22.284 | 60.35 | 1062085 | 60.35 | 52.1 | 916941 | 86% | Work is in progress
6 | Hazar Khwani Branch | Peshawar Canal Division, Peshawar (Kabul River Canal Sub Division) | 23.2 | 18.56 | 28.04 | 1016303 | 28.04 | 25.3 | 916992 | 90% | Work is in progress
7 | Silt clearance from RD:0+00 to RD:8+000 in reaches of Ghazai Khani Flow Irrigation Scheme | Swat Irrigation Division -I | 0.24 | 0.213 | 2.438 | 1339.39 | 2.44 | 2.35 | 990 | 73.91% | Work in Progress
8 | "Silt clearance from RD:0+00 to RD:12+000 in reaches of Karshalizara Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.1199 | 3.657 | 613 | 3.66 | 2.9 | 545 | 88.91% | Work in Progress
9 | "Silt clearance from RD:0+00 to RD:20+000 in reaches of Charorai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.15 | 0.135 | 6.096 | 766.25 | 6.1 | 5.1 | 715 | 93.31% | Work in Progress
10 | "Silt clearance from RD:0+00 to RD:12+000 in reaches of Kuriya Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.25 | 0.225 | 3.657 | 1397.44 | 3.66 | 3.2 | 818 | 58.54% | Work in Progress
11 | "Silt clearance from RD:0+00 to RD:9+000 in reaches of Elai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 2.743 | 613 | 2.74 | 2.5 | 390 | 63.62% | Work in Progress
12 | "Silt clearance from RD:0+00 to RD:60+000 in reaches of Budal Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 18.287 | 672.53 | 9.14 | 6.6 | 415 | 61.71% | Work in Progress
13 | "Silt clearance from RD:0+00 to RD:16+000 in reaches of Singarai Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.12 | 0.108 | 4.267 | 669.7 | 4.27 | 3.5 | 480 | 71.67% | Work in Progress
14 | "Silt clearance from RD:0+00 to RD:26+000 in reaches of Bajkata Flow Irrigation Scheme" | Swat Irrigation Division -I | 0.24 | 0.216 | 7.924 | 408.66 | 7.92 | 5.25 | 355 | 86.87% | Work in Progress
15 | Silt clearance from RD:0+00 to RD:34+000 in reaches of Gagra Flow Irrigation Scheme | Swat Irrigation Division -I | 0.5 | 0.4 | 10.363 | 2797 | 9.75 | 7.2 | 1950 | 69.72% | Work in Progress
16 | Silt clearance/removal of heaps of Disty No. 9 RD; 41000 to 85500 | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 13.41 | 599.93 | 1 | 1 | 599.93 | 100% | Completed
17 | Silt clearance of Power House Minor RD 0 to tail | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 1.28 | 599.9 | 1.28 | 1.28 | 599.9 | 100% | Completed
18 | Silt clearance of conduit covering portion of 2/9 Hoti Minor RD 4200 to 5000, 5800 to 7000 & 7200 to 7500 | Mardan Irrigation Division Mardan | 0.7 | 0.4546 | 0.7 | 745.53 | 0.7 | 0.7 | 745.53 | 100% | Completed
19 | Silt clearance of 2/9 Hoti Minor RD 0 to 4200, 5000 to 5800 & 7500 to 19000 | Mardan Irrigation Division Mardan | 0.8 | 0.5195 | 5.94 | 921.08 | 2.43 | 2.37 | 898.34 | 98% | In progress
20 | Silt clearance /removal of heaps of kalpani disty RD 0-51000 in reaches and clearance of syphones RD 10500 and 15000 | Mardan Irrigation Division Mardan | 0.7 | 0.4544 | 15.6 | 4463.54 | 5.07 | 5.07 | 4463.54 | 100% | Completed
21 | Silt clearance /removal of heaps of 1/kalpani Kodinaka Minor RD 0-27000 in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 8.22 | 599.94 | 1.82 | 1.78 | 586.75 | 98% | In progress
22 | Silt clearance /removal of heaps of 2/kalpani Taus Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 6.4 | 2801.12 | 5.5 | 5.5 | 2801.12 | 100% | Completed
23 | Silt clearance of 3/9 Toru Minor RD 0 to 15800 | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 4.81 | 2801.12 | 4.81 | 4.81 | 2801.12 | 100% | Completed
24 | Silt clearance of branch 2/kalpani Muhib Banda Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.175 | 0.1308 | 2.89 | 1633.98 | 2 | 2 | 1633.98 | 100% | Completed
25 | Silt Clearance of Maho Dheri Minor RD: 4000 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.1493 | 4.57 | 1138.2 | 3.35 | 3.35 | 1138.2 | 100% | Completed
26 | Silt Clearance of Rashakai Minor from RD: 7000 to 31000 in reaches | Mardan Irrigation Division Mardan | 0.6 | 0.3894 | 9.45 | 2972.29 | 7.31 | 7.31 | 2972.29 | 100% | Completed
27 | Silt Clearance of Nowshera Minor RD:0 - tail in reachers | Mardan Irrigation Division Mardan | 0.35 | 0.2613 | 5.18 | 2059.85 | 3.2 | 3.2 | 2059.85 | 100% | Completed
28 | Silt Clearance of Turlandi Minor Head to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 5.27 | 2134.4 | 4.71 | 4.71 | 2134.4 | 100% | Completed
29 | Silt Clearance of Khan Mahi Branch from RD: 0 to 3000 and RD: 8000 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 13.41 | 2344.08 | 5.48 | 5.48 | 2344.08 | 100% | Completed
30 | Silt Clearance of Bara Banda Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 3.04 | 1703.02 | 3.04 | 3.04 | 1703.02 | 100% | Completed
31 | Removal of heaps of Disty No. 8 RD: 52000 to 68000 in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 9.45 | 1860.72 | 1.43 | 1.43 | 1860.72 | 100% | Completed
32 | Silt Clearance/removal of heaps of Disty No. 7 at RD: 4000 to 14000 in reaches | Mardan Irrigation Division Mardan | 0.15 | 0.1133 | 4.26 | 1400.56 | 3.04 | 3.04 | 1400.56 | 100% | Completed
33 | Silt Clearance/removal of heaps of Sheikh yousaf Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 5.48 | 239.97 | 2.13 | 2.13 | 239.97 | 100% | Completed
34 | Silt Clearance/removal of heaps of 1/9 Guide Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 7 | 479.94 | 2.74 | 2.74 | 479.94 | 100% | Completed
35 | Silt Clearance/removal of heaps of Koragh Branch RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 14.93 | 479.94 | 2.23 | 2.23 | 479.94 | 100% | Completed
36 | Removal of heaps of Disty No.8 RD: 0 to 38000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 11.58 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
37 | Removal of heaps of Disty No.9 RD: 0 to 41000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 12.5 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
38 | Swabi Irrigation Division-II Swabi
39 | Clearance of Topi Lift Irrigation Channels RD;00-Tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 4.88 | 1161.77 | 2.84 | 2.8 | 1143.64 | 99% | Work in progress
40 | Clearance of Topi & Zarobi Minors from RD;00 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | Topi =4.24 Zarobi =4.27 | 1159.72 | 3.05 | 2.9 | 1111.43 | 95% | Work in progress
41 | Clearance/Repair of Badri Lift Irrigation Scheme | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 0.34 | 607.12 | 0.33 | 0.33 | 607.12 | 100% | Competed
42 | Clearance of Kotha Disty; from RD;00 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.24 | 0.24 | 17.53 | 1389.07 | 1.89 | 1.89 | 1389.07 | 100% | Competed
43 | Clearance of Pehur main Canal from RD;46000 to RD;54000 | Swabi Irrigation Division-II Swabi | 0.18 | 0.18 | 51.4 | 1042.24 | 0.53 | 0.53 | 1042.24 | 100% | Competed
44 | Clearance of Pehur Main Canal from RD;54500 to RD;66000 | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 51.4 | 1130.88 | 0.55 | 0.52 | 974.73 | 94% | Work in progress
45 | Clearance of Pehur Main Canal from RD;66000 to RD;85000 | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.92 | 0.7 | 0.67 | 1336.83 | 96% | Work in progress
46 | Clearance of Pehur Main Canal RD;85000 to RD;93000 | Swabi Irrigation Division-II Swabi | 0.16 | 0.16 | 51.4 | 976.63 | 0.63 | 0.63 | 976.63 | 100% | Competed
47 | Clearance of Pehur Main Canal from RD;93500 to RD;98000 | Swabi Irrigation Division-II Swabi | 0.17 | 0.17 | 51.4 | 1033.5 | 0.32 | 0.29 | 1013.23 | 91% | Work in progress
48 | Clearance of Pehur Main Canal from RD;98500 to RD;113000 | Swabi Irrigation Division-II Swabi | 0.18 | 0.18 | 51.4 | 1094.71 | 0.61 | 0.59 | 1000.65 | 98% | Work in progress
49 | Clearance of Kaddi, Zaida, Zakarriya & Sheikhdheri Minors from RD;00 to Tail | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | Kaddi= 5.79 Zaida= 3.81 Zakary=3.43 S/Dher=2.95 | 1292.45 | 0.39 | 0.36 | 975.38 | 91% | Work in progress
50 | Clearance of Pehur Main Canal System from RD;113000 to RD;117000 | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 51.4 | 883 | 0.4 | 0.4 | 883 | 100% | Competed
51 | Clearance of Pehur Main Canal System from RD;117000 to RD;122000 | Swabi Irrigation Division-II Swabi | 0.12 | 0.12 | 51.4 | 729.53 | 0.22 | 0.22 | 729.53 | 100% | Competed
52 | Clearance of Pehur main Canal System from RD;122000 to RD;133000 | Swabi Irrigation Division-II Swabi | 0.13 | 0.13 | 51.4 | 790.91 | 0.4 | 0.38 | 697.59 | 96% | Work in progress
53 | Clearance of PMC System from RD;133000 to 140000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 51.4 | 1738.06 | 0.85 | 0.85 | 1738.06 | 100% | Competed
54 | Clearance of PMC Systems from RD;145000 to RD;150000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.23 | 0.23 | 51.4 | 1332.82 | 0.41 | 0.37 | 1211.65 | 91% | Work in progress
55 | Clearance of PMC System from RD;150500 to RD;162000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.81 | 0.44 | 0.4 | 1297.59 | 91% | Work in progress
56 | Clearance of PMC System from RD;162100 to Tail & other allied Branches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.85 | 3.23 | 3.14 | 1406.71 | 97% | Work in progress
57 | Clearance of Thanodher Disty: & Bazar Minor from RD;00 to Tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | Thano=6.00 Bazar=7.47 | 1157.95 | 0.35 | 0.35 | 1000.58 | 100% | Competed
58 | Clearance of flood deposition and silt clearance of ¦Indus Branch RD:74500 Tail in reaches. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 18.54 | 4478 | 11.89 | 11.89 | 4478 | 100% | Competed
59 | Silt Clearance of Dagi Minor from RD:0- 37000 in reaches i/c repair to out lets & other allied structures. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 11.28 | 4482 | 9.15 | 9.15 | 4482 | 100% | Competed
60 | Silt Clearance of Dandoka Minor from RD:0-Tail in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.03 | 2246.38 | 4.27 | 4.27 | 2246.38 | 100% | Competed
61 | Silt Clearance of Sudher Minor RD:0 - tail in reaches & other allied structures | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 2.29 | 1684.86 | 1.83 | 1.83 | 1684.86 | 100% | Competed
62 | Silt Clearance of Yar Hussain Minor RD;0-tail | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 6.8 | 2803.37 | 5.79 | 5.49 | 2703.5 | 95% | Work in progress
63 | Silt Clearance of Ghazi Kot Minor from RD: 0-tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.95 | 2244.11 | 4.57 | 4.57 | 2244.11 | 100% | Competed
64 | Silt Clearance Daulat Minor and Gidar Minor RD; 0-tail in reaches & other allied structures | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 16.84 | 4482 | 13.11 | 13.11 | 4482 | 100% | Competed
65 | Silt Clearance of Pirsabaq Disty and pirsabaq Minor from Rd:0-tail in reaches. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 11.75 | 4946.41 | 14.21 | 14.21 | 4946.41 | 100% | Competed
66 | Silt Clearance of Chowky Disty, Chowki Minor 1 and 2 from RD: 00 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 8.23 | 3710.22 | 11.1 | 11.1 | 3710.22 | 100% | Competed
67 | Silt Clearance of Gumbat Minor No.1 & Gumbat Branch from RD:0+0 to tail in reaches., | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 5.18 | 3096.09 | 6.46 | 6.46 | 3096.09 | 100% | Competed
68 | Silt Clearance of Misri Banda from RD;0 to tal in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.73 | 2472.77 | 5.4 | 5.4 | 2472.77 | 100% | Competed
69 | Silt Clearance of Ambar Branch from RD;0+0 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.35 | 0.35 | 7.88 | 3923.31 | 3.9 | 2.74 | 2971.57 | 70% | Work in progress
70 | Silt Clearance of Jehangira Minor & Nandrak Minor from RD;0-tail in reaches and repair to allied structures | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 11.52 | 2293.66 | 7.01 | 7.01 | 2293.66 | 100% | Competed
71 | Silt Clearance of Thanodher Minor & Manki Minor from RD;0-tail in reaches | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 12.42 | 1090.2 | 5.18 | 5.18 | 1090.15 | 100% | Competed
72 | Silt Clearance of Yaqubi Minor, Sard China Minor and Naik Nam Minor from RD; 0-tail | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 10.46 | 1684.86 | 7.44 | 7.44 | 1684.84 | 100% | Competed
73 | Silt Clearance of Dagi Disty & repair to allied structures Rd 0 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 3.23 | 1158.16 | 2.16 | 2.16 | 1158.16 | 100% | Competed
74 | Silt Clerance of Gumbat Minor No 2 | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 4.57 | 1855.74 | 4.12 | 4.12 | 1855.74 | 100% | Competed
75 | Silt Clearance and repair of Link Channel, Lahor Minor ,Zakaria Minor Sheik Dheri from RD; 0- to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 8.19 | 948.62 | 1.52 | 1.52 | 948.62 | 100% | Competed
76 | Silt Clerance of Toru Minor | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 4.57 | 1855 | 3.81 | 3.81 | 1855 | 100% | Competed
77 | Repair clearance of Sypon Rd 6200 & 8000 Pir Sabaq Disty | Swabi Irrigation Division-II Swabi | 0.1 | 0.1 | 0.06 | 60 | 0.06 | 0.06 | 60 | 100% | Competed
78 | Repair clearance of Sypon Rd 200 Gidar Minor | Swabi Irrigation Division-II Swabi | 0.05 | 0.05 | 0.05 | 37 | 0.04 | 0.04 | 37 | 100% | Competed
79 | Nipki Khel Irrigation Scheme | Swat Irrigation Division -I | 2.2 | 1.76 | 38.87 | 10172.62 | 38.87 | 27.7439 | 7280 | 71.38% | Work is in progress
80 | Desiltation / berm cutting/Jungle clearance of Disty No.04, RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 10.11 | 5964.26 | 5.64 | 5.3 | 5606.4 | 94% | Work is in progress.
81 | Desiltation / berm cutting/Jungle clearance of Disty No.5 & its Minor and sub Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 26.31 | 7688.07 | 8.2 | 7.22 | 6765.5 | 88% | Work is in progress.
82 | Desiltation / berm cutting/Jungle clearance of Dera Disty RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 16.7 | 5812.06 | 6.55 | 6.22 | 5521.46 | 95% | Work is in progress.
83 | Silt clearance/ jungle clearance of Muryali Minor RD. 00-15000 in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.64 | 4021.01 | 5.33 | 2.03 | 1527.98 | 38% | Work is in progress.
84 | Silt clearance/ jungle clearance including removal of debris of Lachra Minor/Makali Minor in reaches. | CRBC Irrigation Division DIKhan | 0.25 | 0.23 | 3.92 | 2402.7 | 11.3 | 5.31 | 1129.27 | 47% | Work is in progress.
85 | Desiltation / berm cutting/Jungle clearance of Mehmood Disty. RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.05 | 5737.19 | 4.42 | 4.2 | 5450.33 | 95% | Work is in progress.
86 | Desiltation / berm cutting/Jungle clearance of Nawab Minor RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.3 | 0.27 | 7.62 | 2952 | 2.59 | 2.43 | 2774.88 | 94% | work in progress
87 | Desiltation / berm cutting/Jungle clearance of Disty No.7, i/c Minors of Disty No.7 RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 30.53 | 7801.33 | 15.37 | 11.53 | 5851 | 75% | work in progress
88 | Desiltation / berm cutting/Jungle clearance of Disty No. 8 & 8-A, RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.29 | 3999 | 3.95 | 3.75 | 3799.05 | 95% | work in progress
89 | Desiltation / berm cutting/Jungle clearance of Disty No.9 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.71 | 3560.86 | 2.9 | 1.54 | 1887.26 | 53% | work in progress
90 | Desiltation / berm cutting/Jungle clearance of Disty No.10 & 10/A RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11 | 3950.22 | 3.19 | 1.6 | 1975.11 | 50% | yet to be started
91 | Desiltation / berm cutting/Jungle clearance of Disty No. 11 & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 9.1 | 5670.47 | 10.66 | 9.59 | 5103.42 | 90% | work in progress
92 | Desiltation / berm cutting/Jungle clearance of Disty No. 11-A, & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 21.86 | 7695.14 | 5.93 | 4.03 | 5232.7 | 68% | work in progress
93 | Desiltation / berm cutting/Jungle clearance of Disty No. 12 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.23 | 5762.51 | 4.11 | 3.9 | 5474.38 | 95% | work in progress
94 | Desiltation /Jungle Clearance of Disty # 13 & its System RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.675 | 0.6075 | 21.655 | 4256.03 | 4.66 | 4.36 | 4170.9 | 98% | Work is in progress.
95 | Shingling of CPR & Jungle Clearance of Disty # 14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.725 | 0.6525 | 21.616 | 4176.75 | 4.58 | 4.53 | 4134.98 | 99% | Work is in progress.
96 | Shingling of CPR & Jungle Clearance of MD-14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.433 | 2145.01 | 2.43 | 2.38 | 2102 | 98% | Work is in progress.
97 | Shingling of CPR & Jungle Clearance of Disty # 15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.7 | 0.63 | 21.494 | 3752 | 3.65 | 3.36 | 3452 | 92% | Work is in progress.
98 | Shingling of CPR & Jungle Clearance of MD-15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.325 | 0.2925 | 5.8384 | 1862.55 | 2.28 | 0.91 | 745 | 40% | Work is in progress.
99 | Shingling of CPR & Jungle Clearance of Disty 16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 12.75 | 3018 | 2.5 | 1 | 1207 | 40% | Work is in progress.
100 | Shingling of CPR & Jungle Clearance of Minor of Disty-16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.8445 |  | 2.45 | 0 |  | 0% | Work not yet started.
101 | Desiltation / Jungle Clearance of Disty # 17 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 9.6951 |  | 2.13 | 0 |  | 0% | Work not yet started.
102 | Shingling of CPR & Jungle Clearance of Disty # 18 its Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 18.009 |  | 4.26 | 0 |  | 0% | Work not yet started.
103 | Shingling of CPR & Jungle Clearance of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.55 | 0.495 | 15.753 |  | 3.96 | 0 |  | 0% | Work not yet started.
104 | Desiltation / Jungle Clearance of M-1 & M-2 of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.829 |  | 4 | 0 |  | 0% | Work not yet started.
105 | Silt Clearance of Lower Siran Canal RD 0-14000 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3110.16 | 3.04 | 2.94 | 3016.1 | 97% | In progress
106 | Silt Clearance of Lower Siran Canal RD 14000-36500 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3142.51 | 4.26 | 3.98 | 3030.72 | 96% | In progress
107 | Silt Clearance of Lower Siran Canal Hathi Maira Branch & Gandian Minor RD 36500 in reaches | Mansehra Irrigation Division Mansehra | 0.55 | 0.4954 | 26.21 | 2080.06 | 12.1 | 11.54 | 2019.51 | 97% | In progress
108 | Silt Clearance of Ichar Canal/ Kalghan Minor RD 0-tail in reaches | Mansehra Irrigation Division Mansehra | 0.25 | 0.2254 | 5.97 | 1197.78 | 5.66 | 4.28 | 1013.74 | 85% | In progress
109 | Silt Clearance of Upper Siran Canal from RD 0-30000 In reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2065 | 3.048 | 2.84 | 1465.16 | 71% | In progress
110 | Silt Clearance of Upper Siran Canal from RD 30000-61000 in reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2110 | 9.44 | 9.44 | 2110 | 100% | Completed
111 | Silt Clearance of Upper Siran Canal from RD 61000-tail in reaches | Mansehra Irrigation Division Mansehra | 0.18 | 0.1623 | 23.86 | 930 | 5.27 | 4.87 | 857.57 | 92% | In progress
112 | Silt Clearance of Dhodial Minor Upper Siran Canal in reaches | Mansehra Irrigation Division Mansehra | 0.22 | 0.1981 | 5.24 | 1135 | 5.24 | 4.88 | 1096.54 | 97% | In progress
113 | Removal of Heaps / Clearance of Bari Band Disty RD: 39+500-88+600 in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.33775 | 14.96 | 1435.76 | 8.21 | 8.21 | 1435.76 | 100% | Completed
114 | Removal of Heaps / Clearance of Hero Shah Minor RD: 0 -38+000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 11.58 | 2446.93 | 11.58 | 11.58 | 2446.93 | 100% | Completed
115 | Removal of Heaps / Clearance of Kalu Shah Disty and Dundian Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.1 | 0.098 | 7.69 | 785.8 | 5 | 5 | 785.8 | 100% | Completed
116 | Removal of Heaps / Clearance of Sarwala Disty and Lund Khwar Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 18.29 | 3172.99 | 10.06 | 10.06 | 3172.99 | 100% | Completed
117 | Removal of Heaps / Clearance of Said Abad Disty and Pir Abad Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 20.42 | 3113.1 | 7.31 | 7.31 | 3113.1 | 100% | Completed
118 | Removal of Heaps / Clearance of Katlang Disty from RD: 0-40+000 in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 12.19 | 1910.43 | 7.61 | 7.61 | 1910.43 | 100% | Completed
119 | Removal of Heaps / Clearance of Shamozai Disty/ Syphon and Likpani Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.392 | 17.67 | 2730.62 | 13.01 | 13.01 | 2730.62 | 100% | Completed
120 | Removal of Heaps / Clearance of Dheri Minor and Tail Minor Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.15 | 0.147 | 7.01 | 1211.68 | 6 | 6 | 1211.68 | 100% | Completed
121 | Bazai Main Canal Head Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 10.5 | 10.5 | 1168.075 | 100% | Completed
122 | Wartair Disty | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 6 | 587.93 | 6 | 6 | 587.93 | 100% | Completed
123 | Kharki Disty No. 02 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 3.3 | 1272.34 | 3.3 | 3.3 | 1272.34 | 100% | Completed
124 | Additional Minor No. 03, 06 and Bazai Disty No. 01. | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | 16.8 | 1272.14 | 3 | 3 | 1272.14 | 100% | Completed
125 | Bazai Main Canal, Syphon No. 4431, 5851, 12530, 13590, 14842, 18400, 47527 & 58853 | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | [5 empty] | 70% | Work in Progress
126 | Bazai Disty No. 04, Bazai Minor No. 09, 11 and 12. | Malakand Irrigation Division Malakand | 0.27 | 0.26625 | 15.2 | 4070 | 9 | 9 | 4070 | 100% | Completed
127 | Clearance of Syphon 79205, 93480 and 97962. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | [5 empty] | 20% | Work in Progress
128 | Bazai Disty No. 03 and Bazai Minor No. 05. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | 20.5 | 1907.82 | 7 | 7 | 1907.82 | 100% | Completed
129 | Bazai Main Canal Tail Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 4.78 | 4.78 | 1168.075 | 100% | Completed
130 | KM-1 RD: 0-2976 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 143.26 | 0.9 | 0.9 | 143.26 | 100% | Completed
131 | KM-1 RD: 0-1500, 22000-29000 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 410.62 | 2.6 | 2.6 | 410.62 | 100% | Completed
132 | Bazai Main Canal RD: 79500 to RD: 84500 | Malakand Irrigation Division Malakand | 0.302 | 0.296 | 39 | 649.87 | 1.5 | 1.4 | 606.52 | 93.33% | Work in Progress
133 | Silt & Shingle Clearance of P.C Minor from RD 0+000 To Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.388 | 12.881 | 1851.77 | 7.62 | 6.1 | 1681.41 | 80% | Work in Progress
134 | Clearance of Shingri Minor from RD 0-17250 in reaches. | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.309 | 530.92 | 2.347 | 2.31 | 479.52 | 98.42% | Work in Progress
135 | Clearance of Meherdi Minor from RD 0-31000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 9.451 | 2167.5 | 8.382 | 6.21 | 1605.68 | 74.08% | Work in Progress
136 | Clearance of Kalu Branch from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.33 | 0.3218 | 11.563 | 1318.25 | 5 | 4.6 | 1212.79 | 92% | Work in Progress
137 | Clearance of Hathian Minor from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.05 | 0.04875 | 2.1 | 265.88 | 1.73 | 0.96 | 146.23 | 55.49% | Work in Progress
138 | Clearance of Jalala Disty from RD: 29000 to Tail in reaches | Malakand Irrigation Division Malakand | 0.37 | 0.3607 | 14.024 | 1476.73 | 5900 | 5400 | 1351.5 | 91.52% | Work in Progress
139 | Clearance of Pirsaddo Disty, Ghano Minor and Qutab Gharh Minor from : H-Tail to Tail in reaches. | Malakand Irrigation Division Malakand | 0.35 | 0.341 | 1.88 |  |  | 0 | 0 | 0% | Not yet started
140 | Clearance of Shergarh Minor from Head to Rd:12+000 in reaches. | Malakand Irrigation Division Malakand | 0.15 | 0.146 | 7.752 |  |  | 0 | 0 | 0% | Not yet started
141 | Clearance of Shergarh Minor from Rd:12+000 tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 7.752 | 1195.13 | 6000 | 5500 | 956.83 | 91.66% | Work in Progress
142 | Clearance of Spokanda Disty from RD: 18000 to Tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 5.659 | 1215.5 | 4.97 | 1.52 | 493.17 | 30.58% | Work in Progress
143 | Silt & Shingle Clearance of Spokanda Disty from 0-18000 | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.488 | 771.85 | 2.743 | 1.34 | 378.2 | 48.85% | Work in Progress
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086

## 17-02-2023
S# | Name of Canal | Name of Division | Estimated Cost(RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Total Quantity of Silt to be removed (m3) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Total Quantity of Silt removed till date (m3) | Progress Till date in % | Remarks
1 | Shamizai Irrigation Canal | Swat Irrigation Division-II Matta | 1 | 0.779 | 20.73 | 5150 | 19.5 | 19.5 | 5150 | 100% | Completed
2 | Barwai Irrigation Canal | Swat Irrigation Division-II Matta | 0.3 | 0.2805 | 11.22 | 1300 | 6.1 | 6.1 | 1300 | 100% | Completed
3 | Silt clearance/removal of heaps of Disty No. 9 RD; 41000 to 85500 | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 13.41 | 599.93 | 1 | 1 | 599.93 | 100% | Completed
4 | Silt clearance of Power House Minor RD 0 to tail | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 1.28 | 599.9 | 1.28 | 1.28 | 599.9 | 100% | Completed
5 | Silt clearance of conduit covering portion of 2/9 Hoti Minor RD 4200 to 5000, 5800 to 7000 & 7200 to 7500 | Mardan Irrigation Division Mardan | 0.7 | 0.4546 | 0.7 | 745.53 | 0.7 | 0.7 | 745.53 | 100% | Completed
6 | Silt clearance of 2/9 Hoti Minor RD 0 to 4200, 5000 to 5800 & 7500 to 19000 | Mardan Irrigation Division Mardan | 0.8 | 0.5195 | 5.94 | 921.08 | 2.43 | 2.37 | 898.34 | 98% | In progress
7 | Silt clearance /removal of heaps of kalpani disty RD 0-51000 in reaches and clearance of syphones RD 10500 and 15000 | Mardan Irrigation Division Mardan | 0.7 | 0.4544 | 15.6 | 4463.54 | 5.07 | 5.07 | 4463.54 | 100% | Completed
8 | Silt clearance /removal of heaps of 1/kalpani Kodinaka Minor RD 0-27000 in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 8.22 | 599.94 | 1.82 | 1.78 | 586.75 | 98% | In progress
9 | Silt clearance /removal of heaps of 2/kalpani Taus Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 6.4 | 2801.12 | 5.5 | 5.5 | 2801.12 | 100% | Completed
10 | Silt clearance of 3/9 Toru Minor RD 0 to 15800 | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 4.81 | 2801.12 | 4.81 | 4.81 | 2801.12 | 100% | Completed
11 | Silt clearance of branch 2/kalpani Muhib Banda Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.175 | 0.1308 | 2.89 | 1633.98 | 2 | 2 | 1633.98 | 100% | Completed
12 | Silt Clearance of Maho Dheri Minor RD: 4000 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.1493 | 4.57 | 1138.2 | 3.35 | 3.35 | 1138.2 | 100% | Completed
13 | Silt Clearance of Rashakai Minor from RD: 7000 to 31000 in reaches | Mardan Irrigation Division Mardan | 0.6 | 0.3894 | 9.45 | 2972.29 | 7.31 | 7.31 | 2972.29 | 100% | Completed
14 | Silt Clearance of Nowshera Minor RD:0 - tail in reachers | Mardan Irrigation Division Mardan | 0.35 | 0.2613 | 5.18 | 2059.85 | 3.2 | 3.2 | 2059.85 | 100% | Completed
15 | Silt Clearance of Turlandi Minor Head to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 5.27 | 2134.4 | 4.71 | 4.71 | 2134.4 | 100% | Completed
16 | Silt Clearance of Khan Mahi Branch from RD: 0 to 3000 and RD: 8000 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 13.41 | 2344.08 | 5.48 | 5.48 | 2344.08 | 100% | Completed
17 | Silt Clearance of Bara Banda Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 3.04 | 1703.02 | 3.04 | 3.04 | 1703.02 | 100% | Completed
18 | Removal of heaps of Disty No. 8 RD: 52000 to 68000 in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 9.45 | 1860.72 | 1.43 | 1.43 | 1860.72 | 100% | Completed
19 | Silt Clearance/removal of heaps of Disty No. 7 at RD: 4000 to 14000 in reaches | Mardan Irrigation Division Mardan | 0.15 | 0.1133 | 4.26 | 1400.56 | 3.04 | 3.04 | 1400.56 | 100% | Completed
20 | Silt Clearance/removal of heaps of Sheikh yousaf Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 5.48 | 239.97 | 2.13 | 2.13 | 239.97 | 100% | Completed
21 | Silt Clearance/removal of heaps of 1/9 Guide Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 7 | 479.94 | 2.74 | 2.74 | 479.94 | 100% | Completed
22 | Silt Clearance/removal of heaps of Koragh Branch RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 14.93 | 479.94 | 2.23 | 2.23 | 479.94 | 100% | Completed
23 | Removal of heaps of Disty No.8 RD: 0 to 38000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 11.58 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
24 | Removal of heaps of Disty No.9 RD: 0 to 41000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 12.5 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
25 | Swabi Irrigation Division-II Swabi
26 | Clearance of Topi Lift Irrigation Channels RD;00-Tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 4.88 | 1161.77 | 2.84 | 2.82 | 1154.96 | 99% | Work in progress
27 | Clearance of Topi & Zarobi Minors from RD;00 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | Topi =4.24 Zarobi =4.27 | 1159.72 | 3.05 | 2.96 | 1120.2 | 97% | Work in progress
28 | Clearance/Repair of Badri Lift Irrigation Scheme | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 0.34 | 607.12 | 0.33 | 0.33 | 607.12 | 100% | Competed
29 | Clearance of Kotha Disty; from RD;00 to Tail in reaches | Swabi Irrigation Division-II Swabi | 0.24 | 0.24 | 17.53 | 1389.07 | 1.89 | 1.89 | 1389.07 | 100% | Competed
30 | Clearance of Pehur main Canal from RD;46000 to RD;54000 | Swabi Irrigation Division-II Swabi | 0.18 | 0.18 | 51.4 | 1042.24 | 0.53 | 0.53 | 1042.24 | 100% | Competed
31 | Clearance of Pehur Main Canal from RD;54500 to RD;66000 | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 51.4 | 1130.88 | 0.55 | 0.53 | 1005.88 | 97% | Work in progress
32 | Clearance of Pehur Main Canal from RD;66000 to RD;85000 | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.92 | 0.7 | 0.67 | 1352.4 | 96% | Work in progress
33 | Clearance of Pehur Main Canal RD;85000 to RD;93000 | Swabi Irrigation Division-II Swabi | 0.16 | 0.16 | 51.4 | 976.63 | 0.63 | 0.63 | 976.63 | 100% | Competed
34 | Clearance of Pehur Main Canal from RD;93500 to RD;98000 | Swabi Irrigation Division-II Swabi | 0.17 | 0.17 | 51.4 | 1033.5 | 0.32 | 0.29 | 1013.23 | 91% | Work in progress
35 | Clearance of Pehur Main Canal from RD;98500 to RD;113000 | Swabi Irrigation Division-II Swabi | 0.18 | 0.18 | 51.4 | 1094.71 | 0.61 | 0.59 | 1014.81 | 98% | Work in progress
36 | Clearance of Kaddi, Zaida, Zakarriya & Sheikhdheri Minors from RD;00 to Tail | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | Kaddi= 5.79 Zaida= 3.81 Zakary=3.43 S/Dher=2.95 | 1292.45 | 0.39 | 0.36 | 1003.69 | 91% | Work in progress
37 | Clearance of Pehur Main Canal System from RD;113000 to RD;117000 | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 51.4 | 883 | 0.4 | 0.4 | 883 | 100% | Competed
38 | Clearance of Pehur Main Canal System from RD;117000 to RD;122000 | Swabi Irrigation Division-II Swabi | 0.12 | 0.12 | 51.4 | 729.53 | 0.22 | 0.22 | 729.53 | 100% | Competed
39 | Clearance of Pehur main Canal System from RD;122000 to RD;133000 | Swabi Irrigation Division-II Swabi | 0.13 | 0.13 | 51.4 | 790.91 | 0.4 | 0.38 | 724.49 | 96% | Work in progress
40 | Clearance of PMC System from RD;133000 to 140000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 51.4 | 1738.06 | 0.85 | 0.85 | 1738.06 | 100% | Competed
41 | Clearance of PMC Systems from RD;145000 to RD;150000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.23 | 0.23 | 51.4 | 1332.82 | 0.41 | 0.37 | 1269.35 | 91% | Work in progress
42 | Clearance of PMC System from RD;150500 to RD;162000 & other allied Branches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.81 | 0.44 | 0.4 | 1311.75 | 91% | Work in progress
43 | Clearance of PMC System from RD;162100 to Tail & other allied Branches | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 51.4 | 1447.85 | 3.23 | 3.14 | 1409.83 | 97% | Work in progress
44 | Clearance of Thanodher Disty: & Bazar Minor from RD;00 to Tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | Thano=6.00 Bazar=7.47 | 1157.95 | 0.35 | 0.35 | 1071.37 | 100% | Competed
45 | Clearance of flood deposition and silt clearance of ¦Indus Branch RD:74500 Tail in reaches. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 18.54 | 4478 | 11.89 | 11.89 | 4478 | 100% | Competed
46 | Silt Clearance of Dagi Minor from RD:0- 37000 in reaches i/c repair to out lets & other allied structures. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 11.28 | 4482 | 9.15 | 9.15 | 4482 | 100% | Competed
47 | Silt Clearance of Dandoka Minor from RD:0-Tail in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.03 | 2246.38 | 4.27 | 4.27 | 2246.38 | 100% | Competed
48 | Silt Clearance of Sudher Minor RD:0 - tail in reaches & other allied structures | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 2.29 | 1684.86 | 1.83 | 1.83 | 1684.86 | 100% | Competed
49 | Silt Clearance of Yar Hussain Minor RD;0-tail | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 6.8 | 2803.37 | 5.79 | 5.49 | 2703.5 | 95% | Work in progress
50 | Silt Clearance of Ghazi Kot Minor from RD: 0-tail | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.95 | 2244.11 | 4.57 | 4.57 | 2244.11 | 100% | Competed
51 | Silt Clearance Daulat Minor and Gidar Minor RD; 0-tail in reaches & other allied structures | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 16.84 | 4482 | 13.11 | 13.11 | 4482 | 100% | Competed
52 | Silt Clearance of Pirsabaq Disty and pirsabaq Minor from Rd:0-tail in reaches. | Swabi Irrigation Division-II Swabi | 0.4 | 0.4 | 11.75 | 4946.41 | 14.21 | 14.21 | 4946.41 | 100% | Competed
53 | Silt Clearance of Chowky Disty, Chowki Minor 1 and 2 from RD: 00 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 8.23 | 3710.22 | 11.1 | 11.1 | 3710.22 | 100% | Competed
54 | Silt Clearance of Gumbat Minor No.1 & Gumbat Branch from RD:0+0 to tail in reaches., | Swabi Irrigation Division-II Swabi | 0.25 | 0.25 | 5.18 | 3096.09 | 6.46 | 6.46 | 3096.09 | 100% | Competed
55 | Silt Clearance of Misri Banda from RD;0 to tal in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 5.73 | 2472.77 | 5.4 | 5.4 | 2472.77 | 100% | Competed
56 | Silt Clearance of Ambar Branch from RD;0+0 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.35 | 0.35 | 7.88 | 3923.31 | 3.9 | 2.74 | 3471.57 | 70% | Work in progress
57 | Silt Clearance of Jehangira Minor & Nandrak Minor from RD;0-tail in reaches and repair to allied structures | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 11.52 | 2293.66 | 7.01 | 7.01 | 2293.66 | 100% | Competed
58 | Silt Clearance of Thanodher Minor & Manki Minor from RD;0-tail in reaches | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 12.42 | 1090.2 | 5.18 | 5.18 | 1090.15 | 100% | Competed
59 | Silt Clearance of Yaqubi Minor, Sard China Minor and Naik Nam Minor from RD; 0-tail | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 10.46 | 1684.86 | 7.44 | 7.44 | 1684.84 | 100% | Competed
60 | Silt Clearance of Dagi Disty & repair to allied structures Rd 0 to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.2 | 0.2 | 3.23 | 1158.16 | 2.16 | 2.16 | 1158.16 | 100% | Competed
61 | Silt Clerance of Gumbat Minor No 2 | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 4.57 | 1855.74 | 4.12 | 4.12 | 1855.74 | 100% | Competed
62 | Silt Clearance and repair of Link Channel, Lahor Minor ,Zakaria Minor Sheik Dheri from RD; 0- to tail in reaches. | Swabi Irrigation Division-II Swabi | 0.3 | 0.3 | 8.19 | 948.62 | 1.52 | 1.52 | 948.62 | 100% | Competed
63 | Silt Clerance of Toru Minor | Swabi Irrigation Division-II Swabi | 0.15 | 0.15 | 4.57 | 1855 | 3.81 | 3.81 | 1855 | 100% | Competed
64 | Repair clearance of Sypon Rd 6200 & 8000 Pir Sabaq Disty | Swabi Irrigation Division-II Swabi | 0.1 | 0.1 | 0.06 | 60 | 0.06 | 0.06 | 60 | 100% | Competed
65 | Repair clearance of Sypon Rd 200 Gidar Minor | Swabi Irrigation Division-II Swabi | 0.05 | 0.05 | 0.05 | 37 | 0.04 | 0.04 | 37 | 100% | Competed
66
67
68 | Desiltation / berm cutting/Jungle clearance of Disty No.04, RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 10.11 | 5964.26 | 5.64 | 5.3 | 5606.4 | 94% | Work is in progress.
69 | Desiltation / berm cutting/Jungle clearance of Disty No.5 & its Minor and sub Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 26.31 | 7688.07 | 8.2 | 7.22 | 6765.5 | 88% | Work is in progress.
70 | Desiltation / berm cutting/Jungle clearance of Dera Disty RD.00-Tail (in reaches). | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 16.7 | 5812.06 | 6.55 | 6.22 | 5521.46 | 95% | Work is in progress.
71 | Silt clearance/ jungle clearance of Muryali Minor RD. 00-15000 in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.64 | 4021.01 | 5.33 | 2.03 | 1527.98 | 38% | Work is in progress.
72 | Silt clearance/ jungle clearance including removal of debris of Lachra Minor/Makali Minor in reaches. | CRBC Irrigation Division DIKhan | 0.25 | 0.23 | 3.92 | 2402.7 | 11.3 | 5.31 | 1129.27 | 47% | Work is in progress.
73 | Desiltation / berm cutting/Jungle clearance of Mehmood Disty. RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.05 | 5737.19 | 4.42 | 4.2 | 5450.33 | 95% | Work is in progress.
74 | Desiltation / berm cutting/Jungle clearance of Nawab Minor RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.3 | 0.27 | 7.62 | 2952 | 2.59 | 2.43 | 2774.88 | 94% | work in progress
75 | Desiltation / berm cutting/Jungle clearance of Disty No.7, i/c Minors of Disty No.7 RD.00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 30.53 | 7801.33 | 15.37 | 11.53 | 5851 | 75% | work in progress
76 | Desiltation / berm cutting/Jungle clearance of Disty No. 8 & 8-A, RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 7.29 | 3999 | 3.95 | 3.75 | 3799.05 | 95% | work in progress
77 | Desiltation / berm cutting/Jungle clearance of Disty No.9 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.71 | 3560.86 | 2.9 | 1.54 | 1887.26 | 53% | work in progress
78 | Desiltation / berm cutting/Jungle clearance of Disty No.10 & 10/A RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11 | 3950.22 | 3.19 | 1.6 | 1975.11 | 50% | yet to be started
79 | Desiltation / berm cutting/Jungle clearance of Disty No. 11 & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 9.1 | 5670.47 | 10.66 | 9.59 | 5103.42 | 90% | work in progress
80 | Desiltation / berm cutting/Jungle clearance of Disty No. 11-A, & its Minor RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.8 | 0.72 | 21.86 | 7695.14 | 5.93 | 4.03 | 5232.7 | 68% | work in progress
81 | Desiltation / berm cutting/Jungle clearance of Disty No. 12 RD. 00-Tail (in reaches) | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 13.23 | 5762.51 | 4.11 | 3.9 | 5474.38 | 95% | work in progress
82 | Desiltation /Jungle Clearance of Disty # 13 & its System RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.675 | 0.6075 | 21.655 | 4256.03 | 4.66 | 4.36 | 4170.9 | 98% | Work is in progress.
83 | Shingling of CPR & Jungle Clearance of Disty # 14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.725 | 0.6525 | 21.616 | 4176.75 | 4.58 | 4.53 | 4134.98 | 99% | Work is in progress.
84 | Shingling of CPR & Jungle Clearance of MD-14 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.433 | 2145.01 | 2.43 | 2.38 | 2102 | 98% | Work is in progress.
85 | Shingling of CPR & Jungle Clearance of Disty # 15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.7 | 0.63 | 21.494 | 3752 | 3.65 | 3.36 | 3452 | 92% | Work is in progress.
86 | Shingling of CPR & Jungle Clearance of MD-15 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.325 | 0.2925 | 5.8384 | 1862.55 | 2.28 | 0.91 | 745 | 40% | Work is in progress.
87 | Shingling of CPR & Jungle Clearance of Disty 16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 12.75 | 3018 | 2.5 | 1 | 1207 | 40% | Work is in progress.
88 | Shingling of CPR & Jungle Clearance of Minor of Disty-16 RD. 00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 5.8445 |  | 2.45 | 0 |  | 0% | Work not yet started.
89 | Desiltation / Jungle Clearance of Disty # 17 RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 9.6951 |  | 2.13 | 0 |  | 0% | Work not yet started.
90 | Shingling of CPR & Jungle Clearance of Disty # 18 its Minors RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.6 | 0.54 | 18.009 |  | 4.26 | 0 |  | 0% | Work not yet started.
91 | Shingling of CPR & Jungle Clearance of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.55 | 0.495 | 15.753 |  | 3.96 | 0 |  | 0% | Work not yet started.
92 | Desiltation / Jungle Clearance of M-1 & M-2 of Disty # 18-A RD.00-Tail in reaches. | CRBC Irrigation Division DIKhan | 0.4 | 0.36 | 11.829 |  | 4 | 0 |  | 0% | Work not yet started.
93 | Removal of Heaps / Clearance of Bari Band Disty RD: 39+500-88+600 in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.33775 | 14.96 | 1435.76 | 8.21 | 8.21 | 1435.76 | 100% | Completed
94 | Removal of Heaps / Clearance of Hero Shah Minor RD: 0 -38+000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 11.58 | 2446.93 | 11.58 | 11.58 | 2446.93 | 100% | Completed
95 | Removal of Heaps / Clearance of Kalu Shah Disty and Dundian Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.1 | 0.098 | 7.69 | 785.8 | 5 | 5 | 785.8 | 100% | Completed
96 | Removal of Heaps / Clearance of Sarwala Disty and Lund Khwar Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 18.29 | 3172.99 | 10.06 | 10.06 | 3172.99 | 100% | Completed
97 | Removal of Heaps / Clearance of Said Abad Disty and Pir Abad Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 20.42 | 3113.1 | 7.31 | 7.31 | 3113.1 | 100% | Completed
98 | Removal of Heaps / Clearance of Katlang Disty from RD: 0-40+000 in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 12.19 | 1910.43 | 7.61 | 7.61 | 1910.43 | 100% | Completed
99 | Removal of Heaps / Clearance of Shamozai Disty/ Syphon and Likpani Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.392 | 17.67 | 2730.62 | 13.01 | 13.01 | 2730.62 | 100% | Completed
100 | Removal of Heaps / Clearance of Dheri Minor and Tail Minor Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.15 | 0.147 | 7.01 | 1211.68 | 6 | 6 | 1211.68 | 100% | Completed
101 | Bazai Main Canal Head Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 10.5 | 10.5 | 1168.075 | 100% | Completed
102 | Wartair Disty | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 6 | 587.93 | 6 | 6 | 587.93 | 100% | Completed
103 | Kharki Disty No. 02 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 3.3 | 1272.34 | 3.3 | 3.3 | 1272.34 | 100% | Completed
104 | Additional Minor No. 03, 06 and Bazai Disty No. 01. | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | 16.8 | 1272.14 | 3 | 3 | 1272.14 | 100% | Completed
105 | Bazai Main Canal, Syphon No. 4431, 5851, 12530, 13590, 14842, 18400, 47527 & 58853 | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | [5 empty] | 70% | Work in Progress
106 | Bazai Disty No. 04, Bazai Minor No. 09, 11 and 12. | Malakand Irrigation Division Malakand | 0.27 | 0.26625 | 15.2 | 4070 | 9 | 9 | 4070 | 100% | Completed
107 | Clearance of Syphon 79205, 93480 and 97962. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | [5 empty] | 20% | Work in Progress
108 | Bazai Disty No. 03 and Bazai Minor No. 05. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | 20.5 | 1907.82 | 7 | 7 | 1907.82 | 100% | Completed
109 | Bazai Main Canal Tail Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 4.78 | 4.78 | 1168.075 | 100% | Completed
110 | KM-1 RD: 0-2976 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 143.26 | 0.9 | 0.9 | 143.26 | 100% | Completed
111 | KM-1 RD: 0-1500, 22000-29000 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 410.62 | 2.6 | 2.6 | 410.62 | 100% | Completed
112 | Bazai Main Canal RD: 79500 to RD: 84500 | Malakand Irrigation Division Malakand | 0.302 | 0.296 | 39 | 649.87 | 1.5 | 1.4 | 606.52 | 93.33% | Work in Progress
113 | Silt & Shingle Clearance of P.C Minor from RD 0+000 To Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.388 | 12.881 | 1851.77 | 7.62 | 6.1 | 1681.41 | 80% | Work in Progress
114 | Clearance of Shingri Minor from RD 0-17250 in reaches. | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.309 | 530.92 | 2.347 | 2.31 | 479.52 | 98.42% | Work in Progress
115 | Clearance of Meherdi Minor from RD 0-31000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 9.451 | 2167.5 | 8.382 | 6.21 | 1605.68 | 74.08% | Work in Progress
116 | Clearance of Kalu Branch from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.33 | 0.3218 | 11.563 | 1318.25 | 5 | 4.6 | 1212.79 | 92% | Work in Progress
117 | Clearance of Hathian Minor from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.05 | 0.04875 | 2.1 | 265.88 | 1.73 | 0.96 | 146.23 | 55.49% | Work in Progress
118 | Clearance of Jalala Disty from RD: 29000 to Tail in reaches | Malakand Irrigation Division Malakand | 0.37 | 0.3607 | 14.024 | 1476.73 | 5900 | 5400 | 1351.5 | 91.52% | Work in Progress
119 | Clearance of Pirsaddo Disty, Ghano Minor and Qutab Gharh Minor from : H-Tail to Tail in reaches. | Malakand Irrigation Division Malakand | 0.35 | 0.341 | 1.88 |  |  | 0 | 0 | 0% | Not yet started
120 | Clearance of Shergarh Minor from Head to Rd:12+000 in reaches. | Malakand Irrigation Division Malakand | 0.15 | 0.146 | 7.752 |  |  | 0 | 0 | 0% | Not yet started
121 | Clearance of Shergarh Minor from Rd:12+000 tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 7.752 | 1195.13 | 6000 | 5500 | 956.83 | 91.66% | Work in Progress
122 | Clearance of Spokanda Disty from RD: 18000 to Tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 5.659 | 1215.5 | 4.97 | 1.52 | 493.17 | 30.58% | Work in Progress
123 | Silt & Shingle Clearance of Spokanda Disty from 0-18000 | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.488 | 771.85 | 2.743 | 1.34 | 378.2 | 48.85% | Work in Progress
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086

## 18-02-2023
S# | Name of Canal | Name of Division | Estimated Cost(RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Total Quantity of Silt to be removed (m3) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Total Quantity of Silt removed till date (m3) | Progress Till date in % | Remarks
1 | Silt clearance/removal of heaps of Disty No. 9 RD; 41000 to 85500 | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 13.41 | 599.93 | 1 | 1 | 599.93 | 100% | Completed
2 | Silt clearance of Power House Minor RD 0 to tail | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 1.28 | 599.9 | 1.28 | 1.28 | 599.9 | 100% | Completed
3 | Silt clearance of conduit covering portion of 2/9 Hoti Minor RD 4200 to 5000, 5800 to 7000 & 7200 to 7500 | Mardan Irrigation Division Mardan | 0.7 | 0.4546 | 0.7 | 745.53 | 0.7 | 0.7 | 745.53 | 100% | Completed
4 | Silt clearance of 2/9 Hoti Minor RD 0 to 4200, 5000 to 5800 & 7500 to 19000 | Mardan Irrigation Division Mardan | 0.8 | 0.5195 | 5.94 | 921.08 | 2.43 | 2.43 | 921.08 | 100% | Completed
5 | Silt clearance /removal of heaps of kalpani disty RD 0-51000 in reaches and clearance of syphones RD 10500 and 15000 | Mardan Irrigation Division Mardan | 0.7 | 0.4544 | 15.6 | 4463.54 | 5.07 | 5.07 | 4463.54 | 100% | Completed
6 | Silt clearance /removal of heaps of 1/kalpani Kodinaka Minor RD 0-27000 in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 8.22 | 599.94 | 1.82 | 1.82 | 599.94 | 100% | Completed
7 | Silt clearance /removal of heaps of 2/kalpani Taus Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 6.4 | 2801.12 | 5.5 | 5.5 | 2801.12 | 100% | Completed
8 | Silt clearance of 3/9 Toru Minor RD 0 to 15800 | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 4.81 | 2801.12 | 4.81 | 4.81 | 2801.12 | 100% | Completed
9 | Silt clearance of branch 2/kalpani Muhib Banda Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.175 | 0.1308 | 2.89 | 1633.98 | 2 | 2 | 1633.98 | 100% | Completed
10 | Silt Clearance of Maho Dheri Minor RD: 4000 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.1493 | 4.57 | 1138.2 | 3.35 | 3.35 | 1138.2 | 100% | Completed
11 | Silt Clearance of Rashakai Minor from RD: 7000 to 31000 in reaches | Mardan Irrigation Division Mardan | 0.6 | 0.3894 | 9.45 | 2972.29 | 7.31 | 7.31 | 2972.29 | 100% | Completed
12 | Silt Clearance of Nowshera Minor RD:0 - tail in reachers | Mardan Irrigation Division Mardan | 0.35 | 0.2613 | 5.18 | 2059.85 | 3.2 | 3.2 | 2059.85 | 100% | Completed
13 | Silt Clearance of Turlandi Minor Head to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 5.27 | 2134.4 | 4.71 | 4.71 | 2134.4 | 100% | Completed
14 | Silt Clearance of Khan Mahi Branch from RD: 0 to 3000 and RD: 8000 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 13.41 | 2344.08 | 5.48 | 5.48 | 2344.08 | 100% | Completed
15 | Silt Clearance of Bara Banda Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 3.04 | 1703.02 | 3.04 | 3.04 | 1703.02 | 100% | Completed
16 | Removal of heaps of Disty No. 8 RD: 52000 to 68000 in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 9.45 | 1860.72 | 1.43 | 1.43 | 1860.72 | 100% | Completed
17 | Silt Clearance/removal of heaps of Disty No. 7 at RD: 4000 to 14000 in reaches | Mardan Irrigation Division Mardan | 0.15 | 0.1133 | 4.26 | 1400.56 | 3.04 | 3.04 | 1400.56 | 100% | Completed
18 | Silt Clearance/removal of heaps of Sheikh yousaf Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 5.48 | 239.97 | 2.13 | 2.13 | 239.97 | 100% | Completed
19 | Silt Clearance/removal of heaps of 1/9 Guide Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 7 | 479.94 | 2.74 | 2.74 | 479.94 | 100% | Completed
20 | Silt Clearance/removal of heaps of Koragh Branch RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 14.93 | 479.94 | 2.23 | 2.23 | 479.94 | 100% | Completed
21 | Removal of heaps of Disty No.8 RD: 0 to 38000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 11.58 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
22 | Removal of heaps of Disty No.9 RD: 0 to 41000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 12.5 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
23 | Jue Shiekh Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 16.29 | 13.03 | 53.35 | 132353 | 53.35 | 53.35 | 132353 | 100% | Completed
24 | Jue Zardad Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 3.6 | 2.88 | 13.1 | 18500 | 13.1 | 13.1 | 18500 | 100% | Completed
25 | Kabul River Canal | Peshawar Canal Division, Peshawar (Kabaul River Canal Sub Division) | 27.855 | 22.284 | 60.35 | 1062085 | 60.35 | 55.2 | 971500 | 91% | Work is in progress
26 | Hazar Khwani Branch | Peshawar Canal Division, Peshawar (Kabul River Canal Sub Division) | 23.2 | 18.56 | 28.04 | 1016303 | 28.04 | 25.3 | 916992 | 90% | Work is in progress
27 | Silt Clearance of Lower Siran Canal RD 0-14000 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3110.16 | 3.04 | 2.98 | 3058.58 | 98% | In progress
28 | Silt Clearance of Lower Siran Canal RD 14000-36500 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3142.51 | 4.26 | 4.01 | 3059.03 | 97% | In progress
29 | Silt Clearance of Lower Siran Canal Hathi Maira Branch & Gandian Minor RD 36500 in reaches | Mansehra Irrigation Division Mansehra | 0.55 | 0.4954 | 26.21 | 2080.06 | 12.1 | 11.69 | 2039.32 | 98% | In progress
30 | Silt Clearance of Ichar Canal/ Kalghan Minor RD 0-tail in reaches | Mansehra Irrigation Division Mansehra | 0.25 | 0.2254 | 5.97 | 1197.78 | 5.66 | 4.58 | 1042.05 | 87% | In progress
31 | Silt Clearance of Upper Siran Canal from RD 0-30000 In reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2065 | 3.048 | 2.88 | 1578.42 | 76% | In progress
32 | Silt Clearance of Upper Siran Canal from RD 30000-61000 in reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2110 | 9.44 | 9.44 | 2110 | 100% | Completed
33 | Silt Clearance of Upper Siran Canal from RD 61000-tail in reaches | Mansehra Irrigation Division Mansehra | 0.18 | 0.1623 | 23.86 | 930 | 5.27 | 4.96 | 871.72 | 94% | In progress
34 | Silt Clearance of Dhodial Minor Upper Siran Canal in reaches | Mansehra Irrigation Division Mansehra | 0.22 | 0.1981 | 5.24 | 1135 | 5.24 | 4.97 | 1117.78 | 98% | In progress
35 | Removal of Heaps / Clearance of Bari Band Disty RD: 39+500-88+600 in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.33775 | 14.96 | 1435.76 | 8.21 | 8.21 | 1435.76 | 100% | Completed
36 | Removal of Heaps / Clearance of Hero Shah Minor RD: 0 -38+000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 11.58 | 2446.93 | 11.58 | 11.58 | 2446.93 | 100% | Completed
37 | Removal of Heaps / Clearance of Kalu Shah Disty and Dundian Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.1 | 0.098 | 7.69 | 785.8 | 5 | 5 | 785.8 | 100% | Completed
38 | Removal of Heaps / Clearance of Sarwala Disty and Lund Khwar Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 18.29 | 3172.99 | 10.06 | 10.06 | 3172.99 | 100% | Completed
39 | Removal of Heaps / Clearance of Said Abad Disty and Pir Abad Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 20.42 | 3113.1 | 7.31 | 7.31 | 3113.1 | 100% | Completed
40 | Removal of Heaps / Clearance of Katlang Disty from RD: 0-40+000 in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 12.19 | 1910.43 | 7.61 | 7.61 | 1910.43 | 100% | Completed
41 | Removal of Heaps / Clearance of Shamozai Disty/ Syphon and Likpani Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.392 | 17.67 | 2730.62 | 13.01 | 13.01 | 2730.62 | 100% | Completed
42 | Removal of Heaps / Clearance of Dheri Minor and Tail Minor Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.15 | 0.147 | 7.01 | 1211.68 | 6 | 6 | 1211.68 | 100% | Completed
43 | Bazai Main Canal Head Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 10.5 | 10.5 | 1168.075 | 100% | Completed
44 | Wartair Disty | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 6 | 587.93 | 6 | 6 | 587.93 | 100% | Completed
45 | Kharki Disty No. 02 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 3.3 | 1272.34 | 3.3 | 3.3 | 1272.34 | 100% | Completed
46 | Additional Minor No. 03, 06 and Bazai Disty No. 01. | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | 16.8 | 1272.14 | 3 | 3 | 1272.14 | 100% | Completed
47 | Bazai Main Canal, Syphon No. 4431, 5851, 12530, 13590, 14842, 18400, 47527 & 58853 | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | [5 empty] | 70% | Work in Progress
48 | Bazai Disty No. 04, Bazai Minor No. 09, 11 and 12. | Malakand Irrigation Division Malakand | 0.27 | 0.26625 | 15.2 | 4070 | 9 | 9 | 4070 | 100% | Completed
49 | Clearance of Syphon 79205, 93480 and 97962. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | [5 empty] | 20% | Work in Progress
50 | Bazai Disty No. 03 and Bazai Minor No. 05. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | 20.5 | 1907.82 | 7 | 7 | 1907.82 | 100% | Completed
51 | Bazai Main Canal Tail Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 4.78 | 4.78 | 1168.075 | 100% | Completed
52 | KM-1 RD: 0-2976 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 143.26 | 0.9 | 0.9 | 143.26 | 100% | Completed
53 | KM-1 RD: 0-1500, 22000-29000 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 410.62 | 2.6 | 2.6 | 410.62 | 100% | Completed
54 | Bazai Main Canal RD: 79500 to RD: 84500 | Malakand Irrigation Division Malakand | 0.302 | 0.296 | 39 | 649.87 | 1.5 | 1.4 | 606.52 | 93.33% | Work in Progress
55 | Silt & Shingle Clearance of P.C Minor from RD 0+000 To Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.388 | 12.881 | 1851.77 | 7.62 | 7.62 | 1851.77 | 100% | Completed
56 | Clearance of Shingri Minor from RD 0-17250 in reaches. | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.309 | 530.92 | 2.347 | 2.347 | 530.92 | 100% | Completed
57 | Clearance of Meherdi Minor from RD 0-31000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 9.451 | 2167.5 | 8.382 | 8.382 | 2167.5 | 100% | Completed
58 | Clearance of Kalu Branch from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.33 | 0.3218 | 11.563 | 1318.25 | 5 | 4.6 | 1212.79 | 92% | Work in Progress
59 | Clearance of Hathian Minor from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.05 | 0.04875 | 2.1 | 265.88 | 1.73 | 0.96 | 146.23 | 55.49% | Work in Progress
60 | Clearance of Jalala Disty from RD: 29000 to Tail in reaches | Malakand Irrigation Division Malakand | 0.37 | 0.3607 | 14.024 | 1476.73 | 5900 | 5400 | 1351.5 | 91.52% | Work in Progress
61 | Clearance of Pirsaddo Disty, Ghano Minor and Qutab Gharh Minor from : H-Tail to Tail in reaches. | Malakand Irrigation Division Malakand | 0.35 | 0.341 | 1.88 |  |  | 0 | 0 | 0% | Not yet started
62 | Clearance of Shergarh Minor from Head to Rd:12+000 in reaches. | Malakand Irrigation Division Malakand | 0.15 | 0.146 | 7.752 |  |  | 0 | 0 | 0% | Not yet started
63 | Clearance of Shergarh Minor from Rd:12+000 tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 7.752 | 1195.13 | 6000 | 5500 | 956.83 | 91.66% | Work in Progress
64 | Clearance of Spokanda Disty from RD: 18000 to Tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 5.659 | 1215.5 | 4.97 | 1.52 | 493.17 | 30.58% | Work in Progress
65 | Silt & Shingle Clearance of Spokanda Disty from 0-18000 | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.488 | 771.85 | 2.743 | 2 | 563.45 | 72.91% | Work in Progress
66 | Shamizai Irrigation Canal | Swat Irrigation Division-II Matta | 1 | 0.779 | 20.73 | 5150 | 19.5 | 19.5 | 5150 | 100% | Completed
67 | Barwai Irrigation Canal | Swat Irrigation Division-II Matta | 0.3 | 0.2805 | 11.22 | 1300 | 6.1 | 6.1 | 1300 | 100% | Completed
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086

## 19-02-2023
S# | Name of Canal | Name of Division | Estimated Cost(RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Total Quantity of Silt to be removed (m3) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Total Quantity of Silt removed till date (m3) | Progress Till date in % | Remarks
1 | Silt clearance/removal of heaps of Disty No. 9 RD; 41000 to 85500 | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 13.41 | 599.93 | 1 | 1 | 599.93 | 100% | Completed
2 | Silt clearance of Power House Minor RD 0 to tail | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 1.28 | 599.9 | 1.28 | 1.28 | 599.9 | 100% | Completed
3 | Silt clearance of conduit covering portion of 2/9 Hoti Minor RD 4200 to 5000, 5800 to 7000 & 7200 to 7500 | Mardan Irrigation Division Mardan | 0.7 | 0.4546 | 0.7 | 745.53 | 0.7 | 0.7 | 745.53 | 100% | Completed
4 | Silt clearance of 2/9 Hoti Minor RD 0 to 4200, 5000 to 5800 & 7500 to 19000 | Mardan Irrigation Division Mardan | 0.8 | 0.5195 | 5.94 | 921.08 | 2.43 | 2.43 | 921.08 | 100% | Completed
5 | Silt clearance /removal of heaps of kalpani disty RD 0-51000 in reaches and clearance of syphones RD 10500 and 15000 | Mardan Irrigation Division Mardan | 0.7 | 0.4544 | 15.6 | 4463.54 | 5.07 | 5.07 | 4463.54 | 100% | Completed
6 | Silt clearance /removal of heaps of 1/kalpani Kodinaka Minor RD 0-27000 in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 8.22 | 599.94 | 1.82 | 1.82 | 599.94 | 100% | Completed
7 | Silt clearance /removal of heaps of 2/kalpani Taus Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 6.4 | 2801.12 | 5.5 | 5.5 | 2801.12 | 100% | Completed
8 | Silt clearance of 3/9 Toru Minor RD 0 to 15800 | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 4.81 | 2801.12 | 4.81 | 4.81 | 2801.12 | 100% | Completed
9 | Silt clearance of branch 2/kalpani Muhib Banda Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.175 | 0.1308 | 2.89 | 1633.98 | 2 | 2 | 1633.98 | 100% | Completed
10 | Silt Clearance of Maho Dheri Minor RD: 4000 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.1493 | 4.57 | 1138.2 | 3.35 | 3.35 | 1138.2 | 100% | Completed
11 | Silt Clearance of Rashakai Minor from RD: 7000 to 31000 in reaches | Mardan Irrigation Division Mardan | 0.6 | 0.3894 | 9.45 | 2972.29 | 7.31 | 7.31 | 2972.29 | 100% | Completed
12 | Silt Clearance of Nowshera Minor RD:0 - tail in reachers | Mardan Irrigation Division Mardan | 0.35 | 0.2613 | 5.18 | 2059.85 | 3.2 | 3.2 | 2059.85 | 100% | Completed
13 | Silt Clearance of Turlandi Minor Head to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 5.27 | 2134.4 | 4.71 | 4.71 | 2134.4 | 100% | Completed
14 | Silt Clearance of Khan Mahi Branch from RD: 0 to 3000 and RD: 8000 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 13.41 | 2344.08 | 5.48 | 5.48 | 2344.08 | 100% | Completed
15 | Silt Clearance of Bara Banda Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 3.04 | 1703.02 | 3.04 | 3.04 | 1703.02 | 100% | Completed
16 | Removal of heaps of Disty No. 8 RD: 52000 to 68000 in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 9.45 | 1860.72 | 1.43 | 1.43 | 1860.72 | 100% | Completed
17 | Silt Clearance/removal of heaps of Disty No. 7 at RD: 4000 to 14000 in reaches | Mardan Irrigation Division Mardan | 0.15 | 0.1133 | 4.26 | 1400.56 | 3.04 | 3.04 | 1400.56 | 100% | Completed
18 | Silt Clearance/removal of heaps of Sheikh yousaf Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 5.48 | 239.97 | 2.13 | 2.13 | 239.97 | 100% | Completed
19 | Silt Clearance/removal of heaps of 1/9 Guide Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 7 | 479.94 | 2.74 | 2.74 | 479.94 | 100% | Completed
20 | Silt Clearance/removal of heaps of Koragh Branch RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 14.93 | 479.94 | 2.23 | 2.23 | 479.94 | 100% | Completed
21 | Removal of heaps of Disty No.8 RD: 0 to 38000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 11.58 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
22 | Removal of heaps of Disty No.9 RD: 0 to 41000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 12.5 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
23 | Shamizai Irrigation Canal | Swat Irrigation Division-II Matta | 1 | 0.779 | 20.73 | 5150 | 19.5 | 19.5 | 5150 | 100% | Completed
24 | Barwai Irrigation Canal | Swat Irrigation Division-II Matta | 0.3 | 0.2805 | 11.22 | 1300 | 6.1 | 6.1 | 1300 | 100% | Completed
25 | Jue Shiekh Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 16.29 | 13.03 | 53.35 | 132353 | 53.35 | 53.35 | 132353 | 100% | Completed
26 | Jue Zardad Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 3.6 | 2.88 | 13.1 | 18500 | 13.1 | 13.1 | 18500 | 100% | Completed
27 | Kabul River Canal | Peshawar Canal Division, Peshawar (Kabaul River Canal Sub Division) | 27.855 | 22.284 | 60.35 | 1062085 | 60.35 | 58 | 1020779 | 96% | Work is in progress
28 | Hazar Khwani Branch | Peshawar Canal Division, Peshawar (Kabul River Canal Sub Division) | 23.2 | 18.56 | 28.04 | 1016303 | 28.04 | 25.3 | 916992 | 90% | Work is in progress
29 | Removal of Heaps / Clearance of Bari Band Disty RD: 39+500-88+600 in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.33775 | 14.96 | 1435.76 | 8.21 | 8.21 | 1435.76 | 100% | Completed
30 | Removal of Heaps / Clearance of Hero Shah Minor RD: 0 -38+000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 11.58 | 2446.93 | 11.58 | 11.58 | 2446.93 | 100% | Completed
31 | Removal of Heaps / Clearance of Kalu Shah Disty and Dundian Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.1 | 0.098 | 7.69 | 785.8 | 5 | 5 | 785.8 | 100% | Completed
32 | Removal of Heaps / Clearance of Sarwala Disty and Lund Khwar Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 18.29 | 3172.99 | 10.06 | 10.06 | 3172.99 | 100% | Completed
33 | Removal of Heaps / Clearance of Said Abad Disty and Pir Abad Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 20.42 | 3113.1 | 7.31 | 7.31 | 3113.1 | 100% | Completed
34 | Removal of Heaps / Clearance of Katlang Disty from RD: 0-40+000 in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 12.19 | 1910.43 | 7.61 | 7.61 | 1910.43 | 100% | Completed
35 | Removal of Heaps / Clearance of Shamozai Disty/ Syphon and Likpani Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.392 | 17.67 | 2730.62 | 13.01 | 13.01 | 2730.62 | 100% | Completed
36 | Removal of Heaps / Clearance of Dheri Minor and Tail Minor Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.15 | 0.147 | 7.01 | 1211.68 | 6 | 6 | 1211.68 | 100% | Completed
37 | Bazai Main Canal Head Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 10.5 | 10.5 | 1168.075 | 100% | Completed
38 | Wartair Disty | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 6 | 587.93 | 6 | 6 | 587.93 | 100% | Completed
39 | Kharki Disty No. 02 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 3.3 | 1272.34 | 3.3 | 3.3 | 1272.34 | 100% | Completed
40 | Additional Minor No. 03, 06 and Bazai Disty No. 01. | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | 16.8 | 1272.14 | 3 | 3 | 1272.14 | 100% | Completed
41 | Bazai Main Canal, Syphon No. 4431, 5851, 12530, 13590, 14842, 18400, 47527 & 58853 | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | [5 empty] | 70% | Work in Progress
42 | Bazai Disty No. 04, Bazai Minor No. 09, 11 and 12. | Malakand Irrigation Division Malakand | 0.27 | 0.26625 | 15.2 | 4070 | 9 | 9 | 4070 | 100% | Completed
43 | Clearance of Syphon 79205, 93480 and 97962. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | [5 empty] | 20% | Work in Progress
44 | Bazai Disty No. 03 and Bazai Minor No. 05. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | 20.5 | 1907.82 | 7 | 7 | 1907.82 | 100% | Completed
45 | Bazai Main Canal Tail Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 4.78 | 4.78 | 1168.075 | 100% | Completed
46 | KM-1 RD: 0-2976 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 143.26 | 0.9 | 0.9 | 143.26 | 100% | Completed
47 | KM-1 RD: 0-1500, 22000-29000 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 410.62 | 2.6 | 2.6 | 410.62 | 100% | Completed
48 | Bazai Main Canal RD: 79500 to RD: 84500 | Malakand Irrigation Division Malakand | 0.302 | 0.296 | 39 | 649.87 | 1.5 | 1.4 | 606.52 | 93.33% | Work in Progress
49 | Silt & Shingle Clearance of P.C Minor from RD 0+000 To Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.388 | 12.881 | 1851.77 | 7.62 | 7.62 | 1851.77 | 100% | Completed
50 | Clearance of Shingri Minor from RD 0-17250 in reaches. | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.309 | 530.92 | 2.347 | 2.347 | 530.92 | 100% | Completed
51 | Clearance of Meherdi Minor from RD 0-31000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 9.451 | 2167.5 | 8.382 | 8.382 | 2167.5 | 100% | Completed
52 | Clearance of Kalu Branch from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.33 | 0.3218 | 11.563 | 1318.25 | 5 | 4.6 | 1212.79 | 92% | Work in Progress
53 | Clearance of Hathian Minor from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.05 | 0.04875 | 2.1 | 265.88 | 1.73 | 0.96 | 146.23 | 55.49% | Work in Progress
54 | Clearance of Jalala Disty from RD: 29000 to Tail in reaches | Malakand Irrigation Division Malakand | 0.37 | 0.3607 | 14.024 | 1476.73 | 5900 | 5400 | 1351.5 | 91.52% | Work in Progress
55 | Clearance of Pirsaddo Disty, Ghano Minor and Qutab Gharh Minor from : H-Tail to Tail in reaches. | Malakand Irrigation Division Malakand | 0.35 | 0.341 | 1.88 |  |  | 0 | 0 | 0% | Not yet started
56 | Clearance of Shergarh Minor from Head to Rd:12+000 in reaches. | Malakand Irrigation Division Malakand | 0.15 | 0.146 | 7.752 |  |  | 0 | 0 | 0% | Not yet started
57 | Clearance of Shergarh Minor from Rd:12+000 tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 7.752 | 1195.13 | 6000 | 5500 | 956.83 | 91.66% | Work in Progress
58 | Clearance of Spokanda Disty from RD: 18000 to Tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 5.659 | 1215.5 | 4.97 | 1.52 | 493.17 | 30.58% | Work in Progress
59 | Silt & Shingle Clearance of Spokanda Disty from 0-18000 | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.488 | 771.85 | 2.743 | 2 | 563.45 | 72.91% | Work in Progress
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086

## 20-02-2023
S# | Name of Canal | Name of Division | Estimated Cost(RS. M) | BID Cost (Rs. M) | Total Length of Canal (Km) | Total Quantity of Silt to be removed (m3) | Length of canal to be Desilted (Km) | Length Desilted till date(Km) | Total Quantity of Silt removed till date (m3) | Progress Till date in % | Remarks
1 | Shamizai Irrigation Canal | Swat Irrigation Division-II Matta | 1 | 0.779 | 20.73 | 5150 | 19.5 | 19.5 | 5150 | 100% | Completed
2 | Barwai Irrigation Canal | Swat Irrigation Division-II Matta | 0.3 | 0.2805 | 11.22 | 1300 | 6.1 | 6.1 | 1300 | 100% | Completed
3 | Silt clearance/removal of heaps of Disty No. 9 RD; 41000 to 85500 | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 13.41 | 599.93 | 1 | 1 | 599.93 | 100% | Completed
4 | Silt clearance of Power House Minor RD 0 to tail | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 1.28 | 599.9 | 1.28 | 1.28 | 599.9 | 100% | Completed
5 | Silt clearance of conduit covering portion of 2/9 Hoti Minor RD 4200 to 5000, 5800 to 7000 & 7200 to 7500 | Mardan Irrigation Division Mardan | 0.7 | 0.4546 | 0.7 | 745.53 | 0.7 | 0.7 | 745.53 | 100% | Completed
6 | Silt clearance of 2/9 Hoti Minor RD 0 to 4200, 5000 to 5800 & 7500 to 19000 | Mardan Irrigation Division Mardan | 0.8 | 0.5195 | 5.94 | 921.08 | 2.43 | 2.43 | 921.08 | 100% | Completed
7 | Silt clearance /removal of heaps of kalpani disty RD 0-51000 in reaches and clearance of syphones RD 10500 and 15000 | Mardan Irrigation Division Mardan | 0.7 | 0.4544 | 15.6 | 4463.54 | 5.07 | 5.07 | 4463.54 | 100% | Completed
8 | Silt clearance /removal of heaps of 1/kalpani Kodinaka Minor RD 0-27000 in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 8.22 | 599.94 | 1.82 | 1.82 | 599.94 | 100% | Completed
9 | Silt clearance /removal of heaps of 2/kalpani Taus Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 6.4 | 2801.12 | 5.5 | 5.5 | 2801.12 | 100% | Completed
10 | Silt clearance of 3/9 Toru Minor RD 0 to 15800 | Mardan Irrigation Division Mardan | 0.3 | 0.2242 | 4.81 | 2801.12 | 4.81 | 4.81 | 2801.12 | 100% | Completed
11 | Silt clearance of branch 2/kalpani Muhib Banda Minor RD 0-tail in reaches | Mardan Irrigation Division Mardan | 0.175 | 0.1308 | 2.89 | 1633.98 | 2 | 2 | 1633.98 | 100% | Completed
12 | Silt Clearance of Maho Dheri Minor RD: 4000 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.1493 | 4.57 | 1138.2 | 3.35 | 3.35 | 1138.2 | 100% | Completed
13 | Silt Clearance of Rashakai Minor from RD: 7000 to 31000 in reaches | Mardan Irrigation Division Mardan | 0.6 | 0.3894 | 9.45 | 2972.29 | 7.31 | 7.31 | 2972.29 | 100% | Completed
14 | Silt Clearance of Nowshera Minor RD:0 - tail in reachers | Mardan Irrigation Division Mardan | 0.35 | 0.2613 | 5.18 | 2059.85 | 3.2 | 3.2 | 2059.85 | 100% | Completed
15 | Silt Clearance of Turlandi Minor Head to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 5.27 | 2134.4 | 4.71 | 4.71 | 2134.4 | 100% | Completed
16 | Silt Clearance of Khan Mahi Branch from RD: 0 to 3000 and RD: 8000 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 13.41 | 2344.08 | 5.48 | 5.48 | 2344.08 | 100% | Completed
17 | Silt Clearance of Bara Banda Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.5 | 0.3245 | 3.04 | 1703.02 | 3.04 | 3.04 | 1703.02 | 100% | Completed
18 | Removal of heaps of Disty No. 8 RD: 52000 to 68000 in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.2986 | 9.45 | 1860.72 | 1.43 | 1.43 | 1860.72 | 100% | Completed
19 | Silt Clearance/removal of heaps of Disty No. 7 at RD: 4000 to 14000 in reaches | Mardan Irrigation Division Mardan | 0.15 | 0.1133 | 4.26 | 1400.56 | 3.04 | 3.04 | 1400.56 | 100% | Completed
20 | Silt Clearance/removal of heaps of Sheikh yousaf Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 5.48 | 239.97 | 2.13 | 2.13 | 239.97 | 100% | Completed
21 | Silt Clearance/removal of heaps of 1/9 Guide Minor RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 7 | 479.94 | 2.74 | 2.74 | 479.94 | 100% | Completed
22 | Silt Clearance/removal of heaps of Koragh Branch RD: 0 to tail in reaches | Mardan Irrigation Division Mardan | 0.4 | 0.302 | 14.93 | 479.94 | 2.23 | 2.23 | 479.94 | 100% | Completed
23 | Removal of heaps of Disty No.8 RD: 0 to 38000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 11.58 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
24 | Removal of heaps of Disty No.9 RD: 0 to 41000 in reaches | Mardan Irrigation Division Mardan | 0.2 | 0.151 | 12.5 | 239.97 | 1 | 1 | 239.97 | 100% | Completed
25 | Silt Clearance of Badwan Kharif Irrigation Scheme at RD 0+00 To Tail. | Chakdara Irrigation Sub Division ,Dir Division | 0.9 | 0.8957 | 22.18 | 4635.35 | 22.18 | 16.15 | 3587.13 | 77.18% | Work is in progress (Today Desiltation is Stope Due To Rain)
26 | Jue Shiekh Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 16.29 | 13.03 | 53.35 | 132353 | 53.35 | 53.35 | 132353 | 100% | Completed
27 | Jue Zardad Canal | Peshawar Canal Division, Peshawar (Civil Canals Sub Division) | 3.6 | 2.88 | 13.1 | 18500 | 13.1 | 13.1 | 18500 | 100% | Completed
28 | Kabul River Canal | Peshawar Canal Division, Peshawar (Kabaul River Canal Sub Division) | 27.855 | 22.284 | 60.35 | 1062085 | 60.35 | 59 | 1038378 | 98% | Work is in progress
29 | Hazar Khwani Branch | Peshawar Canal Division, Peshawar (Kabul River Canal Sub Division) | 23.2 | 18.56 | 28.04 | 1016303 | 28.04 | 25.5 | 924241 | 91% | Work is in progress
30 | Silt Clearance of Lower Siran Canal RD 0-14000 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3110.16 | 3.04 | 2.98 | 3058.58 | 98% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
31 | Silt Clearance of Lower Siran Canal RD 14000-36500 in reaches | Mansehra Irrigation Division Mansehra | 0.6 | 0.5403 | 26.21 | 3142.51 | 4.26 | 4.01 | 3059.03 | 97% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
32 | Silt Clearance of Lower Siran Canal Hathi Maira Branch & Gandian Minor RD 36500 in reaches | Mansehra Irrigation Division Mansehra | 0.55 | 0.4954 | 26.21 | 2080.06 | 12.1 | 11.69 | 2039.32 | 98% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
33 | Silt Clearance of Ichar Canal/ Kalghan Minor RD 0-tail in reaches | Mansehra Irrigation Division Mansehra | 0.25 | 0.2254 | 5.97 | 1197.78 | 5.66 | 4.58 | 1042.05 | 87% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
34 | Silt Clearance of Upper Siran Canal from RD 0-30000 In reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2065 | 3.048 | 2.88 | 1578.42 | 76% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
35 | Silt Clearance of Upper Siran Canal from RD 30000-61000 in reaches | Mansehra Irrigation Division Mansehra | 0.4 | 0.3603 | 23.86 | 2110 | 9.44 | 9.44 | 2110 | 100% | Completed
36 | Silt Clearance of Upper Siran Canal from RD 61000-tail in reaches | Mansehra Irrigation Division Mansehra | 0.18 | 0.1623 | 23.86 | 930 | 5.27 | 4.96 | 871.72 | 94% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
37 | Silt Clearance of Dhodial Minor Upper Siran Canal in reaches | Mansehra Irrigation Division Mansehra | 0.22 | 0.1981 | 5.24 | 1135 | 5.24 | 4.97 | 1117.78 | 98% | Work is in progress (Due to rain falls De-siltation has not been executed at site today)
38 | Nipki Khel Irrigation Scheme | Swat Irrigation Division -I | 2.2 | 1.76 | 38.87 | 10172.62 | 38.87 | 30.1829 | 7920 | 77.65% | Work is in progress
39 | Silt Clearance of Disty No.6 from RD: 55+000 to 60+000 in reaches. | Charsadda Irrigation Sub Division Charsadda | 0.183 | 0.155 | 22.25 | 538.02 | 0.61 | 0.61 | 538.02 | 100% | Completed
40 | Silt Clearance of Disty No.6 from RD: 60+000 to 65+000 in reaches. | -do- | 0.157 | 0.133 | 22.25 | 460.15 | 0.45 | 0.45 | 460.15 | 100% | Completed
41 | Silt Clearance of Disty No.6 from RD: 65+000 to 73+000 in reaches. | -do- | 0.2 | 0.169 | 22.25 | 587.58 | 0.61 | 0.61 | 587.58 | 100% | Completed
42 | Silt Clearance of Nisatta Branch from RD: 0+000 to Tail in reaches. | -do- | 0.336 | 0.284 | 11.88 | 991.1 | 1 | 1 | 991.1 | 100% | Completed
43 | Silt Clearance of Nisatta Minor from RD: 0+000 to Tail in reaches. | -do- | 0.218 | 0.184 | 3.35 | 877.83 | 2 | 2 | 877.83 | 100% | Completed
44 | Silt Clearance of Palosa Minor from RD: 0+000 to Tail in reaches. | -do- | 0.253 | 0.214 | 5.03 | 748.98 | 1.35 | 1.35 | 748.98 | 100% | Completed
45 | Silt Clearance of Zardad and Kheshki Branch in reaches. | -do- | 0.348 | 0.294 | 14.49 | 1880.25 | 7 | 7 | 1880.25 | 100% | Completed
46 | Silt clearance of Sarai Saleh NPC Rd 0-10000 in reaches | Haripur Irrigation Division Haripur | 0.35 | 0.283 | 15.85 | 1271 | 3.04 | 3.04 | 1271 | 100% | Work completed
47 | Silt clearance of Sarai Saleh NPC Rd 10000-17000 i/c Minor No.1 in reaches | Haripur Irrigation Division Haripur | 0.3 | 0.24 | 15.85 | 1131.96 | 2.13 | 2.13 | 1131.96 | 100% | Work completed
48 | Silt clearance of Sarai Saleh NPC Rd 17000-30000 i/c Minor No.2 in reaches | Haripur Irrigation Division Haripur | 0.35 | 0.28 | 15.85 | 1347 | 3.96 | 3.56 | 1298.99 | 95% | Work is in progress
49 | Clearance of Daur Main Canal Rd 0-tail | Haripur Irrigation Division Haripur | 0.15 | 0.1216 | 0.838 | 555.2 | 0.838 | 0.838 | 555.2 | 100% | Work completed
50 | Silt Clearance of Disty No.02 RD 0-20000 in reaches. | Haripur Irrigation Division Haripur | 0.25 | 0.2 | 6.62 | 1287.6 | 6.09 | 6.09 | 1287.6 | 100% | work completed
51 | Silt Clearance of Main KRBC RD 11000-42000 in reaches | Haripur Irrigation Division Haripur | 0.25 | 0.225 | 12.8 | 1287.6 | 9.45 | 9.45 | 1287.6 | 100% | Work completed
52 | Silt Clearance Disty No.04 RD 0-24000 in reaches. | Haripur Irrigation Division Haripur | 0.3 | 0.24 | 7.31 | 1545.12 | 7.31 | 7.31 | 1545.12 | 100% | work completed
53 | Silt Clearance of Disty No.03 i/c Ziarat Minor and Bandi Minor in reaches. | Haripur Irrigation Division Haripur | 0.3 | 0.24 | 10.67 | 1545.12 | 10.67 | 10.67 | 1545.12 | 100% | Work completed
54 | Silt Clearance of Disty No.1 i/c Balartop & Kamalpur Minors in reaches. | haripur Irrigation Division Haripur | 0.3 | 0.24 | 10.36 | 1545.12 | 10.36 | 10.36 | 1545.12 | 100% | work completed
55 | Silt Clearance of KLBC Rd 0-26000 in reaches | haripur Irrigation Division Haripur | 0.3 | 0.24 | 7.92 | 1545.12 | 7.92 | 989 | 5.21 | 75% | work in progress
56 | Silt clearance of Sarai Saleh NPC Rd 30000-40000 i/c Minor No. 3 in reaches | HAripur Irrigation Division Haripur | 0.25 | 0.2 | 15.85 | 946 | 3.04 | 2.56 | 723.87 | 75% | Work is in progress
57 | Clearance of Main Rangila Irrigation system i/c Rangila Tank | Haripur Irrigation Division Haripur | 0.2 | 0.173 | 2.21 | 559 | 2.21 | 2.21 | 559 | 100% | work completed
58 | Silt Clearance of Chak Muneem Minor. | Haripur Irrigation Division Haripur | 0.2 | 0.16 | 7.01 | 1030.8 | 7.01 | 7.01 | 1030.8 | 100% | work completed
59 | Silt clearance of Kharabara Dam Channel | Haripur Irrigation Division Haripur | 0.1 | 0.08 | 2.8 | 515.1 | 2.8 | 2.8 | 515.1 | 100% | work completed
60 | Removal of Heaps / Clearance of Bari Band Disty RD: 39+500-88+600 in reaches | Malakand Irrigation Division Malakand | 0.35 | 0.33775 | 14.96 | 1435.76 | 8.21 | 8.21 | 1435.76 | 100% | Completed
61 | Removal of Heaps / Clearance of Hero Shah Minor RD: 0 -38+000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 11.58 | 2446.93 | 11.58 | 11.58 | 2446.93 | 100% | Completed
62 | Removal of Heaps / Clearance of Kalu Shah Disty and Dundian Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.1 | 0.098 | 7.69 | 785.8 | 5 | 5 | 785.8 | 100% | Completed
63 | Removal of Heaps / Clearance of Sarwala Disty and Lund Khwar Disty from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 18.29 | 3172.99 | 10.06 | 10.06 | 3172.99 | 100% | Completed
64 | Removal of Heaps / Clearance of Said Abad Disty and Pir Abad Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 20.42 | 3113.1 | 7.31 | 7.31 | 3113.1 | 100% | Completed
65 | Removal of Heaps / Clearance of Katlang Disty from RD: 0-40+000 in reaches | Malakand Irrigation Division Malakand | 0.3 | 0.294 | 12.19 | 1910.43 | 7.61 | 7.61 | 1910.43 | 100% | Completed
66 | Removal of Heaps / Clearance of Shamozai Disty/ Syphon and Likpani Minor from Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.392 | 17.67 | 2730.62 | 13.01 | 13.01 | 2730.62 | 100% | Completed
67 | Removal of Heaps / Clearance of Dheri Minor and Tail Minor Head to Tail in reaches | Malakand Irrigation Division Malakand | 0.15 | 0.147 | 7.01 | 1211.68 | 6 | 6 | 1211.68 | 100% | Completed
68 | Bazai Main Canal Head Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 10.5 | 10.5 | 1168.075 | 100% | Completed
69 | Wartair Disty | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 6 | 587.93 | 6 | 6 | 587.93 | 100% | Completed
70 | Kharki Disty No. 02 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 | 3.3 | 1272.34 | 3.3 | 3.3 | 1272.34 | 100% | Completed
71 | Additional Minor No. 03, 06 and Bazai Disty No. 01. | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | 16.8 | 1272.14 | 3 | 3 | 1272.14 | 100% | Completed
72 | Bazai Main Canal, Syphon No. 4431, 5851, 12530, 13590, 14842, 18400, 47527 & 58853 | Malakand Irrigation Division Malakand | 0.1 | 0.0975 | [5 empty] | 70% | Work in Progress
73 | Bazai Disty No. 04, Bazai Minor No. 09, 11 and 12. | Malakand Irrigation Division Malakand | 0.27 | 0.26625 | 15.2 | 4070 | 9 | 9 | 4070 | 100% | Completed
74 | Clearance of Syphon 79205, 93480 and 97962. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | [5 empty] | 20% | Work in Progress
75 | Bazai Disty No. 03 and Bazai Minor No. 05. | Malakand Irrigation Division Malakand | 0.1 | 0.975 | 20.5 | 1907.82 | 7 | 7 | 1907.82 | 100% | Completed
76 | Bazai Main Canal Tail Section | Malakand Irrigation Division Malakand | 0.275 | 0.2681 | 19.5 | 1168.075 | 4.78 | 4.78 | 1168.075 | 100% | Completed
77 | KM-1 RD: 0-2976 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 143.26 | 0.9 | 0.9 | 143.26 | 100% | Completed
78 | KM-1 RD: 0-1500, 22000-29000 | Malakand Irrigation Division Malakand | 0.05 | 0.0478 |  | 410.62 | 2.6 | 2.6 | 410.62 | 100% | Completed
79 | Bazai Main Canal RD: 79500 to RD: 84500 | Malakand Irrigation Division Malakand | 0.302 | 0.296 | 39 | 649.87 | 1.5 | 1.5 | 649.87 | 100% | Completed
80 | Additional Minor No. 05 RD: 0-4750 | Malakand Irrigation Division Malakand | 0.0218 | 0.0212 | 1.44 | 252.19 | 1.44 | 1.44 | 252.19 | 100% | Completed
81 | Bazai Main Canal RD: 97000 to 103000 | Malakand Irrigation Division Malakand | 0.1101 | 0.1097 | 39 | 1274.24 | 1.82 | 1.82 | 1274.24 | 100% | Completed
82 | Bazai Main Canal RD: 110000 to 127920 | Malakand Irrigation Division Malakand | 0.1361 | 0.1334 | 39 | 1574.99 | 5.46 | 5.46 | 1574.99 | 100% | Completed
83 | Silt & Shingle Clearance of P.C Minor from RD 0+000 To Tail in reaches | Malakand Irrigation Division Malakand | 0.4 | 0.388 | 12.881 | 1851.77 | 7.62 | 7.62 | 1851.77 | 100% | Completed
84 | Clearance of Shingri Minor from RD 0-17250 in reaches. | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.309 | 530.92 | 2.347 | 2.347 | 530.92 | 100% | Completed
85 | Clearance of Meherdi Minor from RD 0-31000 in reaches. | Malakand Irrigation Division Malakand | 0.3 | 0.291 | 9.451 | 2167.5 | 8.382 | 8.382 | 2167.5 | 100% | Completed
86 | Clearance of Kalu Branch from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.33 | 0.3218 | 11.563 | 1318.25 | 5 | 4.6 | 1212.79 | 92% | Work in Progress
87 | Clearance of Hathian Minor from RD 0-tail in reaches. | Malakand Irrigation Division Malakand | 0.05 | 0.04875 | 2.1 | 265.88 | 1.73 | 0.96 | 146.23 | 55.49% | Work in Progress
88 | Clearance of Jalala Disty from RD: 29000 to Tail in reaches | Malakand Irrigation Division Malakand | 0.37 | 0.3607 | 14.024 | 1476.73 | 5900 | 5400 | 1351.5 | 91.52% | Work in Progress
89 | Clearance of Pirsaddo Disty, Ghano Minor and Qutab Gharh Minor from : H-Tail to Tail in reaches. | Malakand Irrigation Division Malakand | 0.35 | 0.341 | 1.88 |  |  | 0 | 0 | 0% | Not yet started
90 | Clearance of Shergarh Minor from Head to Rd:12+000 in reaches. | Malakand Irrigation Division Malakand | 0.15 | 0.146 | 7.752 |  |  | 0 | 0 | 0% | Not yet started
91 | Clearance of Shergarh Minor from Rd:12+000 tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 7.752 | 1195.13 | 6000 | 5500 | 956.83 | 91.66% | Work in Progress
92 | Clearance of Spokanda Disty from RD: 18000 to Tail in reaches. | Malakand Irrigation Division Malakand | 0.25 | 0.2437 | 5.659 | 1215.5 | 4.97 | 1.52 | 493.17 | 30.58% | Work in Progress
93 | Silt & Shingle Clearance of Spokanda Disty from 0-18000 | Malakand Irrigation Division Malakand | 0.2 | 0.194 | 5.488 | 771.85 | 2.743 | 2 | 563.45 | 72.91% | Work in Progress
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086